Components of communication strategy:

Phase I:	Today through selection of buyer, (June 9 or 10) unless major leak occurs

Discuss regional and company strategy overall, but not Project California

Phase II:	Occurs only at significant leak

Discuss primarily regional strategy, but some California elements as deemed necessary

Phase III:	No leak and upon selection of buyer, likely June 12

##### Incorporate announcement of transaction in strategy message

| # DUE DATE | ### ACTIVITY | ### COMMUNICATION TOOLS | ### LEAD RESPONSIBILITY |
| --- | --- | --- | --- |
| 3-17 4-15 3-22 3-22 4-15 5-1 | # COMMUNICATION TOOLS Develop all central tools that will be basis for all materials written for key audiences Send corporate materials to 34 Park | “Story”/white paper Version 1 on SA, CA story Version 2 with California specifics Comprehensive internal Q and As Talking points on issues Develop reproducible maps, Fact sheets including background on assets, bios on key asset staff Logo sheets, corp. profile, annual report, gift items | KK KK KK SW SW |
| 3-25 3-25 3-17 3-20 6-? 3/25 Ongoing 4-1 6-10 6-1 5/15 5/30 | # MEDIA RELATIONS Leak policy and procedures written and approved Leak statement and Q and As written and approved. Determine in what circumstance (if any) disclosure before deal is necessary --Stock price movement? --Regulatory filings? --Other? Refine media talking points on SA/CA strategy Develop media calendar of opportunities for story placement in SA and trades Monitor media and adjust strategy if necessary. Provide clips from region and on potential buyer issues to team daily beginning March 15 Media coaching for spokesmen Detailed plan for news conference announcing transaction Develop California sale announcement release jointly with buyer (preferred) Develop release on completion of transaction | Policy Statement (no disclosure) Release (if required) Talking points Calendar Clip service Release and press kit Release | KK KK KK PR/RR RS All KK KK KK KK (DC, DH) KK KK KK |
| 3/22 4/1 5/1 | # EMPLOYEE COMMUNICATION Draft letter on California strategy to No Cal and So Cal employees Draft memo on international strategy for all Company employees Include story in next company newsletters (CA, SA and corp) international strategy | E-mail memo E-mail memo Article | KK KK KK |
| 3-24 3-21 3-24 5-1 | # STAKEHOLDER COORDINATION Develop comprehensive contact list of all audiences and who internally owns each, including addresses, phone, fax --Contacts in target companies --Customers --California and international general, financial and trade media --Investors/analysts --Rating agencies --California/US federal officials --Local, state, regional officials --Regulators --NGOs, environmental, advocacy and special interest groups. Develop list of speaking opportunities to introduce regional strategy Develop comprehensive announcement/rollout plan for dealing with all stakeholders Incorporate international strategy message into management remarks at annual meeting; prepare relevant Q and As | Excel list Speech Plan Bullet points and Q and As | MB MS DC KK PR JM RS RS RS KK KK KK KK |
| 4-1 4-1 3-25 3-17 4-25 | # RESEARCH AND ADMINISTRATION Complete Lexis/Nexis search on buyers including past media stories Review buyer websites Develop budget Select PR firm # Name internal PR team to assist | Report Report Budget | KK KK KK KK KK |
| 5-19 | # BUYER COORDINATION Upon buyer signings, develop PR plan(s) for activities after transaction | Develop PR plan(s) | KK |
| 4-15 | # CONTINGENCY PLANNING Plan for all potential contingencies --No buyers --Separate sales for SoCal, NoCal --Regulatory objections --Attacks by consumer groups, NGOs, unions --Other | Strategy document | KK |

# Assignments

KK	Kelly Kimberly

SW	Stacy Walker

PR	Paula Rieker

RR	Rex Rogers

RS	Rick Shapiro

DC	Diomedes Christodoulou