LONG-TERM NATURAL GAS PURCHASES TIME SCHEDULE

FOR THE CITY OF LAS CRUCES, NEW MEXICO AND

RIO GRANDE NATURAL GAS ASSOCIATION

Request for Qualifications

8/1	Advertisement to press				AUG. 1

8/5	1st add						AUG. 5

8/12	2nd add						AUG. 12

8/16	Registration of bidders				AUG. 16

8/17	Addendum if any					AUG. 17

9/18	Receipt of qualifications and draft contracts		SEPT. 18

9/28 	Members meet and qualify bidders	                             SEPT. 28

Invitation to BiD

10/17	Invitation to Bid mailed				OCT. 17

10/31	 Questions received				OCT. 31

11/17	Addendum (if any faxed)				NOV. 17

01/16/02	Receipt of bids					JAN. 16,2002

01/17   	Open bids at 2:00 p.m.		                            JAN. 17

01/23	Members review bids				JAN. 23

04/24      Negotiate final agreement                                            APR. 24

04/29	Members recommend awards			APR. 29

05/6	Council and Board award contracts			MAY 6

07/10     Contracts executed				JULY 10

08/15	Agency agreements, Passport, Visa to El Paso	AUG. 15

9/1	New service begins				Sept. 1, 2002