# Draft Timeline

| Activity | By when |
| --- | --- |
| VR launched – relevant managers communicate to teams | 8/10 |
| ## BU Give Briefing to Groups ( See Guideline Document ) | 8th & 9th |
| BU and Heads of Department Complete Selection Criteria Data Worksheet | 8th – 19th |
| VR closes and VR lists finalised between relevant business units and HR | 19/10 |
| HR Calculate CR redundancy payments | 19/10 onwards |
| HR Prepare CR individual letters | 19/10 onwards |
| CR group announcements (except Metals) | 21/10 |
| VR paperwork and exits completed | 26/10 |
| Metals CR announcement | 28/10 |
| ## Ken Lay addresses all EEL employees | 29/10 |
| Conduct CR redundancy interviews and finalise all CR (except Metals) | 30/10 |
| Conduct CR redundancy interviews and finalise all CR for Metals | 5/11 |