CAISO Audit

We presume audit team is feeding information to FERC staff informally, now

Audit report draft:						January 9, 2002

Final report due:						January 16, 2002

Comments on audit, if allowed:					    Late January (Comnes/Perrino to produce first draft)

Estimated date of FERC action: 	Not expected this year

California Refund Proceeding

Issue One (the applicable mitigated market clearing prices)

Responsive testimony Due:						November 6

Trial schedule:								December 17-21

Issues Two and Three (the amount of refunds owed by parties and offsets)

Testimony Due:							January 25, 2002

Trial Date:								February 11-15, 2002

Judge to certify findings to Commission:				March 8, 2002

Expected Date for FERC Action:	End of second quarter 2002

ICAP

Nothing Due

Estimated Date of FERC Action:			No action expected this year

Interconnection Proceeding

Comments Due:	Industry-Wide Consensus Document due December 14

Comments Due:	December 21 (Susan drafting comments)

FERC Meetings:	Every week from now until December 13 consensus filing

Expected date for FERC Action:					Mid-January on Procedures

Procedures for Cost Issues:						Procedures not established yet

Market Based Rates

Comments Due:	Comments due approximately January 25 (check Fed Reg notice for exact date)

Draft By:	Alan Comnes with Assists from Christi and Sarah

FERC Action:	Approximately end of 1st quarter of 2002

Marketing Affiliate, Standards of Conduct

Comments due 								December 20

Estimated date for draft circulation:  						November  13

(Leslie drafting with input from Hartsoe and others)

Estimated Date for FERC Action:  	First Quarter 2002

MidWest/Allliance RTO Proceedings

Comments Due:	Various filings submitted with comments due throughout November

Expected date for FERC Action:	Action on scope/governance could be issued by end of year

Northeast

Nothing is due

Estimated Date of FERC Action:	Ruling on scope/goverance could be issued by end of year

Pacific Northwest Refunds Proceeding

Hearing has concluded, comments

on Judge’s Initial Decision were filed:				October 31

FERC Action:	FERC action before the end of the year is unlikely

RTO Energy Market Design (RTO Week)

Comments Due:							November 19

Draft by:  								COB November 15

Sarah Novosel

Estimated Date for FERC Action:					Not expected this year

Type of FERC Action	Could be a Policy Statement Ordering More Procedures

Southeast

Nothing is due

Estimated Date of FERC Action:	Ruling on scope/goverance could be issued by end of year

WestConnect RTO (For-profit TransCo)

WestConnect filing made by PTOs 					October 15

Comments Due							November 15

Estimated Date for Draft Circulation 					November 9 (Perrino/Alvarez)

Estimated Date for FERC Action:                                                     Action not expected this year

West-wide price cap/mitigation

Comments due:							 November 9

WPTF and possibly IEP will also file and

EPMI will coordinate

Estimated date of FERC action: 	November 20 or December 17 on "tweak"  (these are the last two Commission meetings this year)

Items for Discussion with Christi, Jim and Sarah

Next steps, where do we go from here

Other RTO ideas