FORT PIERCE REPOWERING PROJECT

TIMETABLE

##### September 6, 2000

| Date | #### Description | Team | Status |
| --- | --- | --- | --- |
| 8/17/00 | Team Meeting | Origination | Completed |
| 8/18/00 | Determine project structure and economics | Origination | In progress |
| 8/18/00 | Review EPC costs | Engineering | Completed |
| 8/21/00 | Hire outside counsel to assist with all legal agreements | Legal | Andrews & Kurth hired |
| 8/22/00 | Initiate turbine procurement process | Engineering | In progress (pending economics/legal) |
| 8/22/00 | Review and revise modeled property taxes | Property Tax | Completed |
| 8/22/00 | Review and revise O&M costs | OEC | Completed |
| 8/22/00 | Review and update gas pipeline cost | Pipeline | In progress |
| 8/22/00 | Review project structure and economics | Power Structuring | In progress |
| 8/22/00 | Secure que spots for all long-lead items | Engineering | In progress (pending economics/legal) |
| 8/22/00 | Setup site visits | Engineering/OEC | 1st meeting 8/30 – 8/31 |
| 8/23/00 | Evaluate potential financing structures | Finance/Origination | In progress |
| 8/23/00 | Review potential project expenditures | Finance/Origination |  |
| 8/23/00 | Setup site visit for gas pipeline construction | Pipeline/Origination |  |
| 8/24/00 | Prepare legal agreements for internal review | Legal | Land Lease & Steam Sales drafts |
| 8/24/00 | Review and revise modeled sales and use taxes | Sales & Use Tax | Tax update in progress |
| 8/24/00 | Submit commitment fee to FPUA | Origination | Completed |
| 8/25/00 | Construction Risk/Operational Insurance | Finance/Origination | Completed/In progress |
| 8/25/00 | Determine cost of purchasing and transporting natural gas | Gas Structuring | Initial review complete |
| 8/28/00 | Determine capacity and energy charge | Power Structuring | 1st pass completed |
| 8/28/00 | Initiate gas pipeline construction discussion with FGT | Pipeline | Level “B” study underway |
| 8/29/00 | Prepare sound quality analysis of site | Development | ###### Completed initial phase |
| 8/30/00 | Discuss EPC costs with NEPCO/Third Party | Engineering | 1st estimate due by 9/15; 2nd by 10/15 |
| 8/30/00 | Review of Land Lease Agreement | Origination/Legal | In progress |
| 8/30/00 | Review project expenditures | Finance/Origination | On going |
| 8/31/00 | Provide copy of Land Lease Option to FPUA | Development/Origination | Completed |
| 9/01/00 | Finalize modeled property tax amounts | Property Tax |  |
| 9/01/00 | Finalize modeled sales and use tax amounts | Sales & Use Tax |  |
| 9/01/00 | Review of Steam Purchase, Tolling and Water Supply Agreements | Origination/Legal | In progress |
| 9/05/00 | Determine financing structure name | Finance/Origination | Preliminary “Sunrise Repowering” |
| 9/05/00 | Discuss if NEPCO is EPC contractor | Finance/Origination |  |
| 9/05/00 | Finalize heat balancing information | Engineering | In progress |
| 9/05/00 | Prepare preliminary development budget | Development/Origination | In progress |
| 9/05/00 | Review FPUA’s ERP permit | Development |  |
| 9/05/00 | Setup geotech analysis | Development |  |
| 9/06/00 | Finalize cost of purchasing and transporting natural gas | Gas Structuring |  |
| 9/06/00 | Review and prepare EPC contract | Legal/Engineer/Origin |  |
| 9/06/00 | Review draft of Project Development Agreement | Legal/Origination |  |
| 9/06/00 | Review of O&M Agreement | OEC/Legal |  |
| 9/06/00 | Review project expenditures | Finance/Origination |  |
| 9/06/00 | Setup City Council trip to Coyote Springs plant | Engineering | In progress |
| 9/08/00 | Determine gas pipeline construction plan | Pipeline |  |
| 9/08/00 | Determine potential natural gas supplies | Origination/Pipeline |  |
| 9/08/00 | Discuss Land Lease Option with FPUA | Legal/Origination |  |
| 9/08/00 | Finalize financing structure | Finance/Origination |  |
| 9/08/00 | Finalize internal review of O&M costs | OEC/Engineering |  |
| 9/08/00 | Prepare air, special use and waste water permits | Development |  |
| 9/08/00 | Submit air, special use and waste water permits | Development |  |
| 9/12/00 | FPUA/ENA Meeting | Origin/Dev/Engineer | Tentative |
| 9/13/00 | Finalize project expenditures | Finance/Origination |  |
| 9/15/00 | Finalize Land Lease Option and Ground Lease with FPUA | Legal/Origination |  |
| 9/15/00 | Finalize Project Development Agreement with FPUA | Legal/Origination |  |
| 9/15/00 | Finalize site configuration | Engineering |  |
| 9/15/00 | Submit interconnection and transmission agreement | Development |  |
| 9/22/00 | Finalize EPC Contract | Legal/Eng/Tax/Orig/Dev |  |
| 9/22/00 | Finalize gas pipeline construction plans | Pipeline |  |
| 9/22/00 | Secure natural gas supply | Origination/Pipeline |  |