ENRON RISK ASSESSMENT AND CONTROL

DEAL APPROVAL SHEET

| DEAL NAME: | Trailblazer C.S. 601, 602 & 603 | Date DASH Completed: |  |  |
| --- | --- | --- | --- | --- |
| Counterparty: | Kinder Morgan | RAC Analyst: | N/A |  |
| Business Unit: | ETS (EAMR) | Investment Type: | LSTK Bid |  |
| Business Unit Originator: |  | Capital Funding Source(s): | Progress Payments |  |
| Public Private |  | Expected Closing Date: | January, 2001 |  |
| Merchant Strategic |  | Expected Funding Date: |  |  |
| Conforming Nonconforming |  | Board Approval: Pending Received Denied N/A |  |  |

## DEAL DESCRIPTION

Enron Asset Management Resources  (“EAMR”) has proposed to enter into a 3rd party LSTK bid for a design, engineer procure and construction contract with NGPL, a division of Kinder Morgan (“KM”) . Project consists of three compressor stations on the Trailblazer 36” pipeline.  Stations are due in-service 2nd quarter 2002.

The Trailblazer Pipeline is comprised of the following ownership:

- 33% 	 	Enron

- 67%		Kinder-Morgan

The scope of work is the LSTK bid for design, procurement and construction of three natural gas compression facilities:

- Station 601	LOGAN CO. COLORADO 		2-15,000 HP TURBINES/COMPRESSORS

- Station 602	LINCOLN CO. NEBRASKA	1-10,000 HP ELECTRIC COMPRESSION ADDITION

- Station 603	KEARNEY CO. NEBRASKA	2-10,000 HP ELECTRIC COMPRESSION

Upon completion of construction , EAMR will perform performance testing at project turnover.  A 72 hour reliability test is deemed to be the date of in-service.

EAMR requests approval to finance commitments of $2.5 million for the procurement of Engineering and materials to be paid by KM in monthly payments according to a milestone schedule.

ASSOCIATED GUARANTIES –

- Pass through of manufacturers warranties

- Pass through of performance testing penalties to manufacturer

- KM has requested a Standby Letter of Credit for 25% of the construction value or approx $2MM

## SOURCES AND USES OF FUNDS AT CLOSING - ($000)

|  | Sources |  |  |  |  | Uses |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Customer Payments: | $ 45,000 | estimated |  | ### Contract Costs | $ 42,000 est ______ |  |  |  |
| TOTAL | $ 45,000 |  |  | ### TOTAL | $ 42,000 |  |  |  |
| Return Components: | PV @ Capital Price | Cumulative IRR |  |  |  |  |  |  |
| Cash Outflows (hard costs) ($63,421) - | ($42,000) |  |  |  |  |  |  |  |
| Cash Inflows | $45,000 |  |  |  |  |  |  |  |
| Finance Fees | $ 0 |  |  |  |  |  |  |  |
| Bonus Fees | $ 0 |  |  |  |  |  |  |  |
| Total NPV | $ 3,000 |  |  |  |  |  |  |  |

EXISTING EXPOSURE

Bid expenses

## RISKS

| RISKS | DESCRIPTION | COMMENTS |
| --- | --- | --- |
| Payment performance risk | The risk KM defaults on payments due under the construction contract. | EAMR is comfortable with KM’s ability to make payments per the contracts |
| Design Risk | Changes in technical requirements could increase the cost. The size of the facilities are based on information provided by Customer. | EAMR’s pricing assumptions are outlined in the proposal scope of work. If the actual project requirements are not consistent with the project parameters in the contract, EAMR will be entitled to an equitable change order to cover the costs of any such changes. EAMR bears the risk of designing the assets to conform to the existing design specifications. |
| Construction Schedule Delay Risk | Risk of schedule delays. The estimated EPC schedule is 14 months. | Any changes in schedule as a result of delays from contractor’s submittals have been accounted for in the agreement through clearly defined assumptions. In addition, EAMR is entitled to an equitable change order for any delays other than EAMR-caused delays. (Including FERC) |
| Early Termination of Contracts due to Governmental non approval | KM will exercise its right to terminate the contracts in the event of a Force Majeure event. | In the event of KM’s termination of the contracts due to a Force Majeure occurrence, the contracts call for KM to pay EAMR a pro-rata portion of the contract amount based on the percent completion of the project at the time of termination. KM will also be obligated to pay reasonable cancellation fees and demobilization costs as well as pay for all services provided by EAMR prior to the termination event. |

| Interest Rate Risk | No interest rate risk in the transaction |
| --- | --- |
| Equity Risk | Enron is a 33% equity partner in the trailblazer pipeline |
| Credit Risk | KM has an Enron credit rating of ___. This corresponds to an S&P rating of _____. |
| Inflation Risk | Inflation assumption is embedded in the cost components in the model. Time frame of contract is relatively short. |
| Commodity Risk | N/A |

OTHER RAC COMMENTS:

SYNDICATION (ECM):

Immediately syndicatable at current capital price

Syndication within one year at current capital price

Not syndicatable at current capital price

N/A

| APPROVALS: |  | Name |  | Signature |  | Date |
| --- | --- | --- | --- | --- | --- | --- |
| ETS Contributors: |  |  |  |  |  |  |
| Technical Coordinator |  | Arnold Eisenstein |  |  |  |  |
| Technical Support ?? |  | Mike Smith |  |  |  |  |
| Technical Support ?? |  | Greg Matthews |  |  |  |  |
| Project Management |  | Norm Spalding |  |  |  |  |
| Business Development |  | Sarabeth Smith |  |  |  |  |
| Business Development |  | Don Hawkins |  |  |  |  |

| APPROVALS: |  | Name |  | Signature |  | Date |
| --- | --- | --- | --- | --- | --- | --- |
| Enron Capital Management |  | Rod Hayslett |  |  |  |  |
| ETS Management |  | Phil Lowry |  |  |  |  |
| EAMR E&C |  | Jerry D Martin |  |  |  |  |
| ETS Legal |  | Mike Moran |  |  |  |  |
| Business Unit Mgmt |  | Stan Horton |  |  |  |  |

Deal Flow Diagram:

Trailblazer Pipeline Company

Kinder Morgan     67%

NGPL (operator)

Enron	33%

Enron Asset Management Resources

LSTK Bid

Construction

Start Up/Commissioning

Material Procurement

Engineering/Design

DEAL DEFINITIONS

Bid Bond	A letter of credit or surety bond delivered at the time of submission of a bid.  It guarantees that if the bidder is awarded the project that is the subject of the bid, the bidder will execute the relevant project documents in accordance with the terms of the bidder’s bid.

Deal Description	short written summary of the investment.

Deal Name	Unique name for an investment/deal usually defined by Capital Pricing director or Business Unit Originator.

Deal Risk Premium (%)	Premium for a deal derived by a comparison of the transaction volatility of returns to historical sector volatility of returns; additionally incorporates any other adjustments for risks specific to the transaction.  Premium could be negative if the transaction exhibits less risk than is reflected in the unadjusted capital price.

Capital Commitment ($M)	Expected present value of cash outflows in the transaction.

Expected IRR (%)	the discount rate at which the net present value of the expected cash flows would be equal to zero.  This measures the expected return of the transaction but does not incorporate a measure of risk.

NPV @ Capital Price ($M)	Net Present Value at the Capital Price discount rate.

Risk-Free Rate (%)	the rate derived by weighting Treasury curve rates by the expected cash flows in the corresponding periods.

Type of Investment	Specific type of investment.  For example, VPP, LP, loan, equity, alliance, debt, derivatives, refinance, and physical sales.  Sometimes referred to as Instrument Type.

Value at Risk ($M)	The loss in value over a specified period of time (quarterly, daily, etc.) which will be exceeded with a certain probability.  Evaluated based on market comparables.