# TRAILBLAZER STATIONS 601, 602 AND 603

# RECOMMENDATION

THAT WE PURSUE A 3RD PARTY LUMP SUM TURNKEY BIDDING OPPORTUNITY FOR TRAILBLAZER PIPELINE COMPANY (KINDER-MORGAN).

# CUSTOMER

TRAILBLAZER PIPELINE, WITH THE FOLLOWING OWNERSHIP

- 33% 	 	Enron

- 67%		Kinder-Morgan

## SCOPE & ESTIMATED PROJECT SIZE / PROFIT

- ENGINEERING & CONSTRUCTION OF 3 NEW COMPRESSOR STATIONS

  - Station 601	LOGAN CO. COLORADO 		2-15,000 HP TURBINES

  - Station 602	LINCOLN CO. NEBRASKA		1-10,000 HP ELECTRIC ADDITION

  - Station 603	KEARNEY CO. NEBRASKA	2-10,000 HP ELECTRIC

- INITIAL ORDER OF MAGNITUDE ESTIMATE

  - Kinder Morgan Budget - $55MM

  - EAMR Estimate $45-48 MM

- EXPECTED EARNINGS

  - $1MM IN 2001

  - $2MM IN 2002

## PROJECT SCHEDULE

NOTICE TO PROCEED (NTP)	01/15/01

START CONSTRUCTION		07/01/01 (FERC scheduled 06/01/01)

READY FOR SERVICE		06/01/02 all 3 stations per RFQ

12/1/01 potential for 2 stations -  3rd station 02/01/02

## CONTRACTUAL STRUCTURE / SCOPE SPLIT

- RFQ options for Engineering and Procurement Assistance, LSTK and Lease

- EAMR to Bid LSTK (Potential for ECS to bid Lease/Operate)

  - WE TAKE ENGINEERING, PROCUREMENT AND CONSTRUCTION RISK

  - UPRATE OF EXISTING UNIT AT STATION 602 IS T&M

  - DEAL SIMILAR TO PREVIOUS VENTURE WITH TRAILBLAZER STATION 602 (1997)

  - WILL UTILIZE OUTSIDE ENGINEERING FIRM WITH TRAILBLAZER EXPERIENCE

    - UEI BIDDING E&PA SEPARATE -

- WE WILL BE RESPONSIBLE FOR FUNDING PROJECT CASH FLOW after progress payments

- RFQ REQUESTED STANDBY LETTER OF CREDIT FOR APPROX. $2.0 MM

## PROPOSAL MILESTONES

- COMPLETE PROPOSAL W/ PRICING	5 December 2000

- FINAL RAC APPROVAL

- BID DUE					15 December 2000

- EXPECTED AWARD / NTP			15 January 2001

PROPOSAL COSTS

$50,000 – EAMR RISK IF WE LOSE BID

COMPETITION

POTENTIALLY SEVERAL LOCAL E&C COMPANIES, MOST ARE BIDDING E&PA ONLY.

- UEI

- GIEC

- PPP

- MASTER

- FORERUNNER

- TRIGON-SHEHAN

- EPSTEIN

- WILBANKS

- MUSTANG

## HISTORY

- SIMILAR TO STATION 602 SUCCESSFULLY COMPLETED FOR NGPL IN 1997

- ACTUALLY EARNED $2mm PROFIT VS. BUDGET PROFIT OF $1mm (1 STATION)

- GOOD RELATIONSHIP WITH KM/NGPL, A KEY OWNER AND OPERATOR OF TRAILBLAZER

- EECC WAS SUCCESSFUL IN SIMILAR BIDDING SITUATION AGAINST SIMILIAR COMPETITION

RISKS & MITIGATIONS

RISK	MITIGATION

NORMAL PROJECT EXECUTION RISKS	EXPERIENCE & CONTINGENCY

PAYMENT	REGULATED PIPELINE WITH PARTIAL ENRON OWNERSHIP[

BID ADVANTAGES

EECC CONSTRUCTED TRAILBLAZER STATION 602

KM PERSONNEL KNOWN TO ETS PERSONNEL

NGPL/KM STANDARDS SPECIFIED (SIMILAR TO ENRON SPECIFICATIONS)

STANDARD ENRON PRODUCT OFFERING – WILL UTILIZE EQUIPMENT SPECS AND PRICING FROM FGT PHASE 4 & 5