Netco Houston Legal Transition Plan

Draft of 1/9/02

| 1/3 | Finalize draft Online umbrella documents (PA and ETA) | Mark Taylor, Leslie Hansen |
| --- | --- | --- |
| 1/4 | Deliver draft Online umbrella documents to bidders | Louise Kitchen |
| 1/9 | Approve form of employee retention contracts | Michelle Cash |
| 1/10 | Draft Online GTC’s finalized: |  |
|  | Financial | Mark Taylor |
|  | Gas | Mary Cook |
|  | Power | Leslie Hansen |
| 1/11 | Deliver Online GTC forms to purchaser | Mark Taylor |
|  | Facilitate obtaining signatures of key and critical employees to retention contracts | Michelle Cash |
|  | Approve form of employee offer letter | Michelle Cash |
| 1/12 | Discuss required software licenses with purchaser | Anne Koehler, Jay Webb |
| 1/14 | Discussion with purchaser regarding integration of legal department and legal policies and procedures: Contract issues Dispute resolution policies Litigation management Corporate formalities procedures (including Netco formation) Government contractor obligations Employee training Ethics/regulatory/compliance matters Outside counsel selection and retention Banking relationships | Mark Haedicke, Mark Taylor, Elizabeth Sager, Mary Cook, Michelle Cash |
|  | Circulate draft assignment letters for Netco personnel remaining on Enron payroll (for reasons of visa, vesting, etc.) | Michelle Cash |
|  | Obtain list of proposed futures brokers from traders, begin opening accounts (as soon as Netco is formed) | Louise Kitchen, Marie Heard |
|  | Obtain priority list of required natural gas pipeline transport agreements from traders | Jeff Hodge |
|  | Begin application process for required software licenses (see attached schedule) | Anne Koehler |
|  | Begin legal review of completed Online password applications | Tana Jones, Leslie Hansen, Gerald Nemec |
|  | Meet with commercial teams to discuss trading contract forms and processes | Contract team |
| 1/14-1/25 | Participate as needed in commercial marketing efforts attending road show presentations regarding new business | Elizabeth Sager, Mark Taylor, Carol St. Clair Francisco Pinto-Leite (Mexico) |
| Later of 1/14 or as soon as Netco is formed | File application with FERC for a power marketing certificate (earliest possible grant 2/15, more likely after 3/15) | Marcus Nettelton |
|  | Elect Netco corporate officers | Mark Haedicke |
|  | Begin process of opening bank accounts | Travis McCullough |
|  | Begin application process to transfer NYMEX membership to Netco: Transfer Application and Agreements, ABC agreements between Netco and seat holders, guarantee from a Clearing Member | Tana Jones, Mark Taylor |
|  | Begin process for transfer of employee visas and applications for visas | Michelle Cash |
|  | Begin process of applying for membership in power pools (see attached schedule) | Marcus Nettelton |
|  | Begin application process for DOE Import/Export Licenses (for Canada and Mexico) | Marcus Nettelton |
|  | Begin negotiation of pipeline pooling arrangements and transportation agreements based on identified priorities (see attached schedule) | Steve Van Hooser, Jeff Hodge |
| 1/15 | Comments received from purchaser on Online documents |  |
| 1/16 | Draft master agreement forms finalized: |  |
|  | ISDA – | Mark Taylor |
|  | Power – | Leslie Hansen |
|  | Gas – | Mary Cook |
|  | Master Netting Agreement – | Carol St. Clair |
|  | Deliver proposed forms of master trading agreements to purchaser | Mark Taylor |
| 1/17 | Revise Online documents to incorporate purchaser comments, finalize and deliver to online team for upload | (see above) |
|  | Initialize contract negotiation tracking database | Tana Jones |
| 1/18 | Receive from and discuss with purchaser comments to master agreement forms | ? |
|  | Receive form of parent guaranty from purchaser | ? |
|  | Minimum of two futures trading brokerage accounts open | Marie Heard |
| 1/21 | Master Agreement forms revised to incorporate purchaser comments | (see above) |
| 1/22 | Begin drafting master agreements for counterparties based on Credit dept. input | Contract team |
| 2/4 | Schedule appropriate antitrust, litigation risk, harassment prevention, Chinese wall, and other legal risk management training programs | Mark Haedicke, Michelle Cash |
| 2/28 | Approx. six futures trading brokerage accounts open | Marie Heard |
| 3/32 | Compensation audit (for equity purposes) | Michelle Cash |
| 4/23 | NYMEX Membership Committee meeting | Tana Jones, Mark Taylor |
| 5/1 | NYMEX Board meeting to approve membership application | Tana Jones, Mark Taylor |