Memorandum

To:	Louise Kitchen

From:	Chris Calger, Ben Jacoby, Brett Wiggs

Date:	July 5, 2001

Re:	Enron Americas Turbine Book (“Turbine Book”)

The following describes our understanding and agreement with respect to the Turbine Book.  If necessary, we are prepared to discuss at your convenience.

Ownership:

- Chris Calger, West Power Origination

- Ben Jacoby, East Power Development

- Brett Wiggs, South America

Scope:

- All turbines and related equipment (“Turbines”) under the control of Enron Americas

Carrying Cost/Gain Recognition:

- Turbines are carried at the lower of cost or market

- Each owner has a 33% interest in the Turbine Book

- Gains, losses and carrying charges are split evenly by the owners subject to provisions for Allocated Turbines (see below).

Allocation:

- Turbines within the Turbine Book are either Allocated or Available

- Each owner’s business unit is able to market or place any of the Available Turbines

- Interest and other carrying charges on Available Turbines are split evenly by the owners

- Any owner can allocate a Turbine to a specific project to enable its business unit to execute deal agreements, finalize development, etc.

- Interest and other carrying charges on Allocated turbines are paid by the business unit reserving the Turbine

- Turbines transferred from Available to Allocated that get closed will be transferred at the market price (if the owners can not agree on market price, the price shall be cost)

- Any owner can transfer a turbine from Allocated to Available

- Transfer price shall be cost

- For clarity, carrying charges are paid by the business unit when Allocated, split evenly when Available

- Transfer price for Steam Turbine shall be $1 MM.

Dispute Resolution:

- EA Office of the Chair

Turbine Book Objectives:

- Centralize the management of EA’s Turbine positions

- Manage price, market and technical risk associated with Turbines

- Monetize existing Turbine position at highest risk-adjusted value

- Ensure merchant business has access to Turbines for origination and development opportunities

General Strategy:

- Assign responsibility to technical, legal and commercial personnel for each Turbine

- Maintain legal and technical information at each owner’s business unit

- Integrate Turbine Book accounting and reporting into owner’s P&L and RAC Turbine Book

- Identify plan for each Turbine with appropriate milestones

- Utilize multiple distribution channels to market or place Turbines – brokers, originators, developers

- Motivate Enron personnel to focus on Turbine Book Objectives – think globally, act locally.

- Measure and report progress monthly

Turbine Summary:

| Model | Units | Allocation | Delivery | Cost |
| --- | --- | --- | --- | --- |
| ABB11N1 | 2 | Available | Now | $30.0 MM |
| 501D5A | 1 | Available | Now | $28.0 MM |
| MH1501F | 1 | Ft. Pierce | Now | $43.6 MM |
| MH1501F | 3 | Riogen | 9/01 – 5/02 | $117.3 MM |
| 7EA * | 2 | Northwestern | Now | $40.0 MM |
| 7FA | 1 | Longview | 12/02 | $40.0 MM |
| Steam Turbine | 1 | Available | Now | $0.0 |
| Total: | 11 |  |  | $298.90 |
| 7FA - Sythe | 3 | Evaluation | 2001 | $120.00 |
| LM6000 - PGE | 1 | Evaluation | 2001 | $16.5 MM |

* Under definitive purchase and sole agreement with Northwestern.

Initial Plan/Status:

RioGen MH1501FMHI:

Execute sale of RioGen site package with site, permits and three MHI turbines.  Will issue base term sheet with minimum amount we are willing to accept to three parties by 7/6/01 with requirement to respond within three weeks.  All parties have already completed initial due diligence on the project.  If not progressing satisfactorily within four weeks, change classification of turbines to Available.  Permit other sites for MH1 technology.

SW501D5A: Have received recent offers for the subject unit indicating a FMV of $29 - $30 million. Sale is somewhat complicated by status of the damaged generator as the insurance company has raised issues regarding payment of the claim, and SW is claiming risk of loss resided with Enron. Our current sales position is that any buyer taking the unit will have to step into our position as regards the damaged generator. This may have to be revisited in the next several weeks if we are not able to secure a buyer willing to take this position.  Engage new broker, Navigant Consulting, to hold auction.

Ft. Pierce MHI501F: This turbine is tentatively allocated to the Ft. Pierce project. As this turbine was originally purchased under a contract for two units earmarked for the Brazil market, we are currently negotiating a breakout contract with MHI that includes appropriate NOx emission warranties and other terms required for deployment in the US market.

Longview 7FA:  Development has progressed and is expected to be complete September 30, 2001.  EPC contract negotiations continue with Modern Continental, expect to finalize August 31.  Sale process has been initiated with initial bids due August 1, 2001.

Canada Treaty:

- Enron Canada Corp. (ECC) would continue to market the units through September 1, 2001.

- Other EA business units would during this period look at incorporating the units into sites across the Americas.

- Effective September 1, 2001, the prime responsibility for the units would move over to the Turbine Book.

- The units would be transferred at a deemed value to $30 MM US (the “Transfer Price”).

- ECC would take a write down on the cost basis as of September 1, 2001.

- Effective September 1, 2001 the Turbine Book would assume the downside risk of a sale below $30 MM US.

- If any of the parties ECC is currently dealing with on its short list dated June 25 ultimately buys the units after September 1, 2001, ECC would get all of the origination above the Transfer Price less carrying costs from September 1, 2001 less a $1 MM US brokerage fee to be paid to the Turbine Book.

- If the units are sold to a party not currently in discussions with ECC after September 1, 2001, ECC would receive no origination.