| UNCF Debrief Meeting Notes |  |
| --- | --- |
| Thursday, October 4, 2001 |  |
| Good (Fabulous, Great, Wonderful) | Improvements |
| - Team Commitment - Fun – We enjoyed ourselves and in spite of the weather, it felt like a family reunion. - Food – The food was labeled as awesome, many can’t wait until next year. - Prizes - Form Distribution - Organization/Team Work - Timing of UNCF kickoff - ETV ad - Meetings & Lunches were productive - T-Shirt Distribution and Tracking - Corporate Sponsorship/Logo - Walk site - Amount of contributions - Timeliness with deadlines for contribution | - Corporate support – Challenges & executive sponsorship - Improve communication of strategy - Kiosk, Energizer, Body Shop, EFCU, E-Speak, (Volunteers, Communication & Scheduling) - Preparation of walk site (Laminate tent signs) - Resolve budget issues with Community Relations - Secure tables for the black tie gala more timely - Bring back unused forms - Create factsheet - Secure brochures - Deliver walker data sooner to team members for printed sign in sheet/ provide additional blank sign-in sheets |

New Ideas/Concepts & To Do Items

- Create Walkathon Project Timeline - Graduation Cap Pledges & Pins - Historical Reference - Prepare Standard Operating Procedure for the walkathon that will include: - Prize Process - Site setup - Marketing, Communications, & Fundraising efforts - Catering - Prewalk Process - Matching (Policy) - Corporate Sponsorship from vendors