## Power Deal Validation and Consumption Band Analysis

# Accomplishments 9/4 – 9/11

- Organized and staffed KPMG power database team (led by Randy Wilson) - Developed Access database which will store consumption band information, awaiting final approval of Steve Fisher, Chris Stokley, and Kristin Albrecht - Discussed contract structures in various regions to better understand consumption band requirements - Reviewed approximately 20 contracts to validate field requirements in Access DB and validation information in contracts and other sources - GNO deal effort underway - Gathering contracts - Reviewing contract language - Gathering/reviewing historical usage and billing

# Overall Project Approach

GNO Deals (Murray O’Neil/Brenda Herod) - Focused on “quantifying” consumption band value of historical delivery on GNO deals - Mark Denner’s group and two KMPG contractors

Non-GNO Deal Validation Process (Kristin Albrecht/Steve Fisher) Phase 1 – Define Database Requirements – 90% Complete, 100% Complete by 9/12 - Interview key personnel involved in development of contracts - Review sample of contracts - Understand Everest team requirements for data - Finalize field requirements for Access database and validation fields - Create Access database Phase 2 – Obtain Data and Supporting Contracts and Design Process for Capture of New Deals – Estimate 100% Complete by 9/14 - Design process and obtain approval from all parties (Deal Capture, Global Contracts, etc.) - Determine contract sources (Global Contracts, Legal, Originators, Documentum, LiveLink, etc.) - Gather contracts (several sources dedicated to gathering of contracts) - Obtain RPS download with defined data requirements - Obtain CSC billing and settlement information Phase 3 – Validation of RPS Data (Steve Fisher and KPMG Consultants) - Population of Access database with RPS data - Comparison of RPS data to contracts - Comparison of CSC settlement data to RPS data - Comparison of utility billing statements to RPS and CSC data - Contracts accumulated not currently found in RPS are validated and cleared Phase 4 – Management Validates Access Database - Appropriate review by Enron management to ensure appropriate deal capture and validation of deal terms - Database is maintained with new deals until date of data transfer to Everest team Phase 5 – Consumption Band Analysis - Chris to fill in bullet points Phase 6 – Data Transfer to Everest Team - Complete and validated contract information handed off to Everest team for input into new power system