December 13, 2000

James Mackey

Director of Project Management

Siemens Westinghouse Power Corporation

MC 552

4400 Alafaya Trail

Orlando, FL  32826-2399

Subject:	Letter Agreement Regarding W501F, Year 2000, Peaker Plant and W501D5A, Year 2000, Peaker Plant and Southeastern, Peaker Plant Project (Philippines Resale) and The Blue Girl Project

Dear Mr. Mackey:

Bill Monahan of Siemens Westinghouse Power Corporation (“SWPC”) and I, on behalf of Enron North America (formerly Enron Capital and Trade Resources), Enron Equipment Procurement Company, LJM2–Turbine LLC and NEPCO (“Enron”) have had several meetings and an exchange of proposals in an effort to resolve issues arising out of the Gleason and Wheatland Peaker projects (“the Projects”).  The issues relating to the Projects are as follows:

- Enron’s claim for delay liquidated damages for the Gleason and Wheatland Peaker projects (“the Projects”)

- Enron’s claim for heat rate liquidated damages relating to the Projects; and

- Maximum output limitations on the combustion turbine units for the Gleason plant of 182 MW’s.

- The forfeiture of Enron’s reservation deposit of $1,204,350 based upon the expiration of the reservation option agreement between Enron and SWPC for the purchase of one W501D5A (“Blue Girl”) turbine generator set.

To resolve the aforementioned issues related to the Gleason and Wheatland Peaker projects and the forfeiture of the Blue Girl turbine reservation deposit, the parties have negotiated the following proposal:

- Enron will forgive both the Delay and Heat Rate Liquidated Damages for the Gleason facility and the Wheatland facility and release SWPC from any claims relating thereto;

- SWPC will allow the three Gleason units to each have a maximum operating capability of 185,000 kW and will reset the control curves accordingly within seven (7) business days of complete execution of this agreement.

- Within seven (7) business days of complete execution of this agreement, SWPC will provide written notification to Enron that operation of the Gleason units up to and including 185,000 kW is within normal operating parameters and operation up to and including this level will not invalidate the warranty;

- SWPC agrees that the letter allowing increased power levels up to 185,000 kW at the Gleason facility can be presented to potential purchasers of the facility;

- SWPC agrees that the Brownsville, Gleason and Wheatland contracts and associated warranties may be assigned to limited liability companies owned in whole or in part by an Enron entity pursuant to the terms and conditions of the Gleason and Wheatland contracts, and that Enron will not be required to maintain an equity position in these companies. SWPC further acknowledges that the assignment of the contracts and the transfer of equity will not impact any warranties or other provisions of the assigned contracts.

- Enron agrees that SWPC has met Contract noise guarantees at the Gleason, TN facility.  SWPC and Enron agree to continue their joint efforts in exploring actions to lower the low frequency attenuation from the turbines at the Gleason, TN facility. This joint effort will continue through the warranty period as described in the contract.

- SWPC agrees to assist Enron in providing technical information (including copies of the turbine purchase contracts, as edited in the sole discretion of SWPC, and any relevant technical bulletins) to certain third parties for a period of twelve (12) months after the complete execution of this agreement as required for the sale of the Gleason, Wheatland and Brownsville facilities.  Prior to closing on the sale of each facility, this information will be limited to information which is currently available to Enron, is of a technical nature only, and shall be used solely for the purpose contemplated herein.  Nothing in this agreement shall require SWPC to disclose information it otherwise wishes to withhold.  The information will be supplied to no more than three potential buyers per facility.  As a condition of release, the third parties will be required to execute confidentiality agreements furnished by SWPC.

- Enron will issue payment of $1,567,099 to SWPC within ten (10) business days of complete execution of this agreement as settlement of the following:

- $2,397,442 from Enron for settlement of Gleason unpaid invoices;

- $708,704 from Enron for settlement of Wheatland unpaid invoices;

- less $243,994 from SWPC for backcharges from Enron and all Enron Subsidiaries for Wheatland;

- less $495,053 from SWPC for backcharges from Enron and all Enron Subsidiaries for Gleason;

- less $800,000 from SWPC as settlement of all outstanding issues.

- Enron and its subsidiaries waive all currently known claims for payments from SWPC associated with delivery, construction, and startup for the Gleason and Wheatland projects, but reserves all rights under these contracts as to other claims which may arise;

- Enron waives any claim for refund of the Blue Girl reservation deposit payment; and

- SWPC waives all currently known claims for payments from Enron associated with delivery, construction and startup for the Gleason and Wheatland projects, but reserves all rights under these contracts as to other claims which may arise.

- Both Enron and SWPC agree that no contracts or projects not specifically mentioned in this letter will be impacted or affected by this agreement.

Except as modified by the above proposal the terms and conditions of the Gleason and Wheatland Purchase Contracts will remain in full force and effect.  Upon acceptance by signing and returning a copy of this letter, both Enron and SWPC will agree in overall full and final settlement the amount of $1,567,099 (One million, Five hundred sixty seven thousand and ninety-nine dollars) to be paid to SWPC for the work carried out on both the Gleason and Wheatland Purchase projects.

I trust that the proposal will be acceptable to Siemens Westinghouse and await your response.

This letter may be signed in counterparts and the provisions hereof shall be fully binding upon all of the signatory parties.

Sincerely,

Mitch Robinson

Director

ACCEPTED AND AGREED:

Siemens Westinghouse Power Corporation		Enron North America Corp.

By:________________________________		By:_________________________________

Date:______________________________		Date:_______________________________

LJM2-Turbine, LLC

By: _______________________________

Date:_______________________________

Enron Equipment Procurement Company		National Energy Production Corporation

(NEPCO)

By:_______________________________		By:_________________________________

Date:______________________________		Date:_______________________________