Enron Project Schedule (Proposed)

Assumptions::

- Enron will transfer their option to the City sometime next week, so action to exercise it can be on the August 14th agenda.

- The City will close on the property sometime between the City Council's August 14th and August 28th meetings.

- We will have a metes and bounds description of the property in-hand by Monday, August 21 (whether or not closing has taken place)

Timeline #1 - no adjacent property notice of any kind prior to effective annexation date

- August 22 - 	staff prepares Resolution for annexation of City-owned property

- August 28 - 	City Council adopts resolution and sets date of public                   hearing for September 11, 2000.

- September 11 - 	annexation adopted

- September 12 - 	request for tap can move forward

- September 29 - Planning staff mails notices to adjacent property owners for Planning Board meeting on October 10.  Notice will include NCNG  or CP&L, whichever owns the property across the street from the subject site,

- October 10 - 	Planning Board considers city recommendation for new zoning (probably I-2CU, with a site plan attached as a condition.  Site plan must meet all the special use conditions for a Utility Substation

- November 13 - City Council adopts zoning, including the conditional use.  No Board of Adjustment action is required.

Timeline #2 - adjacent property notice for zoning hearing at Planning Board is mailed  prior to effective annexation date

- August 22 - 	City Council Agenda memo - staff prepares Resolution for annexation of City-owned property

- August 28 - 	City Council adopts resolution and sets date of public                   hearing for September 11, 2000.

- Sept. 1 -	Planning staff mails notices to adjacent property owners for Planning Board meeting on September 12.  Notice will include NCNG  or CP&L, whichever owns the property across the street from the subject site.

- Sept. 11 - 	Annexation adopted by City Council

- Sept. 12 - 	Request for tap can move forward

- Sept. 12 - 	Planning Board considers staff recommendation for new zoning (probably I-2CU, with a site plan attached as a condition.  Site plan must meet all the special use conditions for a Utility Substation, which are attached)

- October 9 - 	City Council adopts zoning, including the conditional use.  No Board of Adjustment action is required.

SPECIAL USE REGULATIONS FOR UTILITY STATION (NEEDS TO BE ADDRESSED IN THE SUBMISSION FOR ZONING)

Use--Utility Station or Substation:

Special use districts: Any district

Minimum lot area: One-half (1/2) acre for staffed utility station or substation. Unmanned, equipment-only substations must comply with applicable dimensional requirements if located in an A-1, R-15, R-10, R-8, R-6, R-6S, R10MF, or MF zone. Unmanned, equipment-only substations in PUD, MA, B-1, B-3, and IP districts are exempt from minimum lot area requirements.

Parking and loading: One (1) space for each regular employee employed primarily at the site at any given time.

Screening and fencing: A screen of not less than six (6) feet in height of dense plant material shall be provided where the lot abuts a residential lot. Electrical substations shall be enclosed by a fence not less than eight (8) feet in height with three (3) strands of barbed wire turned out at the top.

Plans are required and must show:

Structures: Location and approximate size of all existing and proposed structures within the site and all buildings and structures within one hundred (100) feet.

Circulation: Proposed points of access and egress.

Parking and loading: Location and arrangement of all proposed off-street parking.

Other details:

(1)	Proposed provisions for fencing and other protective screening at the lot lines adjacent to abutting residential property.

(Ord. No. 0-90-2, § 2, 1-8-90; Ord. No. 0-91-21, § 4, 4-8-91)