AGREEMENT

By and Between

E-NEXT GENERATION, L.L.C.

and

GE PACKAGED POWER, INC.

For The Purchase Of

ONE LM6000 ENHANCED SPRINT GAS TURBINE GENERATOR SET

TABLE OF CONTENTS

ARTICLE I. DEFINITIONS	1

1.1	Acceptance	1

1.2	Adjusted Electrical Output	1

1.3	Adjusted Emissions	1

1.4	Adjusted Exhaust Gas Energy	2

1.5	Adjusted Exhaust Gas Temperature	2

1.6	Adjusted Heat Rate	2

1.7	Affected Party	2

1.8	Affiliate	2

1.9	Agreement	2

1.10	Applicable Laws	2

1.11	Base Load	2

1.12	Basis Conditions	2

1.13	BTU	2

1.14	Cancellation Charge	2

1.15	Change in Law	2

1.16	Change Order	2

1.17	Claim	3

1.18	Commercial Operation	3

1.19	Commissioning Period	3

1.20	Cover Damages	3

1.21	Day	3

1.22	Delivery Liquidated Damages	3

1.23	Delivery Point	3

1.24	Effective Date	3

1.25	Emissions	3

1.26	Emissions Guarantee	3

1.27	Electrical Output	3

1.28	Electrical Output Guarantee	3

1.29	Equipment	3

1.30	Event of Force Majeure	3

1.31	Event of Purchaser Default	3

1.32	Event of Seller Default	3

1.33	Exhaust Gas Energy	3

1.34	Exhaust Gas Temperature	3

1.35	Extended Warranty Period	4

1.36	Facility	4

1.37	Far Field Sound Level Guarantee	4

1.38	Guaranteed Levels	4

1.39	Guaranteed Unit Delivery Dates	4

1.40	Hazardous Materials	4

1.41	Heat Rate	4

1.42	Heat Rate Guarantee	4

1.43	Heat Rate Liquidated Damages	4

1.44	Heat Rate Liquidated Damages Refund Reduction	4

1.45	Installation Period	4

1.46	Insurability Certificate	4

1.47	Insurance Representative	4

1.48	Interest Rate	4

1.49	kW	4

1.50	kWh or kwh	4

1.51	Lender	5

1.52	Liquidated Damages	5

1.53	Liquidated Damages Events	5

1.54	Major Components	5

1.55	Marketing Agreement	5

1.56	Maximum Liability Amount	5

1.57	Near Source Sound Level Guarantee	5

1.58	Notice	5

1.59	O & M Instruction Liquidated Damages	5

1.60	O&M Manuals	5

1.61	O&M Spares.   Shall have the meaning set forth in Section 3.14.2.	5

1.62	Optional Delivery Point	5

1.63	Order Definition Meeting (ODM)	5

1.64	Output Liquidated Damages Refund Reduction	5

1.65	Patent Indemnities	6

1.66	Payment Date	6

1.67	Payment Schedule	6

1.68	Performance Liquidated Damages	6

1.69	Performance Test	6

1.70	Performance Test Completion Certificate	6

1.71	Performance Test Certificate	6

1.72	Power Purchaser	6

1.73	Primary Warranty Period	6

1.74	Project Manager	6

1.75	Proper Scope Value	6

1.76	Punchlist	6

1.77	Purchase Amount	6

1.78	Purchaser	6

1.79	Purchaser Claimant	7

1.80	Purchaser Indemnitees	7

1.81	Purchaser Related Parties	7

1.82	Purchaser’s Representative	7

1.83	Refund Amount	7

1.84	Related Dispute	7

1.85	Retention Amount	7

1.86	Retention Letter of Credit	7

1.87	Scope of Work	7

1.88	Scope Value Due	7

1.89	Seller	7

1.90	Seller Claimant	7

1.91	Seller’s Indemnitees	7

1.92	Shortfall	7

1.93	Site	7

1.94	Site Delivery Date	7

1.95	Sound Levels	7

1.96	Sound Level Guarantee	7

1.97	Sound Level Test	7

1.98	Sound Level Test Procedures	7

1.99	Specific Performance	8

1.100	Specific Performance Electrical Output Guarantee	8

1.101	Specific Performance Exhaust Gas Temperature Guarantee	8

1.102	Specific Performance Exhaust Gas Energy Guarantee	8

1.103	Specific Performance Heat Rate Guarantee	8

1.104	Specific Performance Levels	8

1.105	Specification	8

1.106	Takeover	8

1.107	Take Over Criteria	8

1.108	Take Over Liquidated Damages	8

1.109	Technical Direction of Installation (TD of I)	8

1.110	Termination Costs	8

1.111	Termination Settlement	8

1.112	Test Procedures	8

1.113	Time for Completion	8

1.114	Training	9

1.115	Transportation Option	9

1.116	Unit	9

1.117	Unit Output Liquidated Damages	9

1.118	Vendor	9

ARTICLE II. RESPONSIBILITIES OF PURCHASER	9

2.1	Purchaser Responsibilities	9

2.2	Purchaser Conduct	9

ARTICLE III. RESPONSIBILITIES OF SELLER	9

3.1	General Obligations	9

3.2	Delivery of Equipment and Documentation.	10

3.2.1	Delivery of Equipment to the Delivery Point	10

3.2.2	Delivery to Optional Delivery Point	10

3.2.3	Impact Indicators	10

3.2.4	Packing List	10

3.3	Relevant Information	10

3.4	Hazardous Materials Notification.	11

3.5	Employment of Trained and Experienced Personnel	11

3.6	Not Used.	11

3.7	Guarantee	11

3.8	Compliance with Governmental Rules	11

3.9	Approved Vendors	13

3.10	Packing and Insurance Surveyor.	14

3.10.1	Packing Recommendation	14

3.10.2	Insurability Certificate	14

3.10.3	Notice of Shipment	14

3.10.4	Compliance with Recommendation	15

3.10.5	Coordination	15

3.11	Financing and Insurance Assistance	15

3.12	Purchaser Permit Support	15

3.13	Order Definition Meeting	15

3.14	Spare Parts.	15

3.14.1	Commissioning Spares.	15

3.14.2	O & M Spares.	15

3.15	Key Personnel	16

3.16	Seller’s Representations	16

ARTICLE IV. RESPONSIBILITY FOR INFORMATION	16

4.1	Purchaser Supplied Information	16

ARTICLE V. PURCHASE AMOUNT AND OTHER CHARGES	17

5.1	Purchase Amount	17

5.2	Taxes and Contributions.	17

5.2.1	Seller’s Responsibility for Personal Taxes	17

5.2.2	Seller’s Responsibility for Taxes	17

5.2.3	Tax Penalties	17

5.3	Changes to the Purchase Amount	17

5.4	Cancellation.	18

5.4.1	Cancellation by Purchaser	18

5.4.2	Marketing Agreement	18

5.5	Suspension or Change of Delivery.	19

ARTICLE VI. PAYMENT TERMS	19

6.1	Payment of Purchase Amount.	19

6.1.1	Payment Periods	19

6.1.2	Payment Schedule	19

6.1.3	Retention Letter(s) of Credit	19

6.2	Payment Disputes	20

6.3	Payments Withheld or Offset.	20

6.3.1	Payments Withheld	20

6.3.2	Offset for Liquidated Damages	21

6.4	Payment of Liquidated Damages.	21

6.4.1	Payment of O&M Instruction Liquidated Damages	21

6.4.2	Payment of Delivery Liquidated Damages	21

6.4.3	Payment of Take Over Liquidated Damages	21

6.4.4	Payment of Performance Liquidated Damages	21

6.5	Payment for Changes	21

6.6	Lien Release	22

6.7	Invoices.	22

6.7.1	Agreement Reference	22

6.7.2	Payee and Address for Invoices	22

6.7.3	Date of Receipt	22

6.8	Method of Payment	22

6.9	Payments Not Acceptance of Work	23

ARTICLE VII. COMMENCEMENT OF THE WORK AND TERMINATION	23

7.1	Not Used.	23

7.2	Not Used.	23

7.2.1	Not Used.	23

7.2.2	Not Used.	23

7.2.3	Not Used.	23

7.2.4	Not Used.	23

7.3	Termination	23

ARTICLE VIII. NOT USED	23

ARTICLE IX. INSPECTION AND CORRECTION OF WORK	23

9.1	Inspections	23

9.2	Resident Facilities	24

9.3	Quality Plan	24

9.4	Notice	24

9.5	Correction of Equipment	24

9.6	Additional Factory Testing	25

9.7	Release for Delivery	25

ARTICLE X. DELIVERY AND PERFORMANCE	25

10.1	Delivery of Documentation.	25

10.1.1	Purchaser Review of Documents	25

10.1.2	Delivery of Final O & M Instructions	26

10.2	Delivery of Equipment.	26

10.2.1	Guaranteed Unit Delivery Dates	26

10.2.2	Inventory Upon Delivery	26

10.2.3	Delivery	26

10.2.4	Extensions of the Guaranteed Unit Delivery Date.	27

10.2.5	Loading Responsibilities at Delivery Point	27

10.2.6	OffLoading Responsibilities at Optional Delivery Point	28

10.2.7	Unit(s) Storage	28

10.3	Delivery Liquidated Damages.	28

10.3.1	Unit Delivery Liquidated Damages	28

10.3.2	Take Over Liquidated Damages	29

10.3.3	Invoicing for Delivery and Take Over Liquidated Damages	30

10.4	Specific Performance Exhaust Gas Temperature and Energy Guarantees.	30

10.4.1	Not Used.	30

10.4.2	Specific Performance Exhaust Gas Temperature Guarantee For Combined Cycle Application of Units	30

10.4.3	Not Used.	31

10.4.4	Specific Performance Exhaust Gas Energy Guarantee For Combined Cycle Application of Units	31

10.4.5	Interaction of Exhaust Gas Energy and Exhaust Gas Temperature with Turbine Net Output	31

10.5	Sound Level Specific Performance Guarantee.	31

10.5.1	Specific Performance Near Source Sound Level Guarantee	31

10.5.2	Specific Performance Far Field Sound Level Guarantee	31

10.5.3	Not Used.	31

10.5.4	Sound Level Test	32

10.6	Specific Performance Exhaust Emissions Guarantee	32

10.7	Electrical Output Guarantees.	33

10.7.1	Electrical Output Guarantee	33

10.7.2	Specific Performance Electrical Output Guarantee	33

10.7.3	Not Used	33

10.8	Heat Rate Guarantees.	33

10.8.1	Heat Rate Guarantee	33

10.8.2	Not Used.	33

10.8.3	Specific Performance Heat Rate Guarantee	34

10.8.4	Specific Performance Guarantee	34

10.9	Performance Liquidated Damages.	34

10.9.1	Unit Output Liquidated Damages	34

10.9.2	Heat Rate Liquidated Damages	34

10.9.3	Most Recent Performance Test	34

10.9.4	Performance Test Required	34

10.9.5	Setting Out of Performance Liquidated Damages	34

10.9.6	Not Used.	35

10.9.7	Seller’s Improvement of Performance	35

10.9.8	Reduction in Performance Liquidated Damages	35

10.10	Maximum Liabilities for Liquidated Damages.	36

10.10.1	Maximum O&M Instruction Liquidated Damages	36

10.10.2	Maximum Delivery Liquidated Damages	36

10.10.3	Maximum Take Over Liquidated Damages	37

10.10.4	Maximum Unit Output Liquidated Damages	37

10.10.5	Maximum Heat Rate Liquidated Damages	37

10.10.6	Maximum Aggregate Liquidated Damages	37

10.11	Liquidated Damages Not Penalty	37

10.12	Performance Tests.	38

10.12.1	Concurrence of Tests	38

10.12.2	Election to Conduct a Performance Test	38

10.12.3	Specific Performance Achievement	38

10.12.4	Timing of Tests.	38

10.12.5	Seller Presence at Tests	38

10.12.6	Test Results	39

10.12.7	Performance Test Procedures	39

10.12.8	Reconduct Tests	39

10.12.9	Not Used.	39

10.12.10	Fittings, Instrumentation and Test Uncertainty.	39

10.12.11	Consumable Spare Parts During Retests	40

10.13	Remedies For Failure to Meet Specific Performance Requirements.	40

10.13.1	Corrective Actions	40

10.13.2	Failure to Achieve Specific Performance	40

10.14	Acceptance	41

10.15	Unit Serial Numbers	42

ARTICLE XI. CHANGE ORDER	42

11.1	Adjustment of Purchase Amount	42

11.2	Purchaser Requested Change Order	42

11.3	Seller Requested Change Order	42

11.4	Adjustment to Guaranteed Unit Delivery Dates	43

11.5	Disputes	43

11.6	Change Order Pricing	43

ARTICLE XII. (NOT USED)	43

ARTICLE XIII. ORDER OF PRECEDENCE	43

13.1	Order of Precedence	43

ARTICLE XIV. WARRANTY	43

14.1	Seller’s Warranty	43

14.1.1	Primary Warranty Period	44

14.1.2	Warranty Clarification	44

14.1.3	Warranty Breach Notice	45

14.2	Extended Warranty Period.	45

14.2.1	Continued Warranty on Corrections or Repairs Performed During the Primary Warranty Period	45

14.2.2	Extension of Warranty Due to Unavailability	45

14.3	Obligations, Responsibilities and Recourse	45

14.4	Not Used.	46

14.5	Limited Warranty	46

14.6	Repairs and Alterations by Others	46

14.7	Termination of Warranty	46

ARTICLE XV. RISK OF LOSS AND TITLE	46

15.1	Risk of Loss	46

15.2	Title.	47

15.2.1	Passage of Title	47

15.2.2	Infringement Cures and Defense	47

15.3	Seller’s Drawings, Etc. for Use by Purchaser	48

15.4	Licensing Procedure	48

ARTICLE XVI. TRAINING AND TECHNICAL DIRECTION OF INSTALLATION	48

ARTICLE XVII. DEFAULT	49

17.1	Events of Default by Seller	49

17.2	Purchaser’s Remedies Against Seller	50

17.3	General Obligations	50

17.4	Payment Obligations.	51

17.4.1	Determination of Obligations	51

17.4.2	Damages and Expenses	51

17.4.3	Cover Damages	52

17.4.4	Settlement	52

17.5	Events of Default by Purchaser	53

17.6	Seller Remedies	53

ARTICLE XVIII. FORCE MAJEURE	53

18.1	Failure to Perform Due to an Event of Force Majeure	53

18.2	Events of Force Majeure	53

18.3	Notice of Event of Force Majeure	54

18.4	Events of Force Majeure	55

18.5	Certain Events Not Excused	55

18.6	Continued Performance	56

18.7	Not Used.	56

18.8	Event of Force Majeure - Delays	56

18.9	Event of Force Majeure - Cost	56

ARTICLE XIX. INSURANCE	56

19.1	Insurance - General	56

19.1.1	All Risk	56

19.1.2	Workers Compensation and Employers Liability Insurance	56

19.1.3	Commercial General Liability Insurance	57

19.1.4	Hull and Protection and Indemnity Insurance	57

19.1.5	Business Automobile Liability Insurance	57

19.1.6	Aircraft Liability Insurance	57

19.1.7	Excess Umbrella Liability Coverage	58

19.1.8	Vendors	58

19.1.9	Certificate of Insurance	58

19.1.10	Other Requirements	58

19.1.11	Vendor Waiver of Subrogation	59

19.1.12	Compliance with Insurance	59

19.1.13	Limitation	59

19.2	Purchaser’s Insurance.	60

19.2.1	Cargo Insurance	60

19.2.2	Builder’s All Risk Insurance	60

ARTICLE XX. INDEMNIFICATION	60

20.1	Third Party	60

20.2	Survival of Obligation	62

ARTICLE XXI. NON-DISCLOSURE OF INFORMATION	62

21.1	Proprietary Information	62

21.2	Press Releases	63

21.3	Confidentiality of Seller	63

21.4	Confidentiality of Purchaser	64

ARTICLE XXII. ASSIGNMENT	65

22.1	Assignment by Seller	65

22.2	Assignment by Purchaser	66

ARTICLE XXIII. RELATIONSHIP OF THE PARTIES	67

23.1	Independent Contractor	67

23.2	Responsibilities of Seller as Principal for its Employees	67

23.3	Not Used.	67

ARTICLE XXIV. LIENS AND CLAIMS	68

ARTICLE XXV. NOTICES AND COMMUNICATIONS	68

25.1	Notices	68

25.2	Effectiveness of Notices	69

25.3	Technical Communications	69

ARTICLE XXVI. ARBITRATION	69

26.1	Negotiation of Disputes and Disagreements	69

26.2	Arbitration Resolution	70

26.3	Continuation of Work	70

26.4	Not Used.	70

26.5	Not Used.	70

ARTICLE XXVII. LIMITATION OF LIABILITY	71

27.1	Maximum Liability	71

27.2	Consequential Losses	71

27.3	Releases Valid in All Events	71

27.4	Seller’s Advice or Assistance	71

ARTICLE XXVIII. DRUG AND ALCOHOL-FREE WORKPLACE	71

ARTICLE XXIX. PROJECT PLANNING AND CONTROLS	72

ARTICLE XXX. MISCELLANEOUS	72

30.1	Validity and Enforceability	72

30.2	Governing Law	72

30.3	Entire Agreement	72

30.4	Agreement Modification	73

30.5	Waiver	73

30.6	Headings	73

30.7	Third-Party Beneficiaries	73

30.8	Counterparts	73

30.9	Equal Employment Opportunity	73

30.10	Cooperation on Site	73

30.11	Nuclear Material	73

AGREEMENT

This Agreement is made and entered into as of this ____ day of December 2000, (hereinafter, the “Effective Date”), by and between E-Next Generation, L.L.C., a Delaware limited liability company, with offices located at 1400 Smith Street, Houston, Texas 77002 (“Purchaser”), and GE Packaged Power, Inc. a corporation incorporated under the laws of Delaware, with offices located at 2707 North Loop West, Houston, Texas 77008 (“Seller”).

RECITALS

WHEREAS, Purchaser has a need to acquire one LM6000 Enhanced Sprint combustion turbine generator set (the “Units,” whether one or more) for installation in an electricity generation plant (the “Facility”); and

WHEREAS, Seller is in the business of designing, engineering, manufacturing, and supplying Units and auxiliary services in connection therewith;

WHEREAS, Purchaser has agreed to purchase from Seller, and Seller has agreed to sell to Purchaser, the Unit pursuant to the terms of this Agreement; and

NOW, THEREFORE, in consideration of the mutual covenants herein contained, and intending to be legally bound, the parties hereto agree as follows:

# DEFINITIONS

Terms used in this Agreement without other definition shall have the meanings specified in this ARTICLE I, unless the context requires otherwise.

As used in this Agreement, the terms “herein”, “herewith” and “hereof” are references to this Agreement, taken as a whole, the term “includes” or “including” shall mean “including, without limitation,” and references to a “Section”, “subsection”, “clause”, “Article”, “Exhibit”, “Appendix” or “Schedule” shall mean a Section, subsection, clause, Article, Exhibit, Appendix or Schedule of this Agreement, as the case may be, unless in any such case the context requires otherwise.  All references to a given agreement, instrument or other document shall be a reference to that agreement, instrument or other document as modified, amended, supplemented and restated through the date as of which such reference is made, and reference to a law, regulation or ordinance includes any amendment or modification thereof.  A reference to a person includes its successors and permitted assigns.  The singular shall include the plural and the masculine shall include the feminine, and vice versa.

## Acceptance»

.  Shall have the meaning as set forth in Section 10.14.

## Adjusted Electrical Output»

.  Shall mean the Electrical Output adjusted from test conditions to  Basis Conditions by the methods described in Exhibit F.

## Adjusted Emissions»

.  Shall mean the Emissions as measured during the Performance Tests and adjusted to Basis Conditions by the methods described in Exhibit F.

## Adjusted Exhaust Gas Energy»

.  Shall mean the Exhaust Gas Energy of a Unit as measured during a Performance Test and adjusted from test conditions to Basis Conditions by methods described in Exhibit F.

## Adjusted Exhaust Gas Temperature»

.  Shall mean the Exhaust Gas Temperature of a Unit as measured during a Performance Test and adjusted from test conditions to Basis Conditions by methods described in Exhibit F.

## Adjusted Heat Rate»

.  Shall mean the Heat Rate adjusted from test conditions to Basis Conditions by the methods described in Exhibit F.

## Affected Party»

.  Shall have the meaning set forth in Section 18.1.

## Affiliate»

.  Shall mean a person or entity who, with respect to a specified  person or entity, directly or indirectly through one or more intermediaries controls, or is controlled by, or is under common control with, the person or entity specified.

## Agreement»

.  Shall mean this Agreement, including all Exhibits attached hereto and the Specification, as amended from time to time as provided herein.

## Applicable Laws»

.  Shall mean any applicable national, municipal or local statute, ordinance or other law, regulation or by-law or any rule, code or direction or any license, consent, permit, authorization or other approval including any conditions attached hereto (whether relating to the environment or otherwise) of the government of the United States or foreign jurisdiction or of any public body or authority, local or national agency, department, inspector, ministry, official or public or statutory person (whether autonomous or not) which has appropriate jurisdiction pertaining to a particular Unit.

## Base Load»

.  Shall mean the operation of the Units at 100% Electrical Output for the prevailing ambient temperature, relative humidity, barometric pressure, fuel heating value, exhaust temperature limitation, rated frequency, power factor and voltage.

## Basis Conditions»

.  Shall mean the conditions set forth in Exhibit A which are the basis for the Guaranteed Levels and Specific Performance Levels.

## BTU»

.  Shall mean British Thermal Unit, where one (1) BTU is equal to 1055.056 joules.

## Cancellation Charge»

.  Shall have the meaning as set forth in Section 5.4.1.

## Change in Law»

.  Shall mean any change in, or binding change in the judicial or administrative interpretation of, or adoption of, any Applicable Law, which is implemented after May 12, 2000, and which has an adverse affect on Seller’s ability to perform its obligations under this Agreement; provided, however, that a change in any federal, commonwealth, state or local income or franchise tax law, workers’ compensation, or payroll or withholding tax law shall not constitute a change in law hereunder.

## Change Order»

.  Shall have the meaning as set forth in Section 11.2.

## Claim»

. Shall have the meaning set forth in Section 20.1(a).

## Commercial Operation»

.  Shall mean the reliable operation of the Unit by Purchaser in accordance with industry standards while the Unit is connected to the utility grid and producing electrical energy for sale. This does not include power that may be sold during start up, commissioning, or a performance test unless the generation of such power prevents commissioning.

## Commissioning Period»

.  Shall mean Purchaser’s allowance of thirty (30) days from first roll of each Unit to complete Unit commissioning check outs, any needed replacement, adjustments or corrections to make the Unit(s) ready for testing.

## Cover Damages»

.  Shall have the meaning set forth in Section 17.4.3.

## Day»

.  Shall mean a calendar day, including weekdays, weekends, and holidays.

## Delivery Liquidated Damages»

.  Shall have the meaning as set forth in Section 10.3.1.

## Delivery Point»

.  Shall mean 16415 Jacinto Port Blvd., Houston, Texas.

## Effective Date»

.  Shall have the meaning as set forth in Recitals.

## Emissions»

.  Shall mean the exhaust emissions of a Unit as measured during a Performance Test.

## Emissions Guarantee»

.  Shall have the meaning and value as set forth in Section 10.6.

## Electrical Output»

.  Shall mean the electric output of a Unit measured at the generator terminals during a Performance Test deducting actual electrical consumption of the auxiliaries listed in Exhibit F.

## Electrical Output Guarantee»

.  Shall have the meaning as set forth in Section 10.7.1.

## Equipment»

.  Shall mean for each Unit the equipment comprising an LM6000 generator set described in the Specification and all other material and supplies including without limitation, software, installation and operations manuals and drawings to be furnished by Seller and/or its Vendors pursuant to the Scope of Work.

## Event of Force Majeure»

.  Shall have the meaning as defined in Section 18.4.

## Event of Purchaser Default»

.  Shall have the meaning as defined in Section 17.5.

## Event of Seller Default»

.  Shall have the meaning as defined in Section 17.1.

## Exhaust Gas Energy»

.  Shall mean the exhaust gas energy of a Unit measured or calculated at the gas turbine exhaust outlet during a Performance Test.

## Exhaust Gas Temperature»

.  Shall mean the exhaust gas temperature of a Unit measured or calculated at the gas turbine exhaust outlet during a Performance Test.

## Extended Warranty Period»

.  Shall have the meaning as set forth in Section 14.2.1.

## Facility»

.  Shall have the meaning set forth in the Recitals.

## Far Field Sound Level Guarantee»

.  Shall have the meaning as set forth in Section 10.5.2.

## Guaranteed Levels»

.  Shall mean the Electrical Output Guarantee and Heat Rate Guarantee.

## Guaranteed Unit Delivery Dates»

.  Shall have the meaning as set forth in Section 10.2.1.

## Hazardous Materials»

.  Shall mean any hazardous substance or hazardous waste as defined in the Comprehensive Environmental Response, Compensation and Liability Act of 1980, as amended, the Resource Conservation and Recovery Act, as amended, the Hazardous Waste Transportation Act, as amended, and regulations promulgated pursuant to these Acts and any similar federal, state or local law or regulation defining hazardous substances or hazardous waste, and any equipment containing polychlorinated biphenyls or asbestos that may become friable.

## Heat Rate»

.  Shall mean the actual fuel energy consumed during the Performance Test determined from the actual lower heating value of the fuel multiplied by the quantity of fuel consumed and expressed in BTU, divided by the Electrical Output measured in kWh at the generator terminals during the Performance Tests in accordance with the testing guidelines set forth in Exhibit F, expressed as BTU/kWh(LHV).

## Heat Rate Guarantee»

.  Shall have the meaning as set forth in Section 10.8.1.

## Heat Rate Liquidated Damages»

.  Shall have the meaning as set forth in Section 10.9.2.

## Heat Rate Liquidated Damages Refund Reduction»

.  Shall have the meaning as set forth in Section 10.9.8.

## Installation Period»

.  Shall mean the period of nine (9) months from the date the applicable Unit is delivered to the Site, but no later than fifteen (15) months after the later of the applicable Guaranteed Unit Delivery Date or the date  the Unit is placed in storage at Purchaser’s election.

## Insurability Certificate»

.  Shall have the meaning as set forth in Section 3.10.2.

## Insurance Representative»

.  Shall have the meaning as set forth in Section 3.10.1.

## Interest Rate»

.  Shall mean the Prime Rate as published by Citibank, N.A. at its New York City  office plus two percent (2%) per annum, provided however, that the rate of interest hereunder shall never exceed the highest applicable lawful rate.

## kW»

.  Shall mean kilowatt.

## kWh or kwh»

.  Shall mean kilowatt hour.

## Lender»

.  Shall mean any financial institution or financier from which financing in connection with the Facility and associated facilities and services is obtained by Purchaser or its Affiliate.

## Liquidated Damages»

.  Shall mean any or all Take Over Liquidated Damages, Delivery Liquidated Damages, O & M Instruction Liquidated Damages, and/or Performance Liquidated Damages.

## Liquidated Damages Events»

.  Shall have the meaning set forth in Section 10.11.

## Major Components»

.  Shall mean and consist of all parts and materials of the following for each Unit:

Inlet Filter Module

Gas Turbine (drive module) with Combustors Installed

Electric Generator (driven module)

Combined Starting Auxiliary Skid

Water Injection High Pressure Pump Skid

Unit Control Panel

Sprint Injection Pump Skid

## Marketing Agreement»

.  Shall have the meaning as set forth in Section 5.4.2.

## Maximum Liability Amount»

.  Shall be fourteen million, three hundred and fifty-two thousand dollars($14,352,000), as such amount may be increased by approved Change Orders.

## Near Source Sound Level Guarantee»

.  Shall have the meaning as set forth in Section 10.5.1.

## Notice»

.  Shall mean any notification of one party hereto by the other party hereto with respect to any matter arising under or in connection with this Agreement, to be given as provided in Section 25.1 hereof.

## O & M Instruction Liquidated Damages»

. Shall have the meaning set forth in Section 10.1.2.

## O&M Manuals»

.  Shall have the meaning set forth in Section 10.1.2.

## O&M Spares. 	 Shall have the meaning set forth in Section 3.14.2.

## Optional Delivery Point»

.  Shall mean the place for delivery of the Units as set forth in Section 10.2.3.1.

## Order Definition Meeting (ODM)»

. Shall have the meaning set forth in Section 3.13.

## Output Liquidated Damages Refund Reduction»

.  Shall have the meaning as set forth in Section 10.9.8.

## Patent Indemnities»

. Shall have the meaning set forth in Section 15.2.2.

## Payment Date»

.  Shall have the meaning set forth in Section 6.1.1.

## Payment Schedule»

.  Shall have the meaning as set forth in Section 6.1.2.

## Performance Liquidated Damages»

.  Shall mean the Unit Output Liquidated Damages and Heat Rate Liquidated Damages.

## Performance Test»

.  Shall mean the test(s) conducted at the Site on the Unit(s) in accordance with the Test Procedures to determine Emissions, Heat Rate, Electrical Output and Sound Levels.  In the case of combined cycle applications, Units will be tested for Exhaust Gas Energy and Exhaust Gas Temperature.

## Performance Test Completion Certificate»

.  Shall mean the certificate prepared by  Purchaser in the format attached hereto as Exhibit G-2 and provided to Seller, certifying the results of the Performance Tests that have been completed and quantifying Performance Liquidated Damages, if any, due.

## Performance Test Certificate»

.  Shall mean the certificate prepared by Purchaser in the format attached hereto as Exhibit G-1 and provided to Seller, certifying that a Performance Test has been completed and setting forth the results thereof in such detail to reflect the performance of the Units as tested with respect to Electrical Output, Emissions, Heat Rate and Sound Levels.  In the case of combined cycle applications, testing for Exhaust Gas Energy and Exhaust Gas Temperature will be performed by Purchaser if the combined cycle Facility has demonstrated a shortage of steam-generated performance.

## Power Purchaser»

.  Shall mean the applicable utility or any power purchaser, which has entered into a contract with Purchaser, or its Affiliate, to purchase power from the Facility.

## Primary Warranty Period»

.  Shall have the meaning as set forth in Section 14.1.1.

## Project Manager»

.  Shall mean the project manager designated by Seller pursuant to Section 3.3(a) hereof.

## Proper Scope Value»

.  Shall have the meaning as set forth in Section 17.4.1.

## Punchlist»

.  Shall mean the list of the incomplete or deficient work or materials associated with Seller’s Scope of Work, which is comprised of those items which are minor in nature and do not affect the performance of the Equipment, safety or personnel working on or operating the Equipment or the ability of the Equipment to be used for its intended purpose.  Punchlists shall be produced by Seller and approved by Purchaser for each Unit or the Facility.

## Purchase Amount»

.  Shall mean the amount payable to Seller that constitutes the balance due for the Units, as adjusted pursuant to the terms of this Agreement.

## Purchaser»

.  Shall mean E-Next Generation, L.L.C., its successors and permitted assigns.

## Purchaser Claimant»

. Shall have the meaning set forth in Section 20.1(a).

## Purchaser Indemnitees»

. Shall have the meaning set forth in Section 20.1(a).

## Purchaser Related Parties»

.  Shall have the meaning as set forth in Section 19.1.11.

## Purchaser’s Representative»

.  Shall mean the individual designated by Purchaser pursuant to Section 2.1(a) hereof, who shall have the responsibility and authority specifically delegated to such individual by Purchaser and made known in writing to Seller.

## Refund Amount»

.  Shall have the meaning as set forth in Section 17.4.1.

## Related Dispute»

.  Shall have the meaning as set forth in Section 26.2(c).

## Retention Amount»

.  Shall have the meaning as set forth in Section 6.1.3.

## Retention Letter of Credit»

.  Shall have the meaning as set forth in Section 6.1.3.

## Scope of Work»

.  Shall mean all design, engineering, manufacture, delivery, transportation, technical direction of installation, training, technical services, Equipment, drawings, documentation, supplies and materials to be performed and/or furnished by Seller or its Vendors pursuant to this Agreement or would have been reasonably expected to be supplied by a prudent supplier to ensure the successful operation of the Units.

## Scope Value Due»

.  Shall have the meaning as set forth in Section 17.4.1.

## Seller»

.  Shall mean GE Packaged Power, Inc., its successors and permitted assigns.

## Seller Claimant»

. Shall have the meaning set forth in Section 20.1(b).

## Seller’s Indemnitees»

. Shall have the meaning set forth in Section 20.1(b).

## Shortfall»

.  Shall mean the amount by which a Unit fails to meet a Guaranteed Level.  Such shortfall shall be measured in the same units as the respective guarantee.

## Site»

.  Shall mean any part of the land of the Facility.

## Site Delivery Date»

.  Shall mean the date on which a Unit is delivered  to the Site.

## Sound Levels»

.  Shall mean the Near Source Sound Level Guarantee and the Far Field Sound Level Guarantee.

## Sound Level Guarantee»

.  Shall mean the Near Source Sound Level Guarantee and the Far Field Sound Level Guarantee.

## Sound Level Test»

.  Shall have the meaning as set forth in Section 10.5.4.

## Sound Level Test Procedures»

.  Shall mean the test procedures used to measure Sound Levels as set forth in Exhibit F-1.

## Specific Performance»

.  Shall mean, whether used by itself or as part of another defined term, an obligation that Seller must fulfill or achieve, or otherwise be in breach of its obligations hereunder.  Seller shall not be able to pay Liquidated Damages in lieu of meeting such specific performance requirements.

## Specific Performance Electrical Output Guarantee»

.  Shall have the meaning as set forth in Section 10.7.2.

## Specific Performance Exhaust Gas Temperature Guarantee»

.  Shall have the meaning  as set forth in Section 10.4.2.

## Specific Performance Exhaust Gas Energy Guarantee»

.  Shall have the meaning  as set forth in Section 10.4.4.

## Specific Performance Heat Rate Guarantee»

.  Shall have the meaning as set forth in Section 10.8.3.

## Specific Performance Levels»

.  Shall mean the Specific Performance Electrical Output Guarantee, Specific Performance Heat Rate Guarantee, Emissions Guarantee and Sound Level Guarantee.  If the Facility is a combined cycle plant, it shall also include the Specific Performance Exhaust Gas Temperature Guarantee and the Specific Performance Exhaust Gas Energy Guarantee.

## Specification»

.  Shall mean the specification as issued by Purchaser for the design, manufacture, assembly set forth in Exhibit B, and the specification by Seller for the supply of the Units as set forth in Exhibit B-1.

## Takeover»

.  Shall mean that the Performance Tests have been conducted for a Unit, and  that the Purchaser has accepted the Unit for the purpose of placing the Unit into Commercial Operation.

## Take Over Criteria»

.  Shall mean that a Unit has met its Specific Performance Levels during the applicable Performance Tests and is capable of being commissioned and placed into Commercial Operation.

## Take Over Liquidated Damages»

.  Shall have the meaning as set forth in Section 10.3.2.

## Technical Direction of Installation (TD of I)»

.  Shall have the meaning and scope as set forth in Exhibit H-1.

## Termination Costs»

.  Shall have the meaning as set forth in Section 17.4.2.

## Termination Settlement»

.  Shall have the meaning as set forth in Section 17.4.4.

## Test Procedures»

.  Shall have the meaning as set forth in Section 10.12.7.

## Time for Completion»

.  Shall mean the date of one hundred twenty (120) Days after any specific Unit arrives at the Site.

## Training»

.  Shall have the meaning and scope as set forth in Exhibit H-2.

## Transportation Option»

.  Shall have the meaning set forth in Section 3.2.2.

## Unit»

. Shall mean one LM6000 Enhanced Sprint combustion turbine generator package.

## Unit Output Liquidated Damages»

.  Shall have the meaning as set forth in Section 10.9.1.

## Vendor»

.  Shall mean any vendor, supplier or subcontractor utilized by Seller in the performance of the Scope of Work hereunder.

# RESPONSIBILITIES OF PURCHASER

## Purchaser Responsibilities»

.  Purchaser recognizes and acknowledges the duty to reasonably cooperate with Seller, and agrees not to wrongfully interfere with Seller’s agents, employees or Vendors during the performance of this Agreement.  Without limiting the generality of the foregoing, Purchaser shall be responsible for the following matters and actions to be performed on a timely basis:

##### Purchaser shall designate a Purchaser’s Representative and deliver a Notice to Seller identifying Purchaser’s Representative, within thirty (30) Days of the latest date of signature of this Agreement, who shall act as the primary point of contact for Seller with respect to the prosecution of the Scope of Work;

##### Purchaser shall deliver a Notice within thirty (30) Days of the latest date of signature of this Agreement to Seller identifying such persons within Purchaser’s organization that have authority to approve Change Orders;

##### Purchaser shall pay to Seller the sums required to be paid by Purchaser pursuant to the terms of this Agreement; and

##### the Units shall be installed, operated and maintained by or on behalf of Purchaser as identified in Exhibit B-1, Section 3 and as otherwise stated in the Agreement.

## Purchaser Conduct»

. Purchaser will comply with applicable regulatory requirements and Applicable Laws which pertain to Purchaser’s obligations under this Agreement. Unless otherwise agreed, Purchaser shall procure or cause to be procured the permits necessary for the installation and operation of the Equipment at the Site.

# RESPONSIBILITIES OF SELLER

## General Obligations»

.  Except as expressly set forth in this Agreement, Seller shall provide the new materials and supplies, technical and professional personnel and supervision at Seller’s facilities and as required for Seller to fulfill its transportation responsibilities, tools and equipment, and the services required for performance and timely completion of the Scope of Work, and shall be responsible for timely completing the Scope of Work in accordance with the terms of this Agreement.

References in the Specification to equipment, material, articles or patented processes by trade name, make, or catalog number, shall be regarded as the standard of quality to be met by Seller.  Seller may, subject to written notification to Purchaser, use any equipment, material, article, or process that is operationally, technically and functionally equivalent to that named in the Specification.  For the avoidance of doubt, all equipment, materials and components, whether or not specifically referenced in the Specification or elsewhere in the Agreement, which are incorporated by Seller or its Vendors  into the Scope of Work, shall be new, unrepaired and suitable for the purpose for which it is intended except as otherwise allowed pursuant to this Agreement.

## Delivery of Equipment and Documentation.

### Delivery of Equipment to the Delivery Point»

.  Except as otherwise provided in this Agreement, Seller shall deliver the Equipment to the Delivery Point in accordance with this Agreement by the dates set forth in Section 10.2.1.

### Delivery to Optional Delivery Point»

.  As an added option, to be exercised solely at the discretion of Purchaser, Purchaser may require Seller to deliver some or all of the Equipment to the Optional Delivery Point(s) in lieu of the Delivery Point(s) (the “Transportation Option”), and if so elected Seller shall deliver the specified Equipment to the Optional Delivery Point(s) in accordance with Section 10.2.3.1.  If Purchaser exercises the Transportation Option, the Purchase Amount shall be adjusted per Section 5.3.

### Impact Indicators»

.  To the extent Seller arranges for transportation for any or all of the Units, Seller shall provide Purchaser with details of procedures pertaining to securing the Units during transportation.  If as a result of such review, Purchaser reasonably determines that impact indicators are required, Seller shall do so at no additional cost to Purchaser.

### Packing List»

.  Seller shall provide a pro forma packing list as set forth in Exhibit Q and provide a final packing list thirty (30) Days prior to each shipment.

## Relevant Information»

.  Seller shall provide on a timely basis to Purchaser information reasonably necessary to fulfill Seller’s obligations pursuant to this Agreement, including, without limitation:

##### within fifteen (15) Days of the latest signature date of this Agreement, the identity  of a project manager (the “Project Manager”) who shall have full supervision over the completion of  the Scope of Work and who shall act as the primary point of contact with Purchaser regarding all matters relating to the Scope of Work;

##### such information as is requested by Purchaser in dealing with the Lenders, Power Purchaser and/or any governmental authority in matters relating to the Scope of Work.  Such obligation shall not include information such as grid or power generation studies for the total power system;

##### the project management plan proposed for this Agreement to include, but shall not be limited to staffing, milestones, scheduling, quality control, transportation, technical interface, and other mutually agreed matters required to successfully manage the project to conclusion; and,

##### no later than fourteen (14) Days prior to the shipment of the Unit, or first Unit if these shall be more than one, provide a master equipment bill of materials (BOM) for use by both parties to effectively track deliveries of each Unit’s components and facilitate verification of shipping,  inventory at Site, expediting of shortage lists and look-ahead planning in support of installation. Seller shall provide updates to the BOM periodically as the parties shall reasonably agree is necessary to maintain the effectiveness of the document.

## Hazardous Materials Notification.

##### Seller warrants to Purchaser that in relation to the Scope of Work, it will use reasonable skill and care to ensure that there will not be Hazardous Material specified or permanently incorporated into the Scope of Work; provided that where in the opinion of Seller this results in any conflict with any relevant statutory requirements or where the Scope of Work would be prejudiced through lack of suitable alternatives, then Seller shall immediately notify Purchaser in writing specifying the conflict or prejudice which has arisen and the substance which Seller wishes to stipulate or use and Seller shall not stipulate or use the same without, in each case, the prior written consent of Purchaser which shall not be unreasonably withheld.

##### Seller shall immediately upon the request of Purchaser certify in writing that to the best of its knowledge that no Hazardous Materials have been specified or permanently incorporated in the Scope of Work. In the event Seller, with Purchaser’s approval, incorporates any Hazardous Materials into the Equipment, Seller shall provide Purchaser with notification as set forth in Exhibit O.

## Employment of Trained and Experienced Personnel»

.  Seller shall be responsible for employing and utilizing personnel and for ensuring that its Vendors employ and utilize personnel who possess the proper training and experience and are capable of performing the tasks for which they are employed or utilized.

## Not Used.

## Guarantee»

.  As a condition precedent to the effectiveness of any assignment pursuant to Section 22.1, Seller shall deliver to Purchaser an unconditional parent company guarantee from General Electric Company in the form set forth in  Exhibit C-1  hereto, which shall guarantee full payment and performance of all Seller obligations under this Agreement as due in accordance with the terms of this Agreement.

## Compliance with Governmental Rules»

.  Seller shall comply with Applicable Laws, including but not limited to those described below:

##### Seller Conduct.  Seller shall comply with applicable regulatory requirements including, without limitation, all Applicable Laws issued or promulgated by units of government and regulatory bodies with jurisdiction over any aspect of the performance of this Agreement by Seller. Seller shall not act in violation of the U.S. Foreign Corrupt Practices Act or similar law of the United States, and in connection therewith shall not make any payments, loans, or gifts directly or indirectly, to or for the use or benefit of any official employee, agency or instrumentality of any government, political party or candidate thereof, or any other person or entity, the payment of which would violate the laws or policies of the United States, or the country or countries in which the Scope of Work is performed, in whole or in part.  Seller shall possess or procure all permits, certificates, and licenses necessary to allow Seller to perform this Agreement at all locations of performance and shall ensure that Vendors have all permits, certificates, and licenses necessary for such Vendors to perform under this Agreement. Seller shall answer promptly and in reasonable detail any questionnaire or other written or oral communications, to the extent the same pertain to compliance with this Section 3.8(a) or (b) whether such questionnaires or communications are from Purchaser, their outside auditors, or other representatives.  Seller further agrees to pay any government assessed penalties, fines, and charges, and associated damages, costs, losses, and expenses (including, without limitation, court costs and attorneys’ fees) of whatever kind which Purchaser may incur, be required to pay or be liable for as a result of, in connection with, arising out of or related to any noncompliance of Seller’s performance of this Agreement or any portion thereof with any or all of the above laws, regulations, rules, orders, codes, criteria, standards, ordinances or resolutions.

##### Employment Practices.

###### Seller agrees that it shall be at all times during the term of this Agreement in full compliance with all Applicable Laws relative to Seller’s employment of employees and agents of Seller.

###### Seller agrees to pay any government assessed penalties, fines, and charges, and associated damages, costs, losses, expenses (including, without limitation, court costs and attorneys’ fees) of whatever kind which Purchaser may incur, be required to pay or be liable for as a result of, based on, in connection with, related to or arising from Seller’s noncompliance with this Section 3.8(b).

##### Scope of Work to Comply with Applicable Laws.  Subject to the provisions of Section 3.8(c)(iv):

###### Seller shall cause the Scope of Work to comply with Applicable Laws that were:

in effect on May 12, 2000; or

not yet in effect on May 12, 2000, but at such time a change to such valid Applicable Laws, issued or promulgated by units of government and regulatory bodies, had passed but was not yet effective;

In the event Seller fails to cause the Scope of Work to so comply with the Specification and Applicable Laws, Seller shall correct such noncomplying Scope of Work or portion thereof as necessary to comply with the above.  Seller shall bear the costs of correction of such noncomplying Scope of Work.  In the event that Purchaser reasonably determines that Seller is either not capable of performing the corrections or not capable of performing such corrections in time to meet Purchaser’s requirements, Purchaser may, at Seller’s expense, have the corrections made by a third party or make them itself; provided, however prior to Purchaser having the corrections performed by a third party or itself Purchaser shall have provided Seller Notice of its determination that it believes Seller is not capable of such performance of work or performing such corrections in a timely manner.

###### In the event that Seller does not comply with the Specification or Applicable Law, and Purchaser at its sole determination agrees Seller cannot reasonably incorporate the changes necessary for Seller to comply, Purchaser, in its sole discretion, may either (i) terminate the Agreement in whole or in part if Seller does not comply with the Specification or (ii) terminate the Agreement if Seller does not comply with the Applicable Law, each in accordance with ARTICLE XVII, or (iii) direct Seller to complete the Equipment without such changes, in which case Purchaser shall assume full responsibility for obtaining any necessary waivers from the appropriate federal, state or local authorities.

###### Seller shall, on a reasonable efforts basis, advise Purchaser of pending Applicable Laws so that Purchaser may make an informed decision as to whether to have the Equipment designed in anticipation of such pending change as it affects the Scope of Work.

###### In the event a Change in Law occurs subsequent to the times set forth in Section 3.8(c)(i), Seller shall prepare a request for a Change Order to Purchaser identifying the nature of the change, including any proposed extensions of time to the performance of the Scope of Work and the Purchase Amount.  In the event that Purchaser elects to not have Seller comply with such change, Purchaser shall indemnify Seller for such failure of the Scope of Work to comply with such new law requirement.

## Approved Vendors»

.  Purchaser agrees that Seller may utilize the Vendors listed in Exhibit B-4 for procurement of the components under which they are listed.  For those items of Equipment not listed in Exhibit B-4, Seller reserves the right in its sole discretion to obtain, source, subcontract, manufacture, fabricate and assemble the Equipment and any of its components and systems outside of the United States or from non-domestic concerns, or both, subject to the standards and obligations of the Agreement.  Seller will not utilize any Chinese sourced insulation or flanges in any case.

## Packing and Insurance Surveyor.

### Packing Recommendation»

.  Seller shall perform all packaging of the Equipment to the highest commercial standard practices of the industry to prevent damage during its handling and transportation to the Delivery Point or Optional Delivery Point (as the case may be).   Seller shall comply with Purchaser’s insurance representative’s (Salvage Association or similar insurance surveyor as appointed by Purchaser) (the “Insurance Representative”) recommendations concerning:

###### packaging of the Equipment;

###### Seller’s execution of the load plan on its transport to preclude damage during transit;

###### transshipment; and

###### movement to the Delivery Point (or Optional Delivery Point if applicable), including route surveys.

Seller shall immediately notify Purchaser of any unreasonable recommendations.

### Insurability Certificate»

.  Seller expressly acknowledges and agrees that it will not commence transport of the items of Equipment unless;

###### the Insurance Representative conducts a load plan and load survey and issues an insurance certificate, (the “Insurability Certificate”) attesting that its recommendations were carried out for such shipment with respect to the Equipment listed in Exhibit L; or

###### Purchaser’s Representative expressly waives such requirement for that shipment.

### Notice of Shipment»

.  Seller recognizes that failing to comply with this Section may jeopardize Purchaser’s insurance program.  Seller shall provide Purchaser’s Representative with reasonable advance Notice of the expected packing date and the expected loading date of any such shipment, and shall provide two business days advance Notice of the actual packing date and the actual loading date of such shipment.  Purchaser may designate its Insurance Representatives as recipient of such Notice.  Provided Seller has provided Purchaser with such Notice by such Notice dates, if the Insurance Representative is not available to perform the necessary inspections on the dates of loading indicated in Seller’s final Notice, or the recommendations of the Insurance Representative are mutually agreed by Seller and Purchaser to have been unreasonable, Purchaser shall extend the applicable Guaranteed Unit Delivery Date for the affected Unit to the extent Seller is delayed by such unavailability or unreasonable recommendations, and shall compensate Seller for any applicable costs including demurrage attributable thereto.  Seller shall provide the Insurance Representative with a load and transportation plan thirty (30) Days prior to loading. Seller acknowledges that all efforts and delays (other than as set forth in this Section 3.10) associated with receiving the Insurability Certificate shall not be grounds for extension to the Guaranteed Unit Delivery Date(s).

### Compliance with Recommendation»

.  Seller’s compliance with the Insurance Representative’s recommendations shall not relieve Seller of its responsibility for risk of loss and damage of the Equipment in accordance with this Agreement through delivery to the Delivery Point (or Optional Delivery Point if applicable).

### Coordination»

.  Seller agrees to host a transportation coordination meeting at its facility no later than forty-five (45) Days prior to shipment of the first Major Component for each Unit on a mutually agreed date.  Purchaser shall coordinate attendance by its Insurance Representative.

## Financing and Insurance Assistance»

.  Seller shall provide such information as Purchaser may reasonably request in connection with obtaining financing and insurance for the Facility including without limitation providing information related to design, engineering and status of the completion of the Scope of Work and Seller’s credentials and experience, and, as required, perform reasonable travel.  Purchaser shall reimburse Seller at commercially reasonable rates for its time in providing information not related to the Scope of Work.  Power Purchaser, Lender and their respective engineers and consultants shall have the right to participate in all inspections conducted by Purchaser under this Agreement and to attend all tests of the Equipment.  At Purchaser’s request, Seller shall furnish to Lender copies of Notices given to Purchaser hereunder.

## Purchaser Permit Support»

.  Seller shall provide all information, data and documents in a timely fashion that Purchaser may reasonably require for Purchaser to obtain Facility permits.

## Order Definition Meeting»

.  Seller agrees to host an order definition meeting (“ODM”) at its manufacturing facility no later than six (6) months prior to the Guaranteed Unit Delivery Date for the first Unit for the Facility or as otherwise mutually agreed, to finalize project scope issues for the purpose of Seller’s issuance of its ancillary equipment order and commencement of detailed engineering.

## Spare Parts.

### Commissioning Spares.

Seller’s representative priced list of start-up and commissioning spares and a representative list of special tools needed during start-up and commissioning are set forth in Exhibit M-2. Seller shall provide to Purchaser, at no additional charge, (i) all spare parts necessary to achieve start up, commissioning, performance testing, and (ii) all installation and maintenance tools that are not normally found available in industrial tool supply stores.

### O & M Spares.

Set forth in Exhibit M-1 is a summary price list of operating and maintenance spare parts (the “O&M Spares”) for the Units.  More detailed price lists are contained in the current Year 2000 Price Book which is incorporated herein by reference and is subject to change annually. In addition to the Purchase Amount, Purchaser may elect to purchase any quantity or type of spare parts listed in Exhibit M-1 for the initial inventory purchased for each Facility.   Spare parts ordered shall be delivered FOB factory in accordance with Exhibit M-1.  The purchase value of any such ordered spare parts shall not be included in the Purchase Amount, and will be referred to as the “Spare Parts Amount”.  Purchaser’s purchase or lack of purchase of O&M Spares under this Agreement shall not preclude Purchaser, or Purchaser’s operator, from purchasing such spare parts under separate agreements with Seller.  Spare parts ordered shall be delivered to the Delivery Point.  Payment terms will be determined on a per order basis. Payment will be in U.S. Dollars.

## Key Personnel»

.  Seller shall provide Purchaser with biographical data for the Project Manager, and lead technical advisor for TD of I.  If, in the reasonable opinion of Purchaser, Purchaser determines such a key person is not adequately performing, Purchaser may require Seller to remove such person from work on the Scope of Work under this Agreement and replace with a satisfactory replacement.

## Seller’s Representations»

.  Seller represents and warrants to Purchaser that:

##### Seller is duly incorporated, organized, existing and in good standing under the laws of Delaware; Seller possesses all requisite power and authority to enter into and perform this Agreement, to carry out the transactions contemplated herein, and to conduct business in each of the locations where any portion of the Scope of Work is to be performed; and Seller has all legal power and authority to own and use its properties and to transact the business in which it is engaged and holds or expects to obtain all franchises, licenses, and permits required therefor;

##### Seller’s execution, delivery, and performance of this Agreement have been duly authorized by, and are in accordance with, its articles of incorporation and by-laws; this Agreement has been duly executed and delivered for it by the signatories so authorized; and this Agreement constitutes Seller’s legal, valid, and binding obligation; and

##### Equipment of the same type and model number which is sold by Seller or its Affiliates to other clients is of the same manufacturing technology as the Equipment provided under this Agreement and such equipment has not demonstrated trends of failure.

# RESPONSIBILITY FOR INFORMATION

## Purchaser Supplied Information»

.  Except to the extent that the information provided by Purchaser to Seller is in the form of a specification or performance requirement specifically called out in this Agreement or performance requirements which Purchaser is obligated to provide under the Agreement,  Seller will use reasonable efforts to verify that any supplemental information is accurate, correct, complete and fit for the particular purpose(s) for which Seller utilizes it.

# PURCHASE AMOUNT AND OTHER CHARGES

## Purchase Amount»

.  The Purchase Amount is based on Seller delivering the Equipment to the Delivery Point. The Purchase Amount shall be paid to Seller in accordance with ARTICLE VI.  The Purchase Amount is subject to increases or decreases only as provided in Section 5.3 and in accordance with ARTICLE XI.

Exhibit N-2 lists options, prices and times by which the options must be exercised by Purchaser.  If an option is exercised by Purchaser, the applicable option amount as set forth in Exhibit N-2 shall used to adjust the Purchase Amount.

Seller shall prepare the  initial invoices in the name of Purchaser and forward such invoices to Purchaser for approval and payment pursuant to Section 6.1.1.

## Taxes and Contributions.

### Seller’s Responsibility for Personal Taxes»

.  Seller assumes full responsibility for and agrees to pay or caused to be paid all contributions and taxes payable under all Applicable Laws pertaining to social security laws, unemployment compensation laws and income tax laws as they apply to Seller’s and Vendor’s employees engaged in the performance of the Scope of Work.  Seller acknowledges that Purchaser has no responsibility for such taxes as they apply to Seller or Seller’s employees or the employees.

### Seller’s Responsibility for Taxes»

.  Seller is responsible for taxes arising out of its performance of the Scope of Work including import duties, harbor taxes, personal and corporate taxes.  The price excludes any US state or local jurisdiction imposed property, license privilege, sales, use, excise, gross receipts, valued added, or similar tax which may now or hereafter be applicable to, measured by, or imposed upon with respect to the transaction, the sale, use, value and presence of Seller’s Scope of Work in such taxing jurisdiction, or any services performed in connection therewith.  Such taxes are for the account of Purchaser and Purchaser agrees to pay any such tax when due or reimburse Seller within twenty-five (25) Days after the date of Seller’s invoice Purchaser for any such tax which it is required to pay.  Seller shall provide timely documentation and assistance with respect to any tax paid.  Should Purchaser be exempted from any such tax it shall provide Seller with certification prior to transfer of title of such Scope of Work, or at the time the certification is obtained, whichever first occurs.

### Tax Penalties»

.  Seller further agrees to pay any tax, interest, penalty, fines, costs, losses and expenses (including, without limitation, court costs and reasonable attorney’s fees) of whatever kind, which Purchaser may incur, be required by law to pay, or be liable for as a result of, arising from, in connection with, related to or based on any failure to withhold any amounts from any payments made or any amounts which Seller fails to pay in connection with, as a result of, arising from or based on the Scope of Work or otherwise comply with this Section 5.2.3.

## Changes to the Purchase Amount»

.  The Purchase Amount may only be adjusted if a Change Order has been executed by the parties in accordance with ARTICLE XI due to a change in Purchase Amount due to:

##### Change in Law requiring changes to the Equipment or Scope of Work which have been approved by Purchaser pursuant to Section 3.8.1(iv);

##### suspension pursuant to Section 5.5;

##### material breach or default of Agreement by Purchaser or Seller;

##### an Event of Force Majeure in which Purchaser is the Affected Party, exceeding a duration in the aggregate of 30 Days in accordance with Section 18.9;

##### a change in scope for which an adjustment to the Purchase Amount is expressly provided in this Agreement; and

##### Transportation and costs associated therewith to the Optional Delivery Point.

Seller’s entitlement to an increase in the Purchase Amount shall be conditional upon:

###### its having used reasonable endeavors to mitigate the cost increase (except for Purchaser’s exercise of options or Purchaser instructing Seller in its performance of any option, then compliance would not be considered a breach of this provision);

###### its having given proper and timely Notice in accordance with the terms of this Agreement; and

###### the cost increase not being attributable to its default.

## Cancellation.

### Cancellation by Purchaser»

.  Purchaser may cancel this Agreement at any time in whole or in part, without cause and for its own convenience, upon written Notice to Seller.  If Purchaser cancels this Agreement under this Section 5.4.1, then Purchaser shall pay Seller the Cancellation Charge applicable to the canceled Units in accordance with Exhibit I within thirty (30) Days after the effective date of such cancellation.  If Purchaser cancels this Agreement pursuant to this Section 5.4.1, Seller shall retain title to the Equipment unless title has passed to Purchaser pursuant to ARTICLE XV.

In the event that Purchaser cancels this Agreement in part, the portion of the Purchase Amount attributable to the affected Unit will be adjusted by Change Order.  In the event that Purchaser cancels this Agreement in whole, then upon payment in full of the Cancellation Charge applicable to the canceled Units as provided in the preceding paragraph and the payment in full of the portion of the Purchase Amount due and payable, the Purchaser shall be irrevocably released and forever discharged from any obligations under this Agreement.

### Marketing Agreement»

.  In the event that the project for which one or more Unit is destined is canceled and Purchaser decides to have Seller complete the affected Unit(s), at Purchaser’s request, Purchaser and Seller shall enter into an agreement in which the parties will cooperate to sell the Unit(s) to which Purchaser has taken title.

## Suspension or Change of Delivery.

### »

Purchaser shall be entitled to suspend delivery to the Delivery Point and make such changes to the Delivery Point as it may deem necessary in accordance with Section 5.5.2.

### »

If Purchaser instructs Seller to suspend delivery by written Notice, such Notice to be no later than forty-five (45) Days prior to the Guaranteed Unit Delivery Date of a Unit and the Major Components thereof, and the Equipment or any part of the Equipment cannot be shipped to the Delivery Point in accordance with the Agreement when ready, due to any cause not attributable to Seller, Seller shall ship such Equipment to storage.  If such Equipment is directed by Purchaser to be placed in storage, including storage at the facility where manufactured, the following conditions shall apply: (1) Seller’s delivery obligation shall be deemed fulfilled upon delivery to storage, and title shall thereupon pass to Purchaser if it had not already passed; (2) any amounts otherwise payable to Seller upon delivery shall be payable upon presentation of Seller’s invoices pursuant to Section 6.1.1; (3) all expenses incurred by Seller, such as preparation for and placement into storage, handling, inspection, preservation, insurance, storage, removal charges and any taxes (anything to the contrary in the Agreement notwithstanding), shall be added by Change Order in accordance with Exhibit N-2;  and (4) if the Unit is placed in storage other than at its final use point, when conditions permit, Seller shall arrange on behalf of Purchaser and at Purchaser’s expense for any additional or incremental costs of shipment of the Equipment not then included in Seller’s Scope of Work.  In the event, as a result of direction by Purchaser, to store the Equipment in lieu of shipping to the Delivery Point and to retain care and custody, Seller will also retain risk of damage and loss until delivery to the Delivery Point or Optional Delivery Point.

# PAYMENT TERMS

## Payment of Purchase Amount.

### Payment Periods»

.  Payments shall be due and payable by Purchaser to Seller on the dates contained in Section 6.1.2 (the “Payment Date”); provided that Purchaser has received a properly prepared invoice and any other documentation supporting said payments thirty (30) Days prior to the Payment Date.

### Payment Schedule»

.  Purchaser will pay Seller one million, eight hundred and twenty-nine thousand dollars ($1,829,000) on or before January 15, 2001.

The final payment is also subject to Section 6.1.3.

### Retention Letter(s) of Credit»

. Purchaser shall retain the last seven hundred seventeen thousand and six hundred dollars ($717,600) (the “Retention Amount”) of the Purchase Amount until the expiry of the Primary Warranty Period of the Unit; provided, however, Purchaser shall pay Seller the Retention Amount as earned when:

###### Seller satisfies the requirements set forth in Section 6.6; and

###### Seller provides the Retention Letter of Credit in the amount of seven hundred seventeen thousand and six hundred dollars ($717,600).

Seller shall present as the “Retention Letter of Credit” an irrevocable on demand retention letter of credit for the full amount of the Retention Amount in a form generally in accordance with the sample set forth in Exhibit D from a U.S. bank located in Houston, Texas  acceptable to Purchaser.  The parties agree that, upon the expiry of the Primary Warranty Period of the Unit, the Retention Letter of Credit shall be extinguished.

## Payment Disputes»

.  Payment of any invoices or portions of invoices shall not prejudice the right of Purchaser to protest or question the correctness thereof or Seller’s compliance with the terms of this Agreement or any portion thereof or prejudice or constitute a waiver of any right of Purchaser hereunder.  Any amount questioned by either party and found to be in such party’s favor shall be refunded or paid, as appropriate. In the event an amount is withheld because of a dispute, and it is subsequently determined that the disputed amount or a portion of the disputed amount was due and payable, interest shall accrue at the Interest Rate commencing on the date the payment would have been payable if the dispute had not occurred.  Seller’s acceptance of partial payment of the Purchase Amount shall not be deemed to constitute a waiver of the right to receive amounts which are then in dispute, and Seller and Purchaser shall use their best efforts to resolve all disputed amounts as soon as practicable. Any undisputed amounts not paid when due shall bear interest at the Interest Rate.

## Payments Withheld or Offset.

### Payments Withheld»

.  Purchaser may, following Notice to Seller of its intent to withhold, and Seller not having eliminated the basis for the withholding within thirty (30) Days of Purchaser’s Notice, withhold payment on an invoice or a portion thereof in an amount and to such extent as may be reasonably necessary, subject to the dispute resolution provisions of ARTICLE XXVI, to protect Purchaser from loss because of:

##### defective work or Equipment not remedied pursuant to Section 9.5 or the warranty provisions of ARTICLE XIV;

##### third party suits, stop notices or liens for which Seller is liable under this Agreement, whether directly or pursuant to any indemnification obligation hereunder, (other than those provided for by insurance, bonds or other security) made on or filed with Purchaser or with respect to the Site or the Facility and not cleared by Seller by payment, deposit or otherwise to the reasonable satisfaction of Purchaser within ten (10) Days after receipt by Seller of written Notice from Purchaser requesting such action;

##### uninsured damage to Purchaser which results solely from Seller’s failure to obtain or maintain the insurance required by the provisions of ARTICLE XIX or from any action or inaction by Seller or any Vendor which excuses any insurer from liability for any loss or claim otherwise covered by insurance.

In the event a payment is improperly withheld or not paid when due and payable, such payment amounts due and payable shall accrue interest at the Interest Rate commencing on the date that payment would have been payable had the withholding not occurred.

### Offset for Liquidated Damages»

.  Purchaser shall have the right to offset from  any payments due to Seller any amounts due to Purchaser from Seller, including, but not limited to, the amount of any Liquidated Damages due from Seller.  In the event the Liquidated Damages exceed the payment amount, Purchaser shall retain the payment amount and invoice the excess amount of Liquidated Damages in accordance with Section 6.4.  In the event Purchaser offsets a Liquidated Damage which Seller disputes and it is subsequently determined that amount or a portion of the disputed amount should not have been offset, interest on the portion of the offset that should not have been offset shall accrue at the Interest Rate commencing on the date the payment that was offset would have been payable if the amount had not been offset.

## Payment of Liquidated Damages.

### Payment of O&M Instruction Liquidated Damages»

. Purchaser may upon the fifth (5th) Day of each month, invoice Seller for any O&M Instruction Liquidated Damages that accrued during the preceding month.  To the extent Purchaser has not declared that it has offset such O&M Instruction Liquidated Damages Seller shall pay such invoiced amount within thirty (30) Days of receipt of Purchaser’s invoice.

### Payment of Delivery Liquidated Damages»

.  Purchaser may upon the fifth (5th) Day of each month, invoice Seller for any Delivery Liquidated Damages that accrued during the preceding month.  To the extent Purchaser has not declared that it has offset such Delivery Liquidated Damages Seller shall pay such invoiced amount within thirty (30) Days of receipt of Purchaser’s invoice.

### Payment of Take Over Liquidated Damages»

.  Purchaser may upon the fifth (5th) Day of each month invoice Seller for any Take Over Liquidated Damages that accrued during the preceding month.  To the extent Purchaser has not declared that it has offset such Take Over Liquidated Damages Seller shall pay such invoiced amount within thirty (30) Days of receipt of Purchaser’s invoice.

### Payment of Performance Liquidated Damages»

.  Performance Liquidated Damages, if any, shall be calculated in accordance with Sections 10.9.1 and 10.9.2 and set out in the Units’ Performance Test Completion Certificate as prepared by Purchaser after completion of the Performance Test demonstrating that the Units have not met the Guaranteed Levels.  Purchaser may invoice Seller for Performance Liquidated Damages upon completion of the Performance Test on each Unit.   Purchaser may invoice for Performance Liquidated Damages regardless of whether or not Seller has achieved the Specific Performance Levels that correspond with the Guaranteed Levels.  In the event that the Performance Test which is the basis for the Performance Liquidated Damages occurred after Takeover, the effective date of delivery of the invoice shall be the date of delivery of the invoice to Seller.  Payment of the Performance Liquidated Damages shall be due within thirty (30) Days of the effective date of delivery of the invoice.

## Payment for Changes»

.  Unless a specific Change Order specifies otherwise, the net increase or decrease in the Unit price shall be reflected in the revised Purchase Amount.  Following the execution of an approved Change Order, Seller shall include in its next  invoice that percentage of the change which corresponds to the accumulated Payment Schedule percentages due as of the invoicing date. The remaining balance attributable to the change shall be paid in accordance with the Payment Schedule as a part of the revised Purchase Amount.

## Lien Release»

.  Seller represents that all amounts reflected on invoices submitted by Seller for payment are accurate, just, due and owing under the terms of this Agreement.  Purchaser shall not be required to make a payment under the Payment Schedule unless such invoice is accompanied with its affirmation warranting that all services, equipment, materials and information for which Seller seeks payment are free and clear of liens, claims, security interests and encumbrances arising in favor of Seller and its Vendors, and other persons or entities able to make a claim by reason of having provided labor, materials or equipment relating to performance of this Agreement or any portion thereof.  Seller agrees and represents that in submitting an invoice, Seller waives and releases all liens, claims, security interests and other encumbrances arising in favor of Seller by reason of having provided labor, materials or equipment relating to performance of this Agreement or any portion thereof, to the extent of such invoice.  In the case of payment of the Retention Amount, Seller shall not be entitled to payment of such Retention Amount unless and until Seller submits to Purchaser:

###### an affidavit in the form set forth in Exhibit S; and

###### a release and waiver of liens, claims, security interests and encumbrances for payment for labor, material and services arising out of the Scope of Work for Seller.

## Invoices.

### Agreement Reference»

.  Each invoice will reference Agreement 24-LM6K-2-99, 24LM6000-T-G-CIS01.

### Payee and Address for Invoices»

.  Invoices will be made out as payable by and mailed or hand carried to:

E-Next Generation, L.L.C.

1400 Smith Street

Houston, Texas 77002

Attention: Ben Jacoby

Fax: (773)

Purchaser anticipates that the mailing address of the invoice may change, and agrees to notify Seller of such change prior to the change.

### Date of Receipt»

.  Date of receipt of invoice by Purchaser will be evidenced by date stamp, or other generally accepted date receipting system.

## Method of Payment»

.  Payment will be made by electronic wire transfer, unless otherwise requested by Seller, to a United States bank within the United States.  Seller’s invoices must provide all necessary information (including Tax I.D. and account number) to enable Purchaser to effect such payment.

## Payments Not Acceptance of Work»

.  No payment made by Purchaser hereunder shall be considered or deemed to represent that Purchaser has inspected the work or Equipment or checked the quality or quantity thereof or that Purchaser knows or has ascertained how or for what purpose Seller has used sums previously paid, and shall not be deemed or construed as an approval or acceptance of any work or Equipment or Seller’s compliance with any other of its obligations under this Agreement or as a waiver of any claim or right Purchaser may have hereunder.

# COMMENCEMENT OF THE WORK AND TERMINATION

## Not Used.

## Not Used.

### Not Used.

### Not Used.

### Not Used.

### Not Used.

### »

## Termination»

.  This Agreement shall terminate upon the earlier of:

###### the cancellation by Purchaser of all the Scope of Work under Section 5.4; or

###### termination of this Agreement due to an event of default by Seller or Purchaser under ARTICLE XVII; or

###### when all obligations of the Parties under this Agreement are complete;

provided, however, that the rights and obligations of the parties under ARTICLE XVII (Default), ARTICLE XX (Indemnification), ARTICLE XXI (Non-Disclosure of Information), Section 30.2 (Governing Law), ARTICLE XXVI (Arbitration), ARTICLE XXVII (Limitation of Liability) and the indemnities set forth in the Agreement shall survive termination of the Agreement; except that, if termination occurs under (i) or (ii) above, obligations under ARTICLE XIV (Warranties) shall also survive.

# NOT USED

# INSPECTION AND CORRECTION OF WORK

## Inspections»

.  Seller shall provide Purchaser and Lender, or their designated representatives, access to the Scope of Work at all reasonable times wherever in preparation or progress and shall work closely with Purchaser in performing this Agreement.  Purchaser, or its designated representative, shall have the right  from time to time during this Agreement to observe, inspect, examine and review, Seller’s performance of this Agreement.  Purchaser’s rights to inspect under this Section 9.1 shall include but not be limited to manufacturing schedules; compliance with Specification; workmanship; dimensional tolerances; production tests; production inspections; assembly of components; panel inspection and testing; or witnessing testing of Equipment at any stage of design, procurement, production, or manufacture at  Seller’s works or those of its Vendors to verify that the Equipment conforms to the specified requirements of this Agreement. However, any observance, inspection or review of performance of this Agreement shall not constitute or be deemed to be actual control or a right to control Seller, its employees, agents, personnel, Affiliates, or Vendors.  Purchaser’s inspection of any part of the Equipment shall in no way affect Seller’s obligation to perform the Scope of Work in accordance with the Specification and all other terms of this Agreement, and any audit, examination, inspection, review, or testing by Purchaser shall not constitute acceptance or prejudice, be a waiver, or be deemed to be a waiver of any of Purchaser’s rights hereunder or of its rights to reject defective performance of this Agreement or release Seller from any obligation under this Agreement.  Seller shall not be required to provide Purchaser access to areas where Seller is performing proprietary work unless a portion of the Scope of Work is being performed in such an area.  In such event Seller may take measures as it deems appropriate to isolate other ongoing proprietary work from Purchaser’s view, or if not practical, Purchaser agrees to enter into a mutually agreeable confidentiality agreement pertaining to such proprietary work.

## Resident Facilities»

.  If reasonably requested by Purchaser,  Seller will provide facilities as reasonably available for a resident quality representative in Seller’s works and those of its Vendors who are manufacturing Major Components.

## Quality Plan»

.  Seller shall maintain a quality plan compliant with ISO 9001, 1994 and with the quality assurance plan set forth in Exhibit J, detailing:

###### specific authorities and responsibilities;

###### procedures, methods and work instructions; and

###### inspection and test plans.

In the event of a conflict between Exhibit J, ISO 9001, 1994 and Seller’s quality system, the order of precedence shall be, ISO 9001, 1994, Seller’s quality system and Exhibit J.

## Notice»

.   The agreed schedule of witness test points is set forth in Exhibit R, excluding those that have transpired on Units currently being manufactured and which test and inspection results have been provided to Purchaser.  Seller shall provide Purchaser with a Notice of the date of a witness test point not less than fourteen (14) Days prior to such date.

## Correction of Equipment»

.  Prior to Acceptance of each Unit, Seller shall, at its sole cost and expense and with exception of defects included in the Punchlist applicable to the Unit, promptly correct any part of the Equipment which is defective or not in accordance with this Agreement, regardless of the stage of its completion or the time or place of discovery of such defects  and regardless of whether Purchaser has previously paid for or accepted such part of the Equipment through oversight or otherwise. Seller shall replace or correct such defective work or condition such that the Equipment is in accordance with this Agreement, including the Specification.  Seller may repair (making an item functional, but not necessarily conforming the work to its original specification) the Equipment or a portion of the Equipment only with Purchaser’s prior written consent.  Seller agrees to complete the Punchlist to the satisfaction of Purchaser.  In the event Seller does not complete such Punchlist either (i) to the standards of the Agreement, or  (ii) within a reasonable period of time, but not later than one hundred eighty (180) Days after Takeover, Purchaser may, after prior written Notice to Seller, draw down against the Retention Letter of Credit the estimated value of the uncompleted work in order to have such work completed by others or invoice Seller for any deficiency.

## Additional Factory Testing»

.  Prior to delivery of Equipment at the Delivery Point, Purchaser may request Seller to repeat a test, perform the test using more precise instrumentation than planned, or conduct a test not in Seller’s standard factory test program. If commercially reasonable, Seller shall accommodate that request. In the event as a result of such Purchaser requested test requirement the Equipment is found to not be compliant with the requirements of this Agreement, Seller shall correct such noncompliance and the cost and time associated with such Purchaser test requirement shall be to Seller’s account.  If the Equipment is found to be compliant with this Agreement, Seller shall be eligible for a Change Order arising out of such Purchaser test requirement. If Seller is unable to accommodate Purchaser’s request under this section, and the Equipment is later found to be not compliant with this Agreement, any time spent by TD of I personnel in diagnosing or remedying the problem shall not be counted against Purchaser’s  TD of I hours.

## Release for Delivery»

.  In addition to other conditions set forth in this Agreement, prior to Seller performing any Major Component packing and prior to actual shipment, Seller shall provide, seven (7) Days in advance, Notice of such packing and request in writing to Purchaser’s Quality Assurance Manager for release to ship such Major Components.  Purchaser’s approval shall not be unreasonably withheld provided Seller has met the requirements of this Agreement.  In the event Purchaser fails to respond to Seller’s Notice of intent to pack and ship the Major Component within seven (7) Days, Seller  will proceed to perform packing and will complete staging at Seller’s facility pursuant to the Notice.

# DELIVERY AND PERFORMANCE

## Delivery of Documentation.

### Purchaser Review of Documents»

.  Seller shall provide the documentation described in this Agreement for Purchaser’s review and comment.  Purchaser’s review of such documentation shall be governed by Exhibit B-5.  The parties shall comply with the following in connection with the submittal, review and revision of all such documentation:

##### Upon delivery of each item of documentation Purchaser shall diligently review the document and provide Seller the applicable status code and comments within ten (10) business days of receipt;

##### Upon receipt of any comments from Purchaser, Seller shall diligently correct and resubmit such returned documentation within ten (10) business days; and

##### If Purchaser does not provide comments within ten (10) business day period after receipt, the document shall be deemed to be assigned a Status 1.

Purchasers review of any drawing or documents hereunder shall not be construed as constituting approval of Seller’s work, nor shall Purchaser’s failure to review or failure to comment be construed as approval or disapproval.  Seller at all times shall retain responsibility for a Scope of Work that meets the requirements of this Agreement, regardless of whether or not Purchaser has reviewed Seller’s drawings or documents.  Changes to the documentation for the convenience of Purchaser, which can be accommodated by Seller shall be adopted pursuant to ARTICLE XI of the Agreement.

### Delivery of Final O & M Instructions»

.  Seller shall provide the final operations and maintenance instruction manuals (the “O&M Manuals”) within forty-five (45) Days after the Site Delivery Date for the first Unit.  In the event Seller delivers such instructions later than forty-five (45) Days after the Site Delivery Date, Seller agrees that Liquidated Damages shall accrue at the rate of five hundred dollars ($500.00) for each Day of lateness (the “O & M Instruction Liquidated Damages”), not to exceed fifty (50) Days.  Purchaser may draw down the O & M Instructions Liquidated Damages from the Retention Letter of Credit upon the earlier of (i) delivery of completed final O&M Manuals, or (ii) fifty (50) Days of lateness in delivering the final O&M Manuals has accrued.  Installation and commissioning instructions will be provided by Seller’s TD of I representative at the Site to support installation, start-up and commissioning.

## Delivery of Equipment.

### Guaranteed Unit Delivery Dates»

.  Seller shall deliver Unit 17 (SN 309604) to the Delivery Point by no later than January 30, 2001.

The delivery date set forth herein shall be referred to as the “Guaranteed Unit Delivery Date” for the Unit.

#### Delivery Restrictions»

.  Seller shall use its reasonable efforts to deliver the Unit up to thirty (30) Days earlier than the time set forth in Section 10.2.1, provided that Purchaser has delivered a written Notice to Seller at least forty-five (45) Days prior to the Guaranteed Unit Delivery Date and Seller shall provide written Notice to Purchaser a minimum of fourteen (14) Days before early delivery.

### Inventory Upon Delivery»

.  Seller shall be required, and Purchaser shall have the right, to inspect the Equipment for completeness, condition and packing upon delivery to the Delivery Point and Seller shall immediately inform Purchaser of any damage discovered.

### Delivery»

.  Purchaser shall have the right to inspect the Equipment for completeness, condition and packing prior to loading on Seller’s or Purchaser’s  transport at the Delivery Point for the purposes of determining whether delivery of the Unit has occurred prior to the Guaranteed Unit Delivery Date.  Purchaser reserves the right to reject damaged Equipment.  In the event the Equipment is damaged or defective, Purchaser after making an initial assessment of the damage and consulting with Seller as to how such damage or defect will affect the installation, operation, performance, reliability, efficiency, and warranty of the damaged Equipment may either (i) reasonably determine that such damage or defect is such that the preceding criteria is so adversely affected that Purchaser cannot accept delivery of the damaged Equipment and declare that delivery has not occurred (in which case delivery for the purposes of assessing Delivery Liquidated Damages pursuant to Section 10.3.1 shall not have occurred), or (ii) after taking into account such criteria and Seller’s proposed plan for correcting such damage or defect in accordance with Section 9.5, declare that delivery has occurred.  In the event Purchaser discovers such a damage or defect, it shall immediately notify Seller of such damage.

#### Optional Delivery Point»

.  In the event Purchaser elects by Change Order  to have one or more Units delivered to the Site (the “Optional Delivery Point”), Seller shall deliver such Unit(s) on an expedited basis to Purchaser’s designated laydown area at the Site as soon as possible after the Unit is made available to ship at Seller’s facility.  Both parties shall inspect the Equipment for completeness and condition upon delivery to the Optional Delivery Point to determine if all of the Unit’s components have been delivered and if any Equipment has been lost or damaged. In the event any portion of the Equipment is not received or is found to be damaged or defective upon inspection at the Optional Delivery Point, Purchaser and Seller shall assess the damage, file appropriate insurance documents and Seller shall present Purchaser its plan for either (i) repairing the damage at the Site or (ii) replacing and delivering the missing, damaged or defective Equipment in accordance with this Agreement.  Seller shall repair such item in lieu of replacement with Purchaser’s prior approval which shall not be unreasonably withheld by Purchaser.

### Extensions of the Guaranteed Unit Delivery Date.

#### A Guaranteed Unit Delivery Date may only be extended if a Change Order has been executed by the parties in accordance with ARTICLE XI due to a delay caused by:

##### an Event of Force Majeure which justifies an extension under the terms of this Agreement;

##### a material breach of the Agreement or default (as defined in Section 17.5) thereunder by Purchaser; or

##### a Change in Law requiring changes to the Equipment as provided in Section 3.8.1(iv);

#### Seller’s entitlement to an extension of time shall be conditional upon:

##### its having used reasonable endeavors to mitigate the delay;

##### its having given proper and timely Notice in accordance with the terms of this Agreement; and

##### the delay not being attributable to Seller’s default.

### Loading Responsibilities at Delivery Point»

.  Seller shall provide written Notice of readiness to ship at least two weeks in advance of the expected date when the Equipment (or portions thereof) will be ready for shipment, specifying the date the Equipment will be ready to ship.  Seller shall be responsible for promptly loading the Equipment at the Delivery Point within forty-eight (48) hours of arrival of Purchaser’s transportation carrier at the Delivery Point.  Seller shall reimburse Purchaser all demurrage charges caused by its failure of its obligations under this section except to the extent that such failure is attributable to Purchaser’s acts or omissions.

### OffLoading Responsibilities at Optional Delivery Point»

.  Purchaser shall be responsible for promptly offloading the Equipment at the Optional Delivery Point from Seller’s mode of transportation within forty-eight (48) hours after arrival of Seller’s transportation carrier at the Optional Delivery Point.   Purchaser shall reimburse Seller all demurrage charges caused by its failure of this obligation except to the extent that such failure is attributable to Seller’s acts or omissions.

### Unit(s) Storage»

.  Seller agrees to provide ninety (90) Days of storage of each Unit without charge to Purchaser.  Seller shall assess storage charges ninety (90) Days after the later of the Guaranteed Unit Delivery Date or the date the Unit is delivered ex-works at the rates set forth in Exhibit N-2.  Seller shall retain all risk of loss and damage for Units while in its storage facility.

## Delivery Liquidated Damages.

### Unit Delivery Liquidated Damages»

.  For each Day that Seller delivers a Unit as defined in Section 10.2.3 to the Delivery Point  after its respective Guaranteed Unit Delivery Date, Purchaser may assess and Seller shall pay to Purchaser Delivery Liquidated Damages at the following rates per Day per Unit (the “Delivery Liquidated Damages”) for such lateness:

# Days Late			$/Day/Unit

1  - 15				$10,000.00

16 +				$25,000.00

For the avoidance of doubt, no Delivery Liquidated Damages shall be assessable as a result of Seller delivering an item of Equipment which is not a Major Component of the applicable Unit after such Unit’s Guaranteed Unit Delivery Date, unless such non-Major Component is shown by Purchaser to impede the continuous progress of installation of the Unit.  The Delivery Liquidated Damages rate assessable due to the late non-Major Component shall commence on the date(s) impedance first occurs and continues to occur, against the respective Delivery Liquidated Damages assessable on such date(s) after the applicable Guaranteed Unit Delivery Date.    All Delivery Liquidated Damages shall begin to accrue at 12:01 a.m. on the day following the Guaranteed Unit Delivery Dates.

For purposes of clarity, the following example is provided:

| Example 1 | - All Major Components of Unit 1 are on time |
| --- | --- |
| Situation: | - one or more non-Major Component of Unit 1 is 25 Days late and the first impedance occurs at Day 20 and lasts until delivery |
| LD Calculation: | 5 Days x $10,000/Day = $50,000 TOTAL: $50,000 |

| Example 2 |  |
| --- | --- |
| Situation: | - A Major Component of Unit 1 is 20 Days late - non-Major Component of Unit 1 is 25 Days late and causes an impedance commencing on Day 10 which lasts until Day 25 (15 Days) |
| LD Calculation: | - Major Component Delivery Liquidated Damages 15 Days x $10,000/Day = $150,000 5 Days x $25,000/Day = $125,000 |
|  | For Day 10 to 20 there are no additional Delivery Liquidated Damages assessable due to the late delivery of the non-Major Component since the Unit is considered not delivered because a Major Component has not been delivered and Delivery Liquidated Damages are assessed on that basis. |
|  | For Day 21 through Day 25 there are 5 Days of Delivery Liquidated Damages assessable associated with the lateness of the non-Major Component. |
|  | 5 Days x $25,000 = $125,000 TOTAL: $400,000 |

### Take Over Liquidated Damages»

.  Purchaser at its sole discretion may assess and Seller agrees to pay Liquidated Damages (the “Take Over Liquidated Damages”) at the rate of twenty-five thousand dollars ($25,000.00) per Day per Unit for each Day that the Unit fails to meet the Take Over Criteria by the end of the Time for Completion.

Assessment of such Take Over Liquidated Damages shall be subject to the following conditions:

##### Purchaser elects at its sole discretion not to Takeover a Unit which fails to meet its Specific Performance Levels or operate reliably;

##### During the Commissioning Period, Purchaser makes reasonable efforts to provide the necessary time and operating loads for Seller and Purchaser to commission and check out the Units.  Seller’s time and load requirement shall not be to the exclusion of the needs of other Facility equipment being commissioned.  Purchaser shall coordinate the most advantageous utilization of time and assets whenever conflicting requirement exist and such situations shall not be deemed delay by Purchaser;

##### Subject to (d) below, Purchaser may not assess Take Over Liquidated Damages prior to the expiry of the Commissioning Period;

##### In the event Seller fails to have a number of qualified TD of I personnel on Site in accordance with the requirements of Exhibit H-1 or to use its reasonable efforts to minimize time to make corrections, adjustments or repairs to the deficiently performing Unit(s) during the Commissioning Period, Purchaser shall have the right to void the Commissioning Period and assess Take Over Liquidated Damages without regard for the period afforded by the Commissioning Period;

##### Purchaser provides prompt oral Notice of delays affecting commissioning which is followed up in writing within seventy-two (72) hours of such Notice; and

##### Purchaser provides Seller its commissioning schedule no less than forty-five (45) Days prior to commencement of commissioning on the first Unit and provides periodic updates thereto.

#### In the event a Unit fails to meet its Emissions Guarantee or a Sound Level Guarantee (whether Purchaser elects to Takeover or not), without limiting Seller’s obligations hereunder and at Purchaser’s option, Seller shall use reasonable efforts to obtain, or assist Purchaser in obtaining, a permit variance or modification which will enable the Facility to operate at the electrical output demonstrated during the Performance Test at such higher sound or emissions levels.

In the event that one or more Units fail to meet the Emissions Guarantee or Sound Level Guarantee, in parallel with Seller’s efforts to remedy such failure, Purchaser and Seller agree to pursue alternate remedies including, at the Seller’s expense, improving or modifying other Facility components in order to mitigate the effects of such Unit(s) on the Facility’s performance.  Such alternate remedies must be mutually agreed to by Seller and Purchaser.

### Invoicing for Delivery and Take Over Liquidated Damages»

.  Except to the extent of an offset in accordance with Section 6.3, invoicing for and payment of O&M Instruction, Delivery and Take Over Liquidated Damages shall be in accordance with Section 6.4.

## Specific Performance Exhaust Gas Temperature and Energy Guarantees.

### Not Used.

### Specific Performance Exhaust Gas Temperature Guarantee For Combined Cycle Application of Units»

.  As a Specific Performance obligation, in the event the Facility is a combined cycle plant, Seller guarantees that the Adjusted Exhaust Gas Temperature of each Unit, as measured during the most recent Performance Test, shall not be less than 803 degrees Fahrenheit (ºF) (the “Specific Performance Exhaust Gas Temperature Guarantee”).  Subject to the provisions of Section 10.12.8, if the Adjusted Exhaust Gas Temperature of a Unit is greater than or equal to the Specific Performance Exhaust Gas Temperature Guarantee, Seller will be considered to have satisfactorily caused the Unit to meet the Specific Performance requirement associated with the Specific Performance Exhaust Gas Temperature Guarantee.

### Not Used.

### Specific Performance Exhaust Gas Energy Guarantee For Combined Cycle Application of Units»

.  As a Specific Performance obligation, in the event the Facility is a combined cycle plant, Seller guarantees that the Adjusted Exhaust Gas Energy of each Unit will be greater than or equal to 58,154 BTU/sec., reference 50 ºF (the “Specific Performance Exhaust Gas Energy Guarantee”).  Subject to the provisions of Section 10.12.8, if the Adjusted Exhaust Gas Energy of a Unit is greater than or equal to the Specific Performance Exhaust Gas Energy Guarantee, Seller will be considered to have satisfactorily caused the Unit to met the Specific Performance requirement associated with the Specific Performance Exhaust Gas Energy Guarantee.  The Parties agree to amend the Specific Performance Exhaust Gas Energy Guarantee to reflect changes in Basis Conditions to reflect the Site conditions for the combined cycle Facility within a reasonable time after receipt of Purchaser’s request.  Purchaser will only perform testing for compliance with the Specific Performance Exhaust Gas Energy Guarantee if a Unit when operated in combined cycle during the Performance Test fails to meet the combined cycle Facility Performance Guarantees.

### Interaction of Exhaust Gas Energy and Exhaust Gas Temperature with Turbine Net Output»

.  Exhaust heat measurement will be performed per the guidelines of ASME PTC 4.4.  The Specific Performance Exhaust Gas Energy Guarantee will be corrected to account for Adjusted Electrical Output in excess of the Specific Performance Electrical Output Guarantee.

## Sound Level Specific Performance Guarantee.

### Specific Performance Near Source Sound Level Guarantee»

.  As a Specific Performance obligation, Seller guarantees that the near field average A-weighted sound pressure levels of each Unit shall not exceed 85 dB(A) (referenced to 20 micropascals) (the “Near Source Sound Level Guarantee”) when measured during a Performance Test or Sound Level Test in accordance with the Sound Level Test Procedures at one and a half (1.5) meters above any working elevation and one (1) meter from the surface.

The Near Source Sound Level Guarantee is limited to normal continuous sound sources within the Scope of Work.

### Specific Performance Far Field Sound Level Guarantee»

.  As a Specific Performance obligation, Seller guarantees that the far field average A-weighted sound pressure level of one (1) Unit as installed with Seller provided auxiliary equipment (referenced to 20 micropascals) shall not exceed a contribution of 65 dB(A) proposed for a gas fueled and water injected Unit at 400 feet  (the “Far Field Sound Level Guarantee”) when measured during a Performance Test or Sound Level Test while operating at steady state loads from 50 to 100 percent in accordance with the Sound Level Test Procedure.

The Far Field Sound Level Guarantee is limited to normal continuous sound sources at Base Load within the Scope of Work.

### Not Used.

### Sound Level Test»

.  Purchaser may conduct tests at the Site to measure the Sound Levels generated by the Equipment in accordance with the procedures set out in Exhibit F-1 (the “Sound Level Test”).

###### Purchaser will (a) provide or cause to be provided, all instrumentation (including special test instrumentation), operations, labor, consumables required for the Sound Level Test (b) provide sufficient load during the Sound Level Test (c) read and record the Sound Level Test data, and (d) calculate the Sound Level Test results, all at no cost to Seller.

###### Seller (a) has the right of representation at the Sound Level Test (b) has the right to take its own data (c) will have access to all data resulting from the Sound Level Test, and (d) may verify the calculated Sound Level Test results.

## Specific Performance Exhaust Emissions Guarantee»

.  As a Specific Performance obligation, Seller guarantees that the Adjusted Emissions of a Unit when operated at Base Load at Basis Conditions (the “Emissions Guarantee”) will not be greater than the following values:

| Category | Value | Units of Measure |
| --- | --- | --- |
| Nox | 25 | ppmvd @ 15% O2 |
| CO | * | ppmvd @ 15% O2 |
| VOCs | 10 | ppmvd @ 15% O2 |
| PM10 | 4.5 | lb/hr (front and back half) |

NOx and PM10 emissions guarantees are valid for a load range of 30-100% of Base Load, a compressor temperature (CIT) range of -18F through 110F and a relative humidity range of 0-100% (except the CIT range does not include those coincident ambient temperature/humidity conditions in which the ambient air must be heated to prevent inlet frosting).  CO and VOC emissions are valid for a load range of 60-100% at Basis Conditions.  Where Facility conditions warrant, a CO and VOC emissions guarantee will be provided for load below 60% and for a range of compressor inlet temperature and relative humidity other than the Basis Conditions.

*For CO only, Seller provides the following guarantee:

| No. of Units at Facility | Average Per Unit |
| --- | --- |
| 1 Unit | 56 ppmvd |
| 2 Units | 56 ppmvd |
| 3 Units | 50 ppmvd |
| 4 Units | 47 ppmvd |
| 5 Units | 45 ppmvd |
| 6 Units | 43 ppmvd |

In no case shall the CO emission from any individual Unit (regardless of the number of Units at the Facility) exceed 56 ppmvd @ 15% O2 at loads of 60-100% of Base Load at Basis Conditions.  Subject to the provisions of Section 10.12.8 if the Adjusted Emissions of a Unit are less than Emissions Guarantee values, Seller will be considered to have satisfactorily caused the Unit to have met the Specific Performance requirement associated with the Emission Guarantee.  The above NOx and CO guarantees must include ambient contribution for NOx and CO.

## Electrical Output Guarantees.

### Electrical Output Guarantee»

.  Seller guarantees that the Adjusted Electrical Output of each Unit, as demonstrated during the most recent Performance Test, shall be equal to or greater than 48,315 kW (net of Unit auxiliary loads as listed in Exhibit F) (the “Electrical Output Guarantee”).

### Specific Performance Electrical Output Guarantee»

.  As a Specific Performance obligation, Seller guarantees that the Adjusted Electrical Output of each Unit, as demonstrated during the most recent Performance Test, shall be equal to or greater than 46,382 kW (net of Unit auxiliary loads as listed in Exhibit F) (the “Specific Performance Electrical Output Guarantee”).

### Not Used»

.

## Heat Rate Guarantees.

### Heat Rate Guarantee»

.  Seller guarantees that the Adjusted Heat Rate of each Unit, as demonstrated during the most recent Performance Test, shall not exceed 8,884 BTU/kWh (LHV) (the “Heat Rate Guarantee”).

### Not Used.

### Specific Performance Heat Rate Guarantee»

. As a Specific Performance obligation Seller guarantees that the Adjusted Heat Rate of each Unit, as demonstrated during the most recent Performance Test, shall not be more than 9,303 BTU/kWh (LHV) (the “Specific Performance Heat Rate Guarantee”).

### Specific Performance Guarantee»

. In the case of a dual fuel engine, specific performance guarantees shall also be provided for Electrical Output, Heat Rate and Emissions for liquid fuel operation.  The emissions guarantees will include all categories of emittants are contained in Section 10.6 and SO2 based on the Facility liquid fuel specification.

## Performance Liquidated Damages.

### Unit Output Liquidated Damages»

.  In the event that a Unit fails to achieve the Electric Output Guarantee, Liquidated Damages shall be assessed by Purchaser, and Seller agrees to pay at the rate of five hundred dollars ($500.00) for each kW that the Adjusted Electrical Output of a Unit (as measured during the most recent Performance Test) is less than the Electrical Output Guarantee (the “Unit Output Liquidated Damages”).

Seller agrees that Purchaser will conduct Performance Tests on the Unit at such time as Seller is confident that the Unit can be successfully tested, but not later than the end of the Commissioning Period.  Seller further agrees to pay the Unit Output Liquidated Damages attributable to the Shortfall of the Unit upon completion of the Performance Test.  If Purchaser expressly elects in writing not to test a Unit in a multiple Unit Facility for reasons not attributable to Seller, the untested Unit will be deemed to have made its Performance Guarantees.

### Heat Rate Liquidated Damages»

. Liquidated Damages shall be assessed by Purchaser, and Seller agrees to pay, if a Performance Test has been conducted on a Unit, at the rate of three thousand five hundred dollars ($3,500) for each BTU/kWh (LHV) that the Adjusted Heat Rate of the  Unit (as measured during the most recent Performance Test) exceeds the Heat Rate Guarantee (the “Heat Rate Liquidated Damages”).

Seller recognizes the Units will become ready for testing sequentially, and therefore agrees that Purchaser will conduct a Performance Test on each Unit at such time as Seller is confident that the Unit can be successfully tested, but not later than the end of the Commissioning Period.  Seller further agrees to pay Unit Output Liquidated Damages and Heat Rate Liquidated Damages attributable to the Shortfall of each individual Unit upon the completion of the Performance Test.

### Most Recent Performance Test»

.  Performance Liquidated Damages shall be assessed by Purchaser, and Seller agrees to pay on the results of the most recent Performance Test, including any reperformance of the Performance Tests in accordance with Section 10.12.8, regardless of whether the performance improves or worsens upon the later Performance Test.

### Performance Test Required»

.  No Performance Liquidated Damages shall be payable if no Performance Test has been conducted.

### Setting Out of Performance Liquidated Damages»

.  Performance Liquidated Damages, if any, shall be due and payable by Seller pursuant to Section 6.4 in accordance with the rates set forth in this Section 10.9 and the calculations set forth in the Performance Test Completion Certificate prepared by Purchaser.

### Not Used.

### Seller’s Improvement of Performance»

.  In the event one or more of the Units fail to meet a Guaranteed Level but meet the Specific Performance Levels, Seller shall use its reasonable best efforts, for a period of not more than one hundred eighty (180) Days after the initial Performance Test is run for a Unit, to cause such Unit to meet the Guaranteed Levels.  Prior to Takeover of the Facility, Purchaser shall provide Seller a reasonable opportunity to implement such changes or improvements; however, it is understood by both parties that Purchaser will not be required to delay commencement of Commercial Operation of the Facility for the purpose of Seller making such changes or improvements.  After Purchaser places any Unit into Commercial Operation Purchaser shall provide Seller reasonable opportunity to make such corrections or improvements during scheduled and unscheduled outages.

### Reduction in Performance Liquidated Damages»

.  In the event Seller improves a Unit’s performance for which Performance Liquidated Damages are payable after Purchaser has:

###### made an offset in accordance with Section 6.3 against payments due Seller to cover Performance Liquidated Damages; and/or

###### been paid all Performance Liquidated Damages invoiced to Seller;

then Seller shall be entitled to a reduction/refund in the Performance Liquidated Damages subject to the following:

A) If:

###### the Shortfall has not prevented Purchaser from placing the Unit into Commercial Operation;

###### such corrections are made and are complete prior to Commercial Operation of the applicable Unit;  and

###### such corrections cause a reduction in the performance Shortfall;

then Purchaser shall:

###### refund to Seller an amount equal to the Performance Liquidated Damages associated with such reduction in the Shortfall; and/or

###### reduce the offset associated with such reduced Shortfall;

however, such reduction in offset or amount of refund shall not exceed the amount actually offset in accordance with Section 6.3 or paid in accordance with Section 6.4 for such Shortfall; or

B)   If:

###### such Shortfall has prevented Purchaser from placing the Unit into Commercial Operation; or

###### the corrections to reduce a Shortfall are completed after the Unit goes into Commercial Operation, and such corrections are completed within One Hundred Eighty (180) Days after the Unit went into Commercial Operation, and such corrections cause a reduction in the Shortfall;

then Purchaser shall:

###### refund to Seller an amount equal to the Performance Liquidated Damages associated with such reduction in the Shortfall; and/or

###### reduce the offset associated with such reduced Shortfall;

however, such refund of Performance Liquidated Damages or reduction of offset will not exceed the amount actually offset in accordance with Section 6.3 or paid in accordance with Section 6.4 for such Shortfall and the amount of such refund or reduction of offset shall itself be reduced by the following amounts (based on a ten (10) year lifespan and a net present value factor of seven (7)) for each Day that passes from date of the Performance Test on which the Performance Liquidated Damages were originally based upon until the date that Seller demonstrated the improved performance.

##### At a rate of $0.20/kW per Day that the total Adjusted Electrical Output Shortfall of the Unit is reduced (the “Output Liquidated Damages Refund Reduction”).

##### At a rate of $1.37/BTU/kWh per Day that the average Adjusted Heat Rate Shortfall of the Unit is reduced (the “Heat Rate Liquidated Damages Refund Reduction”).

### »

No refund of Performance Liquidated Damages shall be made if the corrections are made after one hundred eighty (180) Days after Takeover of the Facility, unless Purchaser elects to do so as a result of the corrective action plan presented by Seller prior to the expiry of such one hundred eighty (180) Day period.  In the event Seller determines the cause of a portion or all of the Shortfall prior to the expiry of the one hundred eighty (180) Day period following Takeover, but in spite of its best efforts is not able to effect the necessary corrections to the Equipment, Seller may present a correction plan that extends beyond such one hundred eighty (180) Day period.  Purchaser, at its sole discretion, may elect to permit Seller the opportunity to make such corrections.

## Maximum Liabilities for Liquidated Damages.

### Maximum O&M Instruction Liquidated Damages»

.  Seller’s maximum aggregate liability for O&M Instruction Liquidated Damages shall be fifty thousand dollars ($50,000.00).

### Maximum Delivery Liquidated Damages»

.  Seller’s maximum aggregate liability for Delivery Liquidated Damages shall be fifteen percent (15%) of the Maximum Liability Amount.

### Maximum Take Over Liquidated Damages»

.  Seller’s maximum liability for Take Over Liquidated Damages shall be fifteen percent (15%) of Maximum Liability Amount.

### Maximum Unit Output Liquidated Damages»

.  Seller’s maximum liability for Unit Output Liquidated Damages shall be ten percent (10%) of Maximum Liability Amount.

### Maximum Heat Rate Liquidated Damages»

.  Seller’s maximum liability for Heat Rate Liquidated Damages shall be ten percent (10%) of Maximum Liability Amount.

### Maximum Aggregate Liquidated Damages»

.  Notwithstanding Section 10.3 and Section 10.9, Seller’s maximum aggregate liability for Liquidated Damages, if any, under this Agreement shall be thirty percent (30%) of the Maximum Liability Amount.

## Liquidated Damages Not Penalty»

.  The parties acknowledge and agree that because of the unique nature of the Equipment and the time requirements for performance:

###### Purchaser shall be damaged by:

Seller failing to accomplish delivery of documents;

Seller failing to deliver the Units by the Guaranteed Unit Delivery Date;

A Unit’s performance causing Purchaser a delay in Take Over of the Unit; and/or

Seller failing to cause the Units to achieve Guaranteed Levels (the “Liquidated Damages Events”);

###### it would be impracticable or extremely difficult to fix the actual damages resulting from late delivery or failure to meet the Guaranteed Levels;

###### any sums which would be payable under this ARTICLE X are in the nature of Liquidated Damages, and not a penalty, and are fair and reasonable; and

###### such payment represents a reasonable estimate of fair compensation for the losses that may reasonably be anticipated from such Liquidated Damages Events.  Such payments are compensation solely for Liquidated Damages Events and shall not prejudice any other rights of Purchaser hereunder and shall not relieve Seller of its obligations hereunder.

## Performance Tests.

### Concurrence of Tests»

.  To the extent practical Purchaser shall conduct the Performance Tests for a Unit concurrently so as to  assure itself that the Unit is capable of meeting all of the Guaranteed Levels and Specific Performance Levels concurrently.

### Election to Conduct a Performance Test»

.  Purchaser shall conduct the first series of Performance Tests prior to the expiry of the Installation Period, provided however, Purchaser at it’s sole discretion may elect to waive the conduct of the Performance Test.

### Specific Performance Achievement»

.  In the event that as a result of the performance functional checks it is reasonably evident that the Equipment is performing significantly out of compliance with a Specific Performance Level; Purchaser may require Seller to take corrective actions in accordance with Section 10.13 without the benefit of Performance Test or Sound Level Test results; otherwise, Performance Test or Sound Level Test results will be required to be the basis of such action.

### Timing of Tests.

#### Purchaser may conduct or cause a Performance Test or Sound Level Test to be conducted on the Units as soon as possible after commissioning and after Seller’s representative certifies that the Units to the best of his knowledge:

###### are properly installed;

###### can be safely tested; and

###### have been and may be run up to full load.

#### In the event that a Performance Test or Sound Level Test has been conducted on the Units within the Installation Period and corrective measures or modifications have been performed, if Purchaser elects to conduct a retest in accordance with Section 10.12.8, it shall conduct such retest within thirty (30) Days of the completion of such corrective measures or modifications.

Unit performance shall not be adjusted for degradation unless such Unit has been operated for more than three hundred (300) operating hours at the time of conduct of the initial Performance Test.  Operating hours necessary to diagnose a Unit’s failure to operate in accordance with the requirements of this Agreement shall not be added to the hour count.  Operating hours associated with the conduct of Performance Tests shall be added to the operating hour count.  Methods of correcting for degradation shall be set out in the Performance Test Procedures.

### Seller Presence at Tests»

.  Seller shall have the right to be present or to have a representative present at each Performance Test and Sound Level Test.  Purchaser shall provide Seller with a thirty (30) Days initial Notice and a five (5) Days’ confirmation Notice in advance of each Performance Test.

### Test Results»

.  Upon the completion of each Performance Test, or Sound Level Test, Purchaser will issue a Performance Test Certificate setting forth the results achieved during such test.

### Performance Test Procedures»

. No later than six (6) months after the Order Definition Meeting, Seller will submit to Purchaser a complete set of recommended procedures for the conduct of the Performance Tests and Sound Level Tests (the “Test Procedures”) and for verification of all major systems.  Purchaser shall review and respond to Seller’s recommended Test Procedures within  thirty (30) Days of the submission.  In the event the Test Procedures are not approved by Purchaser in such response, the parties shall meet to finalize the Test Procedures within thirty (30) Days of Purchaser’s response.

### Reconduct Tests»

.  In the event that Seller has made repairs (including those pursuant to ARTICLE XIV) or has taken other corrective action to correct a Shortfall subsequent to the conduct of the Performance Test or Sound Level Test, Purchaser at its sole reasonable discretion may require the conduct of another Performance Test(s) or Sound Level Test to:

###### demonstrate that such repairs or corrective actions have caused the Equipment to now meet the previously failed Specific Performance Level or Guaranteed Level which such repairs or corrective actions were intended to correct;

###### demonstrate that such repairs or corrective actions have not caused the performance of the Equipment as it pertains to the Specific Performance Levels to degrade so that the Equipment no longer meets the Specific Performance Levels; and/or

###### demonstrate that such repairs or corrective actions have not caused the performance of the Equipment as it pertains to the Guaranteed Levels to degrade since the last Performance Test or Sound Level Test.

### Not Used.

### Fittings, Instrumentation and Test Uncertainty.

###### Seller shall be responsible for ensuring that the Units are designed and manufactured with the proper fittings, orifices, and connections necessary to permit the conduct of the Performance Tests in accordance with the Test Procedures.  Seller shall also be responsible for identifying to Purchaser the necessary fittings, orifices, and connections that should be installed in the remainder of the Facility to allow a proper Performance Test to be conducted.

###### The parties anticipate using station instrumentation for Performance Tests.  In the event that Purchaser elects to conduct the first Performance Test on a Unit, the cost of the necessary instrumentation that is not Facility instrumentation shall be borne by Purchaser, and in the case of subsequent Performance Tests caused by Seller’s Equipment not meeting a Guaranteed Level or Specific Performance Level the cost of instrumentation shall be to Seller’s account.

###### Seller will be allowed to account for test uncertainty when comparing the Adjusted Electrical Output to the Electrical Output Guarantee and the Specific Performance Electrical Output Guarantee, and the Adjusted Heat Rate to the Heat Rate Guarantee and the Specific Performance Heat Rate Guarantee.  The definition of and calculation of the test uncertainty shall be in accordance with ASME PTC 22, ASME PTC 19.1 and the Performance Test guidelines set forth in Exhibit F.

### Consumable Spare Parts During Retests»

.  The cost of consumable spare parts during retests caused by Seller’s failure to achieve Guaranteed Levels or Specific Performance Levels shall be to Seller’s account.

## Remedies For Failure to Meet Specific Performance Requirements.

### Corrective Actions»

.  If one or more of the Units at the Facility fails to satisfy one or more of the Specific Performance Levels or a Guaranteed Level, Purchaser will, if Seller so requests and if Takeover has not occurred, operate the Facility or cause the Facility to be operated at the loads and conditions necessary to allow Seller to determine the causes of the nonconformity, if any, and the expedient remedial action.

Following the commissioning functional checks or Performance Test as applicable, or additional running of the Facility for such diagnostic purposes, Seller shall at its own expense:

###### repair at the Site such parts of the Unit(s); or

###### remove the defective parts and provide and install the new parts,

to cause such failed Unit(s) to meet Specific Performance Levels (such election subject to Purchaser’s approval, such approval shall not be unreasonably withheld).

If such failed Unit(s) still fail to satisfy Specific Performance Levels, Seller shall at its own expense make such further repair or replacement until the Units meet Specific Performance Levels.

### Failure to Achieve Specific Performance»

.  In the event of any failure to achieve the Specific Performance Levels within one hundred eighty (180) Days of the completion of the applicable Unit’s initial Performance Test, Purchaser shall have the right to terminate the Agreement in accordance with Sections 7.2.7, 17.2, 17.3 and 17.4.

## Acceptance»

.  Acceptance for each Unit shall occur upon:

##### the earliest of:

###### if, through no fault of Seller, a Performance Test or Sound Level Test on the Unit has not been conducted by the end of the Installation Period (except as provided in Section 10.12.4.2);

###### upon the issuance of a Performance Test Completion Certificate by Purchaser evidencing that the Specific Performance Levels and the Guaranteed Levels have been achieved (such Performance Test Completion Certificate to be issued within thirty (30) Days after successful completion of testing); or

###### in the event that the Unit has passed the Specific Performance Levels, but not the Guaranteed Levels and (1) Seller has for a period of one hundred eighty (180) Days after the initial Performance Test of the Unit made reasonable best efforts to improve the Unit’s performance and still have met the Specific Performance Levels, but not the Guaranteed Levels, and, (2) Seller has paid Liquidated Damages in accordance with Section 6.4 hereof with respect to any Guaranteed Levels not achieved;

Provided that:

##### all special tools provided hereunder shall have been delivered to Purchaser;

##### Seller has delivered to Purchaser a waiver of liens in form as shown in Exhibit S that have been or could have been placed upon the Equipment and that there are no outstanding claims of Seller or any Vendor with respect to the Equipment;

##### Seller has paid any Take Over Liquidated Damages due;

##### Seller has paid any Delivery Liquidated Damages due;

##### Seller has paid any O & M Instruction Liquidated Damages;

##### All Punchlist items have been completed;

##### Seller has satisfied all other material obligations required for Purchaser to achieve Takeover; and

##### Seller has provided all O&M Manuals.

Upon the occurrence of these events, Seller may submit a certificate to Purchaser indicating it has achieved Acceptance.  Purchaser shall within ten (10) Days of receipt of such certificate, either sign such certificate acknowledging concurrence or reject such certificate specifically stating the reasons for such rejection.

## Unit Serial Numbers»

.  Seller has identified and listed in Exhibit P, the Unit serial numbers which are available at the Effective Date of this Agreement.  To the extent Unit serial numbers are not so identified, the serial numbers of the remaining Units will be made available one hundred twenty (120) Days prior to the Guaranteed Unit Delivery Date.  Seller may not change the Units associated with such serial numbers or the serial numbers themselves without Purchaser’s prior written agreement. Purchaser shall only withhold such written agreement if, based upon the reasons given by Seller and verified by Purchaser, Purchaser reasonably believes that such change would result in a delay of the Units.

# CHANGE ORDER

## Adjustment of Purchase Amount»

.  The Purchase Amount shall be subject to adjustment solely for (a) Purchaser-requested changes in the Scope of Work in accordance with Section 11.2, (b) Seller-requested changes in the Scope of Work, which are approved in writing by Purchaser in accordance with Section 11.3, and (c) the circumstances described in Section 5.3.

## Purchaser Requested Change Order»

.  If Purchaser desires to make any change in the Scope of Work (a “Change Order”), Purchaser shall advise Seller, and Purchaser and Seller shall consult concerning the estimated cost and impact on the Guaranteed Unit Delivery Date(s) and the Purchase Amount. Thereafter, Purchaser may request, and Seller shall upon receipt of such reasonable request prepare, a detailed estimate of the cost of such change, taking into account the effect of such change on the Scope of Work and other agreed upon and contemplated Change Orders.  Purchaser shall review Seller’s estimate, and if Purchaser accepts or the parties otherwise agree as to the Change Order, it shall be endorsed by Purchaser.  Thereafter, the parties shall promptly adjust the Guaranteed Unit Delivery Date(s) and the Purchase Amount and any other Exhibits requiring adjustment to reflect the Change Order.  In the event Seller proceeds with any proposed changes in the Scope of Work prior to execution of a Change Order, Seller shall do so at its own risk.  Purchaser has no obligation to pay Seller for any additional cost and Seller is not entitled to any extension of time for performance as a result of any change implemented by Seller without an executed Change Order.  Modifications or changes in the Specification which are within the general scope  of the Agreement may be made at any time by Purchaser’s Representative written order to Seller.

## Seller Requested Change Order»

.  If Seller determines that a condition or the occurrence of an event requires a change in the Scope of Work, Seller shall within fifteen (15) Days of being aware of the occurrence or condition of the event prepare and deliver to Purchaser a request for a Change Order which shall describe such condition or event in detail.  Within fifteen (15) Days following delivery of such request, or such other period as may be agreed upon by the parties, Seller shall specify the  proposed adjustment to the Scope of Work, the Guaranteed Unit Delivery Date(s) and/or the Purchase Amount requested by it.  Following receipt of such request, Purchaser shall determine in its sole and exclusive discretion whether any changes to the Scope of Work, the Guaranteed Unit Delivery Date(s) and/or the Purchase Amount shall be effected, but failure by Purchaser to approve any such changes  shall not affect or modify any of Seller’s obligations hereunder or cause an increase in the Purchase Amount and/or extension of the Guaranteed Unit Delivery Date(s).  If Seller proposes changes in the Scope of Work to Purchaser, Seller shall not make such changes without receiving the prior written consent of Purchaser which shall be reflected on a Change Order, in accordance with the procedures as described in Section 11.2.

## Adjustment to Guaranteed Unit Delivery Dates»

. The Guaranteed Unit Delivery Dates shall be subject to adjustment solely for (a) Purchaser-requested changes in the Scope of Work in accordance with Section 11.2,  (b) Seller- requested changes in the Scope of Work, which are approved in writing by Purchaser in accordance with Section 11.3, and (c) the circumstances described in Section 10.2.4.1., if and to the extent that such circumstances directly result in delay.

## Disputes»

.  In the event of an unresolved dispute regarding a Change Order, the parties agree that the matter shall be submitted to dispute resolution in accordance with ARTICLE XXVI.

## Change Order Pricing»

.  All changes to this Purchase Amount resulting from a Change Order shall be either lump sum, or unit price.

# (NOT USED)

# ORDER OF PRECEDENCE

## Order of Precedence»

.  This Agreement shall be read as a whole and in the event of a conflict between documents, the following order of precedence shall govern:

a:  Articles I through XXX

b:  Exhibits, other than Exhibits B and B-1

c:  Exhibit B

d:  Exhibit B-1

# WARRANTY

## Seller’s Warranty»

.  Seller warrants with respect to each Unit on a continuing basis during the Primary Warranty Period, that:

##### the Equipment and all other materials and articles furnished hereunder are new, unrepaired (except as permitted in writing by Purchaser) and of suitable grade for the purpose intended;

##### the Scope of Work was performed in a good and workmanlike manner and in  accordance with the degree of care, skill and diligence consistent with industry standards, the Equipment is free of defects in materials and/or workmanship and the Equipment is designed and fit for the purpose of generating electric power when operated in accordance with Seller’s specific written operation instructions and, in the absence thereof, in accordance with generally accepted operation practices of the electric power producing industry;

##### the Equipment conforms to the Specification and other requirements of this Agreement;

##### the Equipment will be “Year 2000 Capable,” meaning that (I) the computer hardware and software that is part of said Equipment and any information technology contained therein will accurately process date and time data within the Warranty Period and (ii) neither performance nor functionality of the said Equipment will be affected materially by dates within the Warranty Period.

### Primary Warranty Period»

. With respect to each Unit, the Primary Warranty Period shall be for one (1) year commencing upon the earlier of:

###### Acceptance; or

###### Commercial Operation (the “Primary Warranty Period”).

### Warranty Clarification»

.  Seller shall have no obligation for correction, repair or replacement of the Equipment in accordance with this ARTICLE XIV to the extent that a defect is the result of:

###### normal wear and tear;

###### normal degradation in the performance of the Equipment;

###### Purchaser’s misuse or negligence;

###### the Equipment not having been operated and maintained in accordance with Seller’s written operating limitations and maintenance instructions, or accepted industrial practice.

###### installation of the Equipment or any relevant part thereof by Purchaser or its contractors other than in conformance with Seller’s or its Vendor’s written specifications, manuals or other written instructions (except as specifically set forth in this Agreement); or

###### a Purchaser directed change in the design or construction of the Equipment which Seller reasonably disputes as not being in accordance with good workmanship or generally accepted professional engineering standards, provided that Seller has given Purchaser written Notice of its dispute prior to performing any such change and such dispute ultimately is resolved in Seller’s favor.

###### Seller also shall have no obligation for defects in the Equipment to the extent that, after the commencement of the Primary Warranty Period, such defect arises out of Purchaser’s failure to: notify Seller within a reasonable time after an Equipment defect becomes apparent (such Notice not to be later than thirty (30) Days from the date supervisory level personnel of Purchaser responsible for the Facility become aware of such defect).

###### Seller shall have no Year 2000 Warranty responsibility for any such failure of the Equipment that is directly or indirectly caused by the failure of products used with the Equipment to function properly, use of data or information that is inaccurate or incompatible with the Equipment’s interfaces, requirements, or specifications, or use of the Equipment other than in accordance with written instructions of Seller.

### Warranty Breach Notice»

.  In the event Purchaser believes that a defect has arisen, Purchaser shall notify Seller of such a defect in writing (fax notification followed by mailed Notice) describing the nature of the breach.

## Extended Warranty Period.

### Continued Warranty on Corrections or Repairs Performed During the Primary Warranty Period»

.  With respect to any portion of the Equipment corrected, repaired, modified or replaced as a result of a defect manifesting during the Primary Warranty Period,  Seller shall warrant such portion of the Equipment in accordance with Section 14.1 for a period of twelve (12) months from the date of such modification or correction (the “Extended Warranty Period”), but in no event shall the Extended Warranty Period extend more than twelve (12) months beyond the Primary Warranty Period.

### Extension of Warranty Due to Unavailability»

.  The Primary Warranty Period or Extended Warranty Period shall be extended by a period equal to the period during which the Unit(s) (or that part in which the defect or damage has appeared or occurred) cannot be reliably operated as intended by reason of that defect or damage.

## Obligations, Responsibilities and Recourse»

.  If the warranties set forth in Section 14.1 hereof are breached, Seller shall repair, replace, and/or correct the applicable portion of the Scope of Work immediately or on an expedited basis such that it meets the requirements of this Agreement but at no cost to Purchaser.  Seller shall provide a service engineer to begin corrective action on the Equipment as soon as reasonably possible after receipt by Seller of Purchaser’s Notice referred to in Section 14.1.3 but not later than seventy-two (72) hours after receipt of such Notice.  Seller shall, at its sole expense, disassemble, remove, replace and reinstall the Equipment to the extent necessary while minimizing the downtime required for Seller to perform its warranty obligation.  Purchaser shall provide Seller with full and free access to the Facility to perform its warranty obligations under this Agreement, so long as such access does not unreasonably interfere with operation of the Facility.  Any change to parts or equipment that would alter conformance with the Specification may be made only with prior written approval of Purchaser in accordance with the terms of ARTICLE XI hereof.  If, after notification of such defect, Seller shall unreasonably delay the commencement, continuance or completion of making good such defect(s), Purchaser may then, following written Notice to Seller, correct such defect(s) in accordance with this Agreement, and Seller shall be liable for all reasonable costs, charges and expenses incurred by Purchaser in connection with such reasonable repair or replacement and shall forthwith pay to Purchaser an amount equal to such costs, charges and expenses upon receipt of invoices certified by Purchaser.  In an emergency where delay would cause serious risk of loss or damage, and Notice to and corrective action by Seller is not possible in a timely manner, Purchaser may take such actions as reasonably necessary to mitigate such risk and correct the deficiency with oral Notice followed immediately with written confirmation of the Notice to Seller in accordance with Section 14.1.3.  Such emergency actions shall be to the account of Seller.

## Not Used.

## Limited Warranty»

.  THE WARRANTIES AND REMEDIES FOR BREACH OF WARRANTY CONTAINED IN THIS AGREEMENT ARE THE EXCLUSIVE WARRANTIES AND WARRANTY REMEDIES BY SELLER APPLICABLE TO THE EQUIPMENT AND ARE EXPRESSLY IN LIEU OF ANY OTHER WARRANTIES, EXPRESS OR IMPLIED, INCLUDING ANY IMPLIED WARRANTY OF SATISFACTORY QUALITY (MERCHANTABILITY) OR FITNESS FOR A PARTICULAR PURPOSE, OR ANY OTHER WARRANTY EXPRESS OR IMPLIED AGAINST VICES OR DEFECTS, LATENT  OR OTHERWISE.  SELLER NEITHER ASSUMES NOR AUTHORIZES ANY OTHER PERSON TO ASSUME FOR IT ANY OTHER WARRANTY OBLIGATION IN CONNECTION WITH THE EQUIPMENT OR ANY PART THEREOF.

## Repairs and Alterations by Others»

.  Unless Seller has failed to provide a service representative or otherwise comply with its repair obligations under this Agreement, Seller shall have no obligation hereunder to the extent that the Equipment becomes defective in whole or in part as a direct result of repairs (other than normal maintenance as set out in Seller’s instruction manuals, approved emergency repairs, and replacing defective parts with Seller approved spares) not made by Seller or a GE-managed depot repair facility.  In the event that Purchaser or a third party other than a GE-managed depot undertakes major unauthorized alterations or repairs to the Equipment without Seller’s written consent, any warranty applicable to the Equipment adversely affected by such alterations or repairs shall be terminated.

## Termination of Warranty»

.  If a defect covered by the warranty is discovered by Purchaser and Purchaser does not:

###### promptly take reasonable action to mitigate the damage consequent to the occurrence of the defect; or

###### notify Seller and allow Seller to correct the defect in accordance with Section 14.3.

Seller shall not be responsible for repair of that part of the damage attributed to Purchaser’s failure to take such action.

# RISK OF LOSS AND TITLE

## Risk of Loss»

.  Seller shall bear the risk of loss and damage with respect to an item of Equipment until Seller has completed the delivery at the Delivery Point in accordance with Section 10.2.5.  In the event Purchaser elects to use the Optional Delivery Point, the point of transfer of risk of loss and damage will be set out in the applicable Optional Delivery Point Change Order pursuant to Section 10.2.3.1.

## Title.

### Passage of Title»

.  Title to Equipment, drawings, specifications, O & M Manuals and like materials prepared specifically for the Scope of Work under this Agreement will pass from Seller to Purchaser when the Equipment is ready for shipment to the Delivery Point(s) and Seller has notified Purchaser that the Equipment is ready for shipment.  Seller shall be the importer of record for all such non-U.S. manufactured Major Components, and will be responsible for all import duties and costs associated with clearing U.S. customs. Seller warrants that legal title to and ownership of the Equipment (including, subject to the use and disclosure limitations in ARTICLE XXI, all calculations, as-built, arrangements drawings, detailed engineering drawings and other drawings and documentation required by Purchaser in connection with the operation and maintenance of the Equipment) shall be free and clear of any and all liens, claims, security interests or other encumbrances when title thereto passes to Purchaser.  Title to Seller’s standard drawings and documents which are provided to Purchaser shall remain with Seller, provided however Seller grants permission without charge to Purchaser, Lender, Purchaser’s operator and subsequent owners and operators to use such documents as set out in Section 15.3.

### Infringement Cures and Defense»

.  In the event a suit or proceeding is brought against Purchaser, Lender, Purchaser’s Facility operator or their Affiliates, (the “Patent Indemnities”) for infringement of any patent, copyright, trademark, trade secret or other intellectual property right, Seller shall indemnify and hold harmless Patent Indemnities, their authorized agents, and anyone directly or indirectly employed by them from and against all claims, damages, losses and expenses (including attorneys’ fees) arising out of any infringement of patent rights or copyrights incident to the use or production of the Equipment or incorporation therein of any invention, design process, product or device not specified in the Agreement, and shall defend all such claims in connection with any alleged infringement of such rights.  Seller shall pay all costs and expenses of any such action or suit or threat thereof, including compensation and expenses of experts and counsel of its choice and selection and Seller shall also pay and hold Patent Indemnitees free and harmless from expenses incurred or any damages or other sums awarded or assessed in any such action or suit including costs resulting from imposition of any injunction against Patent Indemnitees.  Patent Indemnitees may be represented by counsel of their own selection and expense, but agree to cooperate fully in the defense of any such action or suit and to furnish all the evidence in its control.

Nothing herein shall authorize Seller to settle any such suit or action as referred to in this Section 15.2.2 without prior authorization from the affected Patent Indemnitee if, by such settlement, the affected Patent Indemnitee shall be obliged to make any monetary payment, part with any property or any interest therein, to assume any obligation or restriction upon operation of the Equipment or Facility or production of electricity, to be subject to any injunction or to grant licenses or other rights under its patent or other industrial or intellectual property rights, or surrender or release any other rights, remedies, interests or claims.

In the event a Patent Indemnitee is as a result of such suit or proceeding prevented from using such alleged infringing Equipment or other deliverables, Seller shall undertake and conclude as quickly as reasonably possible at its option and expense one of the following courses of action:

###### obtain the right to continued use of the Equipment or other deliverables under this Agreement;

###### correct or modify the infringing aspect of the Equipment or other deliverables under this Agreement so that it becomes non-infringing; or

###### replace the infringing Equipment or other deliverables under this Agreement with equivalent non-infringing Equipment or other deliverables.

THIS SECTION IS AN EXCLUSIVE STATEMENT OF ALL THE DUTIES OF THE PARTIES RELATING TO PATENTS AND DIRECT OR CONTRIBUTORY PATENT INFRINGEMENT AND OF ALL THE REMEDIES OF PURCHASER RELATING TO ANY CLAIM, SUIT, OR PROCEEDING INVOLVING PATENTS, COPYRIGHT, TRADEMARK, TRADE SECRET OR OTHER INTELLECTUAL PROPERTY RIGHTS.  Compliance with this Section as provided herein and ARTICLE XXI shall constitute fulfillment of all liabilities of the parties under the Agreement with respect to patents, copyright, trademark, trade secret or other intellectual property rights.

## Seller’s Drawings, Etc. for Use by Purchaser»

.  All drawings, documents, engineering and other data furnished or to be furnished by Seller in performing the Scope of Work may be used by Purchaser, Purchaser’s operator or a subsequent owner for the purpose of designing, procuring, constructing, operating, maintaining, repairing and altering the Equipment and Facility.

## Licensing Procedure»

.  Seller grants Purchaser a non-exclusive license to use the Equipment supplied under this Agreement for operating, maintaining and repairing the Facility.  Purchaser shall have no right to the source code; provided, however in the event Seller or Seller’s vendor discontinue maintenance of such Equipment, Seller shall on a best efforts basis attempt to obtain such source code for Purchaser.  The non-exclusive license granted herein to Purchaser may be transferred by Purchaser to Purchaser’s Facility operator, Lender(s), or successor owners of the Facility (for the sole purpose of operating the Facility).

Seller and/or its licensors shall at all times remain owners of the software/firmware licensed.

# TRAINING AND TECHNICAL DIRECTION OF INSTALLATION

Seller shall provide technical direction of installation of the Equipment in accordance with Exhibit H-1.  Seller shall provide on Site operation and maintenance training for Purchaser’s operations and maintenance personnel in accordance with Exhibit H-2.  Purchaser shall be responsible for the travel and per diem costs of its personnel and for providing or procuring all training facilities on or in the immediate vicinity of the Site.

# DEFAULT

## Events of Default by Seller»

.  Seller shall be in default hereunder upon the occurrence of any one of the following events, which shall be events of default (each an “Event of Seller Default”) if not cured within thirty (30) Days following delivery to Seller of a Notice of such event from Purchaser, or, if not curable in such thirty (30) Day period, if Seller has not commenced the cure within such period and does not thereafter diligently pursue such cure, provided that in no event shall such extended cure period exceed one hundred twenty (120) Days and further provided that the event described in paragraph (e) below shall be an Event of Seller Default upon its occurrence without the aforesaid Notice or cure period:

##### Seller shall have assigned or transferred this Agreement or any right or interest herein except as expressly permitted by this Agreement;

##### any representation made by Seller in this Agreement (which shall be true and correct throughout the performance of this Agreement)  shall be materially false or misleading as made, including without limitation the following representations:

###### Seller is not in breach of, in default under, or in violation of, any applicable statute, law, ordinance, decree, rule, or regulation of any governmental authority, or the provisions of  its articles of incorporation or by-laws or any franchise or license, or in breach of, in default under, or in violation of, any provision of any indenture or any evidence of indebtedness or security therefor, lease, contract, license or other agreement by which it is bound if such breach, default or violation may result in a material adverse effect on the business or financial condition of Seller; and the execution and delivery of this Agreement and the performance of its obligations hereunder will not constitute or result in any such breach, default or violation; and

###### no suit, claim, action, arbitration, or legal, administrative or other proceeding is pending or to the best of Seller’s knowledge threatened against Seller that would affect the validity or enforceability of this Agreement, the ability of Seller to fulfill its commitments hereunder in any material respect, or that could result in any material adverse change in the business or financial condition of Seller;

##### Seller shall have defaulted in its performance under any material provision of this Agreement or failed to comply with any covenant herein.  The parties agree that Purchaser may not terminate for default based upon a Unit’s failure to meet Guaranteed Levels if Seller has caused the Unit to meet Specific Performance Levels in accordance with the terms of this Agreement.

##### Purchaser may also terminate this Agreement for default in part as to the applicable Unit in the event of the following, each of which shall constitute an Event of Seller Default:

###### Seller’s liability for Delivery Liquidated Damages with respect to a Unit, as determined in accordance with Section 10.3, amounts to fifteen percent (15%) of the Maximum Liability Amount; or

###### Seller’s liability for Take Over Liquidated Damages with respect to a Unit, as determined in accordance with Section 10.3.2, amounts to fifteen percent (15%) of the Maximum Liability Amount; or,

###### Seller fails to cause a Unit to achieve a Specific Performance Level within one hundred eighty (180) Days after Purchaser conducts the initial Performance Tests or Sound Level Test; or

###### Seller’s liability for Liquidated Damages with respect to a Unit, determined as provided in ARTICLE X, amounts to exceeds thirty percent (30%) of the Maximum Liability Amount.

If the defaulting Unit is to be used in conjunction with other Units at the same Facility, at Purchaser’s sole discretion, the Agreement may be terminated as to those Units as well if (i) the default in relation to the affected Unit impacts Purchaser’s ability to comply with obligations to a third party, (ii) the value of the remaining Units is materially diminished by the defaulting Unit, or (iii) it reasonably appears to Purchaser that Seller will be unable to comply with its  obligations under this Agreement relating to the remaining Units.

##### any proceeding is instituted against Seller seeking to adjudicate Seller as a  bankrupt or insolvent, or Seller makes a general assignment for the benefit of its creditors, or a receiver is appointed on account of the insolvency of Seller, or Seller files a petition seeking to take advantage of any other law relating to bankruptcy, insolvency, reorganization, winding up or composition or readjustment of debts and, in the case of any such proceeding instituted against Seller (but not by Seller), such proceeding is not dismissed within sixty (60) Days of such filing.

## Purchaser’s Remedies Against Seller»

.  The provisions of ARTICLE XXVI hereof notwithstanding, and without limitation of Purchaser’s rights under ARTICLE X for those Liquidated Damages paid or due prior to an Event of Seller Default, if an Event of Seller Default shall have occurred and be continuing, Purchaser or its assignee shall have the right to terminate this Agreement in whole or in part by delivery of a Notice of termination to Seller.  For the avoidance of doubt, the Agreement, may be partially terminated on a Unit basis as a result of an Event of Seller Default in accordance with the provisions of this Agreement.

## General Obligations»

.  If Purchaser elects to terminate this Agreement in whole or in part  pursuant to Section 17.2 hereof, Seller shall, and at Seller’s expense, subject to Section 27.1 hereof,  at Purchaser’s option either:

##### promptly refund all amounts paid to date and pay Cover Damages plus Termination Costs described in Sections 17.4.2(i) and 17.4.2(iv) described below; or

##### perform the following services relative to the Scope of Work so affected;

assist  Purchaser in preparing an inventory of all Equipment and documentation to which Purchaser has not already taken title;

assign to Purchaser, or to any person designated by Purchaser without any right to compensation not otherwise provided for herein, title to all portions of the Equipment and documentation not already owned by Purchaser, together with all subcontracts and other contractual agreements (including warranties) as may be designated by Purchaser, all of which subcontracts and contractual agreements shall be so assignable, and to Purchaser to the extent assignable all issued licenses,  authorizations, approvals and rights to complete and to use the Equipment under patents and other proprietary or intellectual property rights then held by Seller or its Vendors pertaining to the Equipment;

afford to Purchaser all design, expertise and other information as may be  necessary for the operation of the Equipment for which title has passed to Purchaser (subject to the requirements of Section 21.1 hereof); and

supply any proprietary components or procure and supply substituted nonproprietary components need for the completion and operation of the Equipment.

## Payment Obligations.

### Determination of Obligations»

.  If Purchaser terminates this Agreement pursuant to Section 17.2 hereof, and requests delivery of the Equipment and the materials and services described in Section 17.3(b) above, Purchaser shall determine the value of that portion of the Scope of Work, which has been properly completed, if any (the “Proper Scope Value”).  The Proper Scope Value shall not exceed the Maximum Liability Amount on a Unit basis.  If Purchaser has paid Seller an amount greater than the Proper Scope Value, the difference between the amount paid to Seller, considering amounts paid prior to the execution of this Agreement, and the  Proper Scope Value (the “Refund Amount”) shall be settled between the parties in accordance with Section 17.4.4 below.  If the amount paid by Purchaser to Seller is less than the Proper Scope Value, considering amounts paid prior to the execution of this Agreement, the difference between the amount paid and the Proper Scope Value (the “Scope Value Due”) shall be settled between the parties in accordance with Section 17.4.4 below.  If Seller disagrees with Purchaser’s determination of the Proper Scope Value, such dispute shall be resolved in accordance with ARTICLE XXVI.

### Damages and Expenses»

.  Purchaser shall determine the total damages and reasonable and necessary expenses incurred in connection with:

###### the termination of this Agreement or part thereof (including all legal fees and expenses for,  inter alia, the negotiation of an agreement with an alternate supplier);

###### if Section 17.3(b) hereof is applicable, any rework, modifications or replacement of the Equipment to cause it to comply with the requirements of this Agreement;

###### if Section 17.3(b) hereof is applicable, the completion of the Scope of Work and all associated incidental costs, and

###### amounts otherwise due Purchaser from Seller pursuant to this Agreement (including but not limited to Liquidated Damages).

The total of items (i) through (iv) above shall be referred to as the “Termination Costs”.  In the case of Event of Seller Default as set forth in Section 17.1.1(i), (ii) or (iv), Purchaser shall be entitled to such Liquidated Damages plus Termination Costs.

### Cover Damages»

.  If Section 17.3(a) hereof is applicable, the amount of “Cover Damages” shall be the difference between the Maximum Liability Amount under this Agreement (or portion thereof in the case of partial termination) and the purchase price payable by Purchaser for a replacement contract for substantially similar Equipment and Scope of Work under this Agreement, suitable for the Facility and substantially meeting the Specifications set forth in this Agreement, plus incremental transportation costs incurred.  Purchaser agrees that it has a duty to mitigate any damages and that it shall use commercially reasonable efforts to minimize Cover Damages it may incur as a result of procuring a replacement contract in the event of termination hereunder.

### Settlement»

.   Upon determining the Proper Scope Value and the Termination Costs, if any, the termination settlement (the “Termination Settlement”) shall be determined and invoiced as follows:

##### if Section 17.3(a) is applicable, the Termination Settlement shall be the amounts described in Section 17.3(a).

##### if Section 17.3(b) hereof is applicable, the Termination Settlement shall be as follows:

###### if the Scope Value Due is greater than zero (0), and if

the Termination Costs are greater than the Scope Value Due, Seller shall pay Purchaser the difference of the Termination Costs less the Scope Value Due, or

the Scope Value Due is greater than the Termination Cost, Purchaser shall pay Seller the difference of the Scope Value Due less the Termination Costs.

###### if the Refund Amount is greater than zero (0), then Seller shall pay Purchaser the sum of the Refund Amount plus the Termination Costs.

###### if the Refund Amount and the Scope Value Due are each zero (0), Seller shall pay Purchaser the Termination Costs.

Seller or Purchaser, as applicable, shall make payment of an invoice received for Termination Settlement within thirty (30) Days of receipt of such invoice.  Any such Termination Settlement not paid when due shall accrue interest at the Interest Rate.

## Events of Default by Purchaser»

.  Purchaser shall be in default hereunder upon the occurrence of any one of the following events, which shall be events of default (each an “Event of Purchaser Default”) if not cured within thirty (30) Days following delivery to Purchaser of a Notice of such event from Seller or if not curable in such thirty (30) Day period, if Purchaser has not commenced the cure within such period and does not thereafter diligently pursue such cure, provided that in no event shall such extended cure exceed one hundred twenty (120) Days further provided that the event described in paragraph (d) below shall be an Event of Purchaser Default upon its occurrence without the aforesaid Notice or cure period:

##### Purchaser shall have assigned or transferred this Agreement or any right or interest herein except as expressly permitted by this Agreement;

##### any representation made by Purchaser in this Agreement shall have been materially false or misleading when made;

##### Purchaser shall have defaulted in its performance under any material provision of this Agreement; or

##### any proceeding is instituted against Purchaser seeking to adjudicate Purchaser as a bankrupt or insolvent, or Purchaser makes a general assignment for the benefit of its creditors, or a receiver is appointed on account of the insolvency of Purchaser, or Purchaser files a petition seeking to take advantage of any other law relating to bankruptcy, insolvency, winding up or composition or readjustment of debts and in the case of any such proceeding instituted against Purchaser (but not by Purchaser) such proceeding is not dismissed within sixty (60) Days of such filing.

## Seller Remedies»

.  The provisions of ARTICLE XXVI hereof notwithstanding, if an Event of Purchaser Default shall have occurred and be continuing beyond the time allowed in Section 17.5, Seller shall have the right, as its sole and exclusive remedy, to terminate this Agreement by delivery of a Notice of termination to Purchaser and receive as liquidated damages the applicable Cancellation Charge pursuant to Section 5.4 as if the Agreement was cancelled by Purchaser.

# FORCE MAJEURE

## Failure to Perform Due to an Event of Force Majeure»

.  Subject to the terms of this ARTICLE XVIII, either party shall be excused from performance and shall not be considered to be in default with respect to any obligation hereunder, to the extent such party’s (the “Affected Party”) failure of performance is due to an Event of Force Majeure.

## Events of Force Majeure»

.  Events of Force Majeure shall be limited to the circumstances set forth in Section 18.4 (the “Event of Force Majeure”)  but only if, and to the extent:

###### such circumstance is not within the reasonable control of the Affected Party;

###### such circumstance, despite the exercise of reasonable diligence, can not be prevented, avoided or removed by Affected Party;

###### such circumstance prevents the Affected Party from fulfilling its obligations under the Agreement;

###### the Affected Party has taken all reasonable precautions, due care and reasonable alternative measures in order to avoid the effect of such event on the Affected Party’s ability to fulfill its obligations under the Agreement and to mitigate the consequences thereof; and

###### such event is not the result of any failure of the Affected Party to perform any of its obligations under the Agreement.

## Notice of Event of Force Majeure»

.  As soon as possible following the date of commencement of any Event of Force Majeure, if either party desires to invoke such Event of Force Majeure as a cause for delay in the performance of any obligation hereunder or as potential adjustment of the Purchase Amount, it shall promptly (but not later than three (3) Days upon learning of such Event of Force Majeure), advise the other party in writing of such date.  Notices shall be in accordance with Section 25.1.  Within seven (7) Days, the Affected Party shall provide in writing a description of the event and reasonable alternative measures which the Affected Party has taken in order to avoid the effect of such event on such party’s ability to fulfill its obligations under the Agreement and to mitigate the consequences thereof, and the nature and expected duration of such Event of Force Majeure.  The Affected Party shall provide additional information concerning the event as reasonably requested by the other party (including, without limitation, updating of any information already provided under this Section 18.3).  As soon as practicable after the commencement of the Event of Force Majeure, the Affected Party shall allow the other party’s professional advisers access to its premises and equipment to enable the other party to assess the event and the steps to avoid or remove the circumstances constituting the event.  Within a reasonable time following the date of termination of such Event of Force Majeure, the party having invoked such Event of Force Majeure as a cause for such delay or potential adjustment of the Purchase Amount shall submit to the other party as soon as practicable, reasonable proof of the nature of such delay and its effect upon the Guaranteed Unit Delivery Date, or the basis for an adjustment of the Purchase Amount.  The burden of proof to demonstrate that an Event of Force Majeure has occurred and affects the Affected Party’s ability to perform, rests with the Affected Party.  The parties will meet within ten (10) Days after receipt of the Notice by the unaffected party to discuss appropriate measures that should be taken.  The parties shall thereupon consult with one another concerning the effect of such Event of Force Majeure and an extension of the Guaranteed Unit Delivery Date(s) described in Section 10.2.1 or, if applicable, an adjustment in the Purchase Amount described in Section 5.1 shall be made by the parties to take into account such effect on the ability of Purchaser and Seller to reschedule project activities to avoid or minimize overall delays or additional costs resulting from the Event of Force Majeure.  The parties:

###### shall make all reasonable efforts to prevent and reduce to a minimum and mitigate the effect of any delay or potential adjustment of the Purchase Amount occasioned by any Event of Force Majeure including recourse to alternate acceptable source of services, equipment and materials and construction equipment; and

###### shall use their best efforts to ensure resumption of normal performance of this Agreement after the occurrence of any Event of Force Majeure and shall perform their obligations to the maximum extent practicable as agreed between the parties.

## Events of Force Majeure»

.  Subject to the provisions of Section 18.2 and Section 18.5, Events of Force Majeure shall mean the following:

##### explosions, fires, nuclear radiation contamination, hurricanes, earthquakes, floods, natural disasters, epidemics, other acts of God, and any other similar circumstances;

##### war and other hostilities (whether declared or not), revolution, public disorders, insurrection, rebellion, sabotage, acts of public officials or terrorist action;

##### any action or relative material inaction taken by any national or local government or judicial authority after the date of this Agreement, including without limitation any order, legislation, enactment, judgment, ruling or decision; or

##### national or regional strikes (to the extent affecting the Seller’s performance of Scope of Work) and strikes specific to the Site or to Seller’s manufacturing facility.

## Certain Events Not Excused»

.  Notwithstanding that an Event of Force Majeure may otherwise exist, the provisions of this  ARTICLE XVIII shall not excuse:

##### late delivery of equipment or materials caused by Seller, or caused by any of the subcontractors of Seller if Seller could have avoided such late delivery by exercising all reasonable endeavors as a prudent equipment supplier;

##### late performance by Seller caused by Seller’s failure to engage qualified subcontractors and suppliers or to hire an adequate number of personnel or labor or by inefficiencies on the part of Seller; or

##### delays resulting from reasonably foreseeable unfavorable weather or reasonably foreseeable unsuitable ground conditions.

## Continued Performance»

.  Upon the occurrence of any Event of Force Majeure, the parties shall endeavor to continue to perform their obligations under the Agreement so far as reasonably practicable and Seller shall during the period of such circumstances protect and secure the works in such manner as Purchaser shall require.  Seller shall notify Purchaser of the steps it proposes to take including any reasonable alternative means for performance of the works not prevented by the Event of Force Majeure.

## Not Used.

## Event of Force Majeure - Delays»

.  If either party becomes unable to perform all or part of its obligations under the Agreement because of an Event of Force Majeure, and the Affected Party has properly invoked and observed the provisions of Section 18.3 in respect thereof, the Affected Party shall be permitted a delay in the performance of its obligations affected by the Event of Force Majeure and, to the extent affected, an extension of the Guaranteed Unit Delivery Date(s).

## Event of Force Majeure - Cost»

.  Seller shall bear its own delay costs occasioned by any Event of Force Majeure for the first thirty (30) Day period during the occurrence or continuance of each such Event of Force Majeure.  If an Event of Force Majeure continues beyond such thirty (30) Day period in which Seller is the Affected Party, provided Seller has properly invoked and observed the provisions of Section 18.3 in respect thereof, Seller shall be entitled, subject to the provisions of Section 11.3, to recover costs occasioned by each such Event of Force Majeure which accrue after each such thirty (30) Day period pursuant to a Purchase Amount adjustment in accordance with Section 5.5 and ARTICLE XI hereof. Notwithstanding the foregoing, Seller shall not be entitled to an increase in cost due to strikes specific to its manufacturing facilities.

# INSURANCE

## Insurance - General»

.  Seller shall procure insurance at its own expense and maintain in full force and effect at all times throughout Seller’s performance under this Agreement (to include Seller’s performance of its warranty obligations) with responsible insurance carriers as set forth in this Agreement.  Seller may establish programs of self insurance to the same minimum levels as set forth below, as allowed by law.

### All Risk»

.  Seller shall purchase and maintain insurance to the full replacement cost of the Equipment during the process of fabrication and in the factory until the Equipment is loaded on Purchaser’s transport, or, if the Purchaser elects deliver at an Optional Delivery Point, until delivery at the Optional Delivery Point, for physical loss and damage including but not limited to theft, vandalism, and malicious mischief, collapse, water damage and such other perils as Seller deems appropriate.  Seller may self insure work during the fabrication process.

### Workers Compensation and Employers Liability Insurance»

.  Seller agrees to comply with workers compensation laws of each jurisdiction where the Scope of Work is performed, and to maintain a Workers Compensation and Employers Liability policy.   This policy shall be endorsed, if applicable, to provide all state coverage, alternate employer, voluntary compensation coverage and occupational disease with the limits set forth below. If the work is to be performed  on or near navigable U.S. waters, the policy shall include coverage for United State Longshoreman’s and Harbor Worker’s Act, Death on the High Seas Act, Jones Act, or their equivalent as required by the applicable laws in the jurisdiction where such work is performed.

Workers Compensation	Statutory

Employers Liability		$1,000,000 Each Accident

$1,000,000 Disease

Each Employee (Minimum)

### Commercial General Liability Insurance»

.  Seller shall maintain Commercial General Liability Insurance, endorsed to provide coverage for: Explosion, Collapse and Underground Hazards; Contractual Liability (particularly applicable to the provisions of the “General Indemnity” section of this Agreement);  and Products and Completed Operations (for a minimum of one year after completion of the Scope of Work) with the following limits:

Bodily Injury and	$1,000,000 Combined Single Limit

Property Damage	Each Occurrence, (Minimum)

### Hull and Protection and Indemnity Insurance»

.  Seller shall ensure that if any owned or non-owned watercraft of any kind is used for performance of the Scope of Work, Hull and Protection and Indemnity Insurance shall be provided for the vessels in the amounts as follows:

Hull	Full replacement value of the watercraft

P&I	$1,000,000 Each Occurrence or the full value of the vessel, whichever is greater

Such insurance may be provided by the vessel operator, by the vessel charter agreement, or by Seller as Seller deems appropriate.

### Business Automobile Liability Insurance»

.  Seller shall provide Business Automobile Liability Insurance which shall include the following coverage for all owned, non-owned and hired vehicles:

Bodily Injury   	$1,000,000 Each Person  (Minimum)

$1,000,000 Each Occurrence (Minimum)

Property Damage 	$1,000,000 Each Occurrence (Minimum)

or

Bodily Injury and 	$1,000,000 Combined Single Limit

Property Damage 	Each Occurrence (Minimum)

### Aircraft Liability Insurance»

.  If the Scope of Work necessitates the use of Seller’s or Seller’s affiliate’s owned or leased aircraft, Seller shall provide Aircraft Liability Insurance which shall be endorsed to provide coverage for non-owned as well as Guest Voluntary Settlement, with limits of:

Bodily Injury and	$10,000,000 Combined Single Limit

Property Damage	Each Occurrence

Such insurance may be provided by the aircraft operator, by the aircraft charter agreement, or by Seller as Seller deems appropriate.

### Excess Umbrella Liability Coverage»

.  Seller shall provide Excess Umbrella Liability coverage with minimum limits of:

Bodily Injury and	$5,000,000 Combined Single Limit

Property Damage 	Each Occurrence

### Vendors»

.  Seller shall require its Vendors and others connected with the Scope of Work  to provide and maintain insurance at all times during the period that their agreement related to the Scope of Work under this Agreement is in force and effect at the Vendor’s, or other’s own cost, with insurance limits which at minimum meets levels as required for similar contracts and is customary for the applicable industry.

### Certificate of Insurance»

.  Within twenty (20) Days of execution of this Agreement, Seller shall submit to Purchaser a Certificate of Insurance, in form satisfactory to Purchaser, evidencing that satisfactory coverage of the type and limits set forth hereinabove are in effect.  Policies providing such coverage shall contain provisions that no cancellation or material changes in the policies shall become effective except on sixty (60) Days advance written Notice thereof to Purchaser.  Irrespective of the requirements as to insurance to be carried as provided for herein, the insolvency, bankruptcy or failure of any insurance company carrying insurance of Seller, the failure of any insurance company to pay claims accruing, shall not affect, negate or waive any of the provisions of this Agreement including, without exception, the indemnity obligations of Seller.

### Other Requirements»

.  Seller shall be responsible for the payment of all deductible and self insurance retention amounts with respect to the insurance required to be maintained by it pursuant hereto.  All Seller insurance shall:

##### Specify Purchaser and Lender, and such other parties as Purchaser may require as additional insured for all insurance coverage other than Worker’s Compensation Insurance, or its equivalent as required in jurisdictions other than the United States;

##### Provide that Purchaser shall have the right, but not any obligation, to pay any premiums if Seller shall fail to do so, and such payment of premiums by Purchaser shall be at Seller’s expense, either by direct charge or setoff;

##### For all insurance coverage related to Scope of Work, (i) endorse policies to apply as primary insurance without right of contribution from any similar coverage which may be maintained by the Purchaser Related Parties; (ii) waive any right of subrogation against the Purchaser Related Parties and all other named and additional insured and any other right of the insurer to any setoff or counterclaim or any other deduction, whether by attachment or otherwise, in respect of any liability of Purchaser Related Parties, or any other named or additional insured; and

##### For all other insurance other than as stated in (c) immediately above, waive any right of subrogation against Purchaser, Lender and all other named and additional insured and any other right of the insurer to any setoff or counterclaim or any other deduction, whether by attachment or otherwise, in respect of Purchaser, or any other named or additional insured.

### Vendor Waiver of Subrogation»

.  Seller agrees to require all policies of insurance which are in any way related to the Scope of Work and that are secured and maintained by Seller’s Major Component Vendors to include clauses providing that each underwriter shall waive its rights of recovery, under subrogation or otherwise, against Purchaser, and Lender, and their parent and affiliated companies and their directors, officers, employees and agents (the “Purchaser Related Parties”) or alternatively shall indemnify and defend Purchaser Related Parties against such action if such action arises out of or is in any way related to this Agreement.

### Compliance with Insurance»

.  Seller and its directors, officer, representatives, agents and employees shall comply with all the terms of the policies of insurance referred to in Section 19.2 and to the extent Seller is made aware of such terms, in any Delay in Start-Up and Business Interruption Insurance obtained by Purchaser.  Seller and its directors, officers, representatives, agents and employees shall comply with the procedures for claims, notification and administration under the aforesaid insurance policies and shall not do or omit to do anything which might  void policies of insurance or entitle insurers to avoid liabilities thereunder.  Seller shall ensure that all Major Component Vendors shall be subject to provisions identical to this Section 19.1.12.

### Limitation»

. In the event that Seller breaches its obligations under the first two sentences of Section 19.1.12 of the Agreement and such breach results in an insurer avoiding, in relation to Seller, any policy of insurance obtained by Purchaser pursuant to Section 19.2 of the Agreement, Seller shall not be regarded as an additional insured under such policy and any waiver of subrogation in favor of Seller included in that policy pursuant to Section 19.2 shall not apply.

In the event that any Vendor fails to comply with the procedures for claims notification and administration under any policy of insurance obtained by Purchaser pursuant to Section 19.2 of the Agreement or does anything which might render any such policy of insurance void or entitle insurers to avoid liability thereunder and as a result thereof an insurer avoids in relation to that Vendor any such policy of insurance, that Vendor shall not be regarded as an additional insured under such policy and any waiver of subrogation in favor of that Vendor included in that policy pursuant to Section 19.2 of the Agreement shall not apply.

## Purchaser’s Insurance.

### Cargo Insurance»

.  Purchaser shall provide or cause to be provided and maintained All Risk Marine Cargo Insurance for the period of transportation commencing upon transportation from factory where final assembly occurs prior to commencing delivery to Purchaser and ending upon delivery to the Site, unless Purchaser elects to have the Seller provide transportation services to the Optional Delivery Point, in which case Seller provides Marine Cargo Insurance as provided herein.  The maximum per occurrence deductible, shall be no more than $25,000.  Purchaser shall cause Seller to be an additional insured and provided a waiver of subrogation under such policy.

### Builder’s All Risk Insurance»

.  Purchaser shall provide or cause to be provided and maintained Builder’s All Risk Insurance policy covering activities at the Site for the period of time that Seller performs TD of I Services at the Site.  Seller, to the extent of its TD of I Services on the Site, shall be named as an additional insured and provided a waiver of subrogation under such policy.  Such additional insured status and waiver shall not apply to any loss arising out of Seller’s warranty obligations as described in ARTICLE XIV hereof.

Seller shall have an opportunity to review and make reasonable comments to the Purchaser’s proposed insurance policies in respect to the Cargo insurance and Builder’s All Risk insurance.  Upon request, Purchaser shall provide Seller one copy of the relevant portions of such final insurance policies as such policies become available.

# INDEMNIFICATION

## Third Party»

.  With respect to claims brought by third parties against either Seller or Purchaser relating to the property or facilities with respect to which this Agreement pertains or the Scope of Work performed under this Agreement, Seller and Purchaser agree as follows:

##### Seller agrees to indemnify, protect, defend, and hold harmless Purchaser its directors, Lenders, officers, employees, agents, and contractors, and the directors, officers employees, agents, and contractors of Purchaser’s parent and affiliated companies (collectively “Purchaser Indemnitees”), from and against any and all demands, claims, suits and causes of action and any and all liability, costs, expenses, and judgments incurred in connection therewith, including, without limitation, court costs and reasonable attorney’s fees (a “Claim”), whether arising in equity, at common law, or by statute, or under the law of contracts, torts (including, without limitation, negligence and strict liability without regard to fault) for personal injury or damage to property of third parties (excluding Purchaser Indemnitees) or arising in favor of or brought by any of Seller’s employees, agents, subcontractors, or representatives, or by any governmental agency or any other third party (the “Purchaser Claimant”), based upon, in connection with, relating to or arising out of or alleged to arise out of Seller’s, its agents’ affiliates’, subcontractors’ or vendors’ negligence, and even if due in whole or in part to Purchaser’s concurrent negligence or fault or other fault, breach of contract or warranty, or strict liability without regard to fault; provided, however, that Seller’s contractual obligation of indemnification shall extend only to the percentage of the Claim caused by Seller, it directors, officers, employees, agents and contractors and the directors, officers, employees, agents, and contractors of Seller’s parent and affiliated companies, and shall not extend to the percentage of the Purchaser Claimant’s Claim attributable to Purchaser’s negligence or other fault, breach of contract or warranty, or to strict liability imposed upon Purchaser as a matter of law.  This indemnification obligation shall apply regardless of the amount of insurance coverage held by Seller, including that under any worker’s compensation act, disability act, or other act or law which would limit the amount or type of damages, compensation, or benefits payable by or for Seller, and shall not be limited by any insurance carried or provided by Seller in accordance with this Agreement or otherwise.

##### Purchaser agrees to indemnify, protect, defend, and hold harmless Seller its directors,  officers, employees, agents, and contractors, and the directors, officers, employees, agents, and contractors of Seller’s parent and affiliated companies (collectively “Seller’s Indemnitees”) from and against any and all demands, claims, suits and causes of action and all liability, costs, expenses, and judgments incurred in connection therewith (including, without limitation, costs and reasonable attorney’s fees), whether arising in equity, at common law, or by statute, or under the law of contracts, torts (including, without limitation, negligence and strict liability without regard to fault) for personal injury or damage to property of third parties (excluding Seller’s Indemnitees) or arising in favor of or brought by any of Purchaser’s employees, agents, subcontractors, or representatives, or by any governmental agency or any other third party (the “Seller Claimant”), based upon, in connection with, relating to or arising out of or alleged to arise out of Purchaser’s, its agents’ affiliates’, subcontractors’ or vendors’ negligence, and even if due in whole or in part to Seller’s concurrent negligence or fault or other fault, breach of contract or warranty, or strict liability without regard to fault, breach of contract or warranty, or strict liability without regard to fault; provided, however, that Purchaser’s contractual obligation of indemnification shall extend only to the percentage of the Claim caused by Purchaser, it directors, officers, employees, agents and contractors and the directors, officers, employees, agents, and contractors of Purchaser’s parent and affiliated companies, and shall not extend to the percentage of the Seller Claimant’s Claim attributable to Seller’s negligence or other fault, breach of contract or warranty, or to strict liability imposed upon Seller as a matter of law.  This indemnification obligation shall apply regardless of the amount of insurance coverage held by Purchaser, including that under any worker’s compensation act, disability act, or other act or law which would limit the amount or type of damages, compensation, benefits payable by or for Purchaser in accordance with this Agreement or otherwise.

##### In the event that both Seller, its agents, affiliates, subcontractors or vendors, and Purchaser are adjudicated negligent or otherwise at fault or strictly liable without fault with respect to damage or injuries sustained by the Seller Claimant or Purchaser Claimant, this contractual obligation of indemnification shall continue but each of Seller and Purchaser shall indemnify the other only for the percentage of responsibility of the damage or injuries adjudicated to be attributed to the indemnitor.

##### It is a condition precedent to the indemnitor’s contractual obligation of indemnification under this Agreement that the party seeking indemnity shall provide written notice of the third party claim, demand or cause of action promptly after such third party claim, demand or cause of action is received by the party seeking indemnity.  Notice shall be served on the earlier of:

###### fifteen (15) business days prior to the last day for responding to such claim or, action; or

###### the date which is one-half of the period allowed for responding to such claim or action.

It is further a condition precedent to the indemnitor’s contractual obligation of indemnification under this Agreement that the indemnitor shall thereafter have the right to participate in the investigation, defense and resolution of such third party claim.

## Survival of Obligation»

.  The duty to indemnify under this Article XX will continue in full force and effect notwithstanding the expiration or termination of this Agreement.

# NON-DISCLOSURE OF INFORMATION

## Proprietary Information»

.  Without prejudice to Sections 21.1, 21.3 and 21.4, any information concerning the parties which is designated in writing as proprietary and/or confidential and disclosed to the other party incident to the performance of the Scope of Work pursuant to this Agreement in confidence shall not be published or otherwise disclosed to others without the written approval of the disclosing party, provided, however, that nothing herein shall limit either party’s rights to disclose data which:

##### was developed on its own or furnished to it prior to this Agreement without restriction;

##### becomes generally available to the public through no fault of either party; or

##### is received by either party from a third party without restriction and not in breach of this Agreement or without fault or wrongdoing of the recipient.

Proprietary and/or confidential information disclosed hereunder shall only be used by the transferee in the performance of its obligations hereunder or as expressly permitted under this Agreement.  Each party shall take such actions to protect proprietary and/or confidential information disclosed by the other party as are consistent with its practices to protect its own proprietary and/or confidential information.

Furthermore Purchaser or Seller may upon written Notice in advance to the other party  provide any such information to any governmental authority having jurisdiction and asserting a right to obtain such information, but only to the extent required to do so by law. This clause shall survive the termination of this Agreement.

## Press Releases»

.  Seller and Purchaser agree that it is in both parties’ interest to limit information of strategic value disseminated to the independent power industry regarding this Facility.  To the extent that a party desires to issue press releases, advertisements in the trade press, tombstones in the financial or trade press then that party must obtain the other party’s written release to do so.

## Confidentiality of Seller»

.  Seller acknowledges that Purchaser’s business is highly competitive and that Purchaser’s books, records, documents and technical information concerning its products, equipment, services, processes, procurement procedures, pricing techniques, the names of and other information (such as credit and financial data) concerning Purchaser’s customers and business affiliates, all comprise confidential business information and trade secrets of Purchaser which are valuable, special and unique proprietary assets.  Seller further acknowledges that protection of Purchaser’s confidential business information and trade secrets against unauthorized disclosure and use is of critical importance to Purchaser in maintaining its competitive position.  Accordingly, Seller hereby agrees that it will not, at any time during or after the term of this Agreement, make any unauthorized disclosure of any confidential business information or trade secrets of Purchaser or make any use thereof, except for the benefit of, and on behalf of Purchaser.  However, Seller’s obligation under this Section 21.3 shall not extend to information which is or becomes part of the public domain or is available to the public by publication or otherwise through no wrongful act or omission or noncompliance with this Section by Seller or its agents.  The provisions of this Section 21.3 shall survive the termination of this Agreement.  Seller agrees and acknowledges that money damages would not be sufficient to remedy  for any breach of this Section 21.3 by Seller, and Purchaser shall be entitled to specific performance and injunctive relief as remedies for such breach or any threatened breach.  Such remedies shall not be deemed the exclusive remedies for a breach of this Section 21.3 by Seller but shall be in addition to all remedies available at law or in equity to Purchaser including recovery of damages from Seller.  For the purposes of this paragraph, the term “Purchaser” shall also include Affiliates of Purchaser.

Seller shall deliver to Purchaser all Purchaser confidential information provided or disclosed to or used or acquired by Seller, including all information developed, derived, or created therefrom, or portions thereof, upon the earlier of:

###### the ending of the need for the information for performance of the Scope of Work;

###### Purchaser’s request;

###### the completion of the Scope of Work for which it was provided, disclosed used or acquired; or

###### cancellation, termination or suspension of this Agreement.

Seller may retain a single copy of all information upon which its Scope of Work is based for record purposes only.  In the event Seller, with Purchaser’s consent, releases Purchaser’s confidential information to a third party, Seller shall require such third party to enter into a confidentiality agreement similar to this Section 21.3 with Seller, and Seller shall retrieve all such released confidential information, including any and all copies of the confidential information and all information developed, derived, or created therefrom, upon the earlier of the events set forth above in this Section.

No documents, data, materials or information available to Seller as set forth in this Section 21.3 or produced in whole or in part under this Agreement shall be the subject of an application for copyright by or on behalf of Seller without the prior written consent of Purchaser.

Either party shall be entitled to disclose the terms and conditions of this Agreement and any data or information acquired by it under or pursuant to this Agreement without the prior consent of the other party:

##### to any Affiliate of such party;

##### to any outside consultants or advisers engaged by or on behalf of such party in connection with the Scope of Work or the financing or operation of the Facility and acting in that capacity;

##### to any operator of the Facility, permitted assignees and Lenders;

##### to the extent required by the rules of a relevant and recognized stock exchange;

##### to the extent required by law or pursuant to an order of any court of competent jurisdiction, provided that the original disclosing party is given Notice and adequate time to seek a protective order applicable to the information before it is disclosed;

##### to any insurer under a policy of insurance required to be taken out by either party under the Agreement; or

##### to directors, employees and officers of such party;

##### provided that:

##### the disclosing party determines in good faith that the recipient has a legitimate need to see such data or information; and

##### the recipient has been made aware of and has agreed to be bound by the requirements of this ARTICLE XXI.

## Confidentiality of Purchaser»

.  Purchaser acknowledges that Seller’s business is highly competitive and that Seller’s books, records, documents and technical information concerning its products, equipment, services, processes, procurement procedures, pricing techniques, the names of and other information (such as credit and financial data) concerning Seller’s customers and business affiliates, all comprise confidential business information and trade secrets of Seller which are valuable, special and unique proprietary assets.  Purchaser further acknowledges that protection of Seller’s confidential business information and trade secrets against unauthorized disclosure and use is of critical importance to Seller in maintaining its competitive position.  Accordingly, Purchaser hereby agrees that it will not, at any time during or after the term of this Agreement, make any unauthorized disclosure of any confidential business information or trade secrets of Seller or make any use thereof, except for the benefit of, and on behalf of Seller.  However, Purchaser’s obligation under this Section 21.4 shall not extend to information which is or becomes part of the public domain or is available to the public by publication or otherwise through no wrongful act or omission or noncompliance with this Section by Purchaser or its agents.  The provisions of this Section 21.4 shall survive the termination of this Agreement.  Purchaser agrees and acknowledges that money damages would not be sufficient to remedy  for any breach of this Section 21.4 by Purchaser, and Seller shall be entitled to specific performance and injunctive relief as remedies for such breach or any threatened breach.  Such remedies shall not be deemed the exclusive remedies for a breach of this Section 21.4 by Purchaser but shall be in addition to all remedies available at law or in equity to Seller including recovery of damages from Seller.  For the purposes of this paragraph, the term “Seller” shall also include Affiliates of Seller.

Purchaser shall deliver to Seller all Seller confidential information provided or disclosed to or used or acquired by Purchaser, including all information developed, derived, or created therefrom, or portions thereof, upon the earlier of:

###### the ending of the need for the information relating to the Scope of Work;

###### Seller’s request;

###### the completion of the Scope of Work for which it was provided, disclosed used or acquired; or

###### cancellation, termination or suspension of this Agreement.

Purchaser may retain a single copy of all information upon which its Scope of Work is based for record purposes only.  In the event Purchaser, with Seller’s consent, releases Seller’s confidential information to a third party, Purchaser shall require such third party to enter into a confidentiality agreement similar to this Section 21.4 with Purchaser, and Purchaser shall retrieve all such released confidential information, including any and all copies of the confidential information and all information developed, derived, or created therefrom, upon the earlier of the events set forth above in this Section.

No documents, data, materials or information available to Purchaser as set forth in this Section 21.4 or produced in whole or in part under this Agreement shall be the subject of an application for copyright by or on behalf of Purchaser without the prior written consent of Seller.

# ASSIGNMENT

## Assignment by Seller»

.  This Agreement may be assigned by Seller without Purchaser’s consent to a wholly owned subsidiary of Seller’s ultimate parent company subject to Section 3.7.  This Agreement may not be assigned by Seller to any other entity without the prior written consent of Purchaser, which shall not be unreasonably withheld.  Any assignment by Seller other than as permitted herein shall be void and without force or effect.

## Assignment by Purchaser»

.  This Agreement or any right or obligation contained herein may be assigned, from time to time, by Purchaser without Seller’s consent to the following:

###### an Affiliate of Purchaser;

###### a joint venture, partnership, limited liability company, or other similar entity in which Purchaser or any of its  Affiliates is a venturer, partner or participant with no less than a nineteen and one-half percent (19.5%) equity interest;

###### any Lender or financial institution providing financing to Purchaser, its Affiliates or any permitted assignee in connection with the Equipment or the Facility;

###### any party which is obligated or may be obligated to indemnify Seller from any claims or liabilities arising in connection with this Agreement;

###### any party (1) for which Purchaser or any of its Affiliates has agreed to construct or develop a Facility using the Equipment or (2) to which Purchaser or any of its Affiliates has agreed to convey a power plant project which it has under development; or

###### any contractor or developer which is retained by Purchaser or any of its Affiliates to construct or develop a Facility using the Equipment.

Except for (i) through (vi) above, this Agreement or any rights and/or obligations hereunder may not be assigned by Purchaser to other parties without the prior written consent of Seller which shall not be unreasonably withheld, conditioned or delayed.  Seller agrees to respond to any request for consent within thirty (30) Days following its receipt of such request.  Any failure to respond within the foregoing time period shall be deemed to be a grant by Seller of its consent to the proposed assignment. In the event of assignment to a party as described in (v) or (vi) above, Purchaser will receive a guaranty in a form substantially similar to that attached as Exhibit C-1. The guaranty shall be from a company with a credit rating of BBB+ or better.

In determining whether Purchaser shall be permitted to assign this Agreement, Seller shall only be deemed to be reasonable in withholding its consent if the proposed assignee: (i) does not have substantially the same or better credit quality than Purchaser unless (a) the proposed assignee provides appropriate guaranties, letters of credit or other assurances of payment issued by an entity or person with substantially the same or better credit quality than Purchaser or (b) the assignor agrees to remain liable for all future liability under this Agreement, (ii) is a direct competitor of Seller in the turbine manufacturing business, (iii) is an adverse party to Seller in any material litigation or (iv) if purchasing any Equipment (or its rights thereto), is not purchasing such Equipment (or rights thereto) as part of a transaction in which (x) Purchaser or any of its Affiliates is providing related goods and/or services to such assignee, and (y) Purchaser is not merely acting as a broker or market maker with respect to such Equipment (or rights thereto).  Purchaser shall have the right to assign or pledge, from time to time, all or any portion of its right, title and interest in, to and under the Agreement as collateral for financing of the Facility without Seller’s consent.

When duly assigned in accordance with this Section 22.2 (including, following any collateral assignment, upon foreclosure by any collateral assignee), (i) this Agreement or the rights and/or obligations so assigned shall be binding upon and shall inure to the benefit of the assignee (and all rights and/or obligations so assigned, including, without limitation, any and all warranty rights, shall be assigned to the assignee as if such assignee were an original party hereto), (ii) the assignor shall be irrevocably relieved of and forever discharged from all liability under this Agreement so long as the assignee executes an assumption of such liabilities, and (iii) the Seller shall look only to such assignee for the performance of the obligations so assigned.  Any assignment by Purchaser other than as permitted herein shall be void and without force or effect.

The parties hereto further agree and acknowledge that the foregoing provisions relating to this assignment will only control the assignment of Purchaser’s rights under this Agreement prior to the date upon which the Equipment achieves Takeover.  Following such date, Purchaser shall be permitted, without Seller’s consent, to: (i) assign its rights under this Agreement, (ii) convey any ownership interest that it may have in the Facility and/or (iii) convey any equity interest that it may have in the entity which owns the Facility.

# RELATIONSHIP OF THE PARTIES

## Independent Contractor»

.  Seller undertakes performance of this Agreement as an independent contractor.  Nothing herein shall create a relationship of employer and employee, joint venture, or partnership between Purchaser and Seller, its agents, representatives, employees, Affiliates, Vendors or subcontractors, for any purpose whatsoever.  Nothing herein shall create a relationship of principal and agent between Purchaser and Seller, its agents, employees, representatives or subcontractors.  Neither party shall have the authority to bind or obligate the other in any manner as a result of the relationship created hereby.  Purchaser shall not have the right to control the manner(s) or prescribe the method(s) by which Seller performs this Agreement.  Seller shall be wholly responsible for supervision and the methods of performance.  Seller is entirely and solely responsible for its acts and the acts of its agents, employees, representatives, Affiliates, and Vendors engaged in the performance of this Agreement.  Seller shall provide qualified personnel who shall be and remain solely the employees of Seller, and at no time or in any manner shall said personnel be considered as or deemed to be employees of Purchaser.  Purchaser’s general coordinative efforts, suggestions and procedures with respect to the Scope of Work and Purchaser’s right of inspection, review and observation of the performance of this Agreement shall not make Seller or its employees, employees of Purchaser.

## Responsibilities of Seller as Principal for its Employees»

.  Seller has complete and sole responsibility as a principal for its agents, Vendors and all other hires to perform or assist in performing the Scope of Work.

## Not Used.

# LIENS AND CLAIMS

Seller shall not directly or indirectly create, incur, assume or suffer to be created by it or any Vendors, employees, laborers, materialmen or other suppliers of goods or services any claim, lien, security interest, charge or other encumbrance on the Equipment or any part thereof or interest therein and Seller shall immediately notify Purchaser of the assertion of any lien, claim, security interest or other encumbrance against the Equipment or any part thereof.  Seller shall remove immediately any lien, claim, security interest or other encumbrances against Purchaser, Purchaser’s property, or Purchaser’s Affiliates’ property, or the Equipment arising in favor of Seller or its Vendors or other persons or entities by reason of having provided labor, materials or equipment related to performance of this Agreement and to pay any damages, costs, losses and expenses (including, without limitation, court costs and attorneys’ fees) of whatever kind which Purchaser may incur, be required to pay or be liable for as a result of, in connection with, arising out of, or related to any such lien, claim, security interest or other encumbrance.  In the event of a lien from a Vendor, supplier or subcontractor is levied, Seller shall immediately post a letter of credit, in form and substance acceptable to Purchaser, against such lien.  Upon the failure of Seller promptly to pay or discharge any lien claim, security interest or other encumbrance as required hereby within twenty (20) Days of Notice of the existence thereof from any source, Purchaser may, but shall not be obligated to, pay or discharge such lien claim, security interest or other encumbrance and, upon the payment or discharge thereof, shall be entitled to recover from Seller the amount thereof together with all expenses incurred by Purchaser in connection with such payment or discharge.

# NOTICES AND COMMUNICATIONS

## Notices»

.  Any Notice pursuant to the terms and conditions of this Agreement shall be in writing and either:

##### delivered personally;

##### sent by certified mail, (return receipt requested);

##### sent by a recognized overnight mail or courier service with delivery receipt required; or

##### sent by confirmed facsimile transfer.

| Such Notices shall be sent: If to Seller: | GE Packaged Power, Inc. 2707 North Loop West Houston, Texas 77008 Attn: Lee Johnson Fax: 713-803-0390 |
| --- | --- |
| cc: | Daniel Rowley, Esq. Fax: 713-803-0368 |
| cc: | Michael Storm 16415 Jacinto Port Blvd. Houston, Texas 77015 Fax: 281-864-2116 |
| If to Purchaser: | E-Next Generation, L.L.C. 1400 Smith Street Houston, Texas 77002 Attention: Ben Jacoby Fax: (773) |

Either party may change its address or the person to be notified by a Notice delivered in accordance with this section.

## Effectiveness of Notices»

.  Notices shall be effective when received  at the address or facsimile number specified.

## Technical Communications»

.  Notwithstanding communications and Notices addresses as set forth in Section 25.1, the parties will route routine and technical communications as follows:

| If to Seller: | GE Packaged Power, Inc. 2707 North Loop West Houston, Texas 77008 Attn: Lee Johnson Fax: 713-803-0390 |
| --- | --- |
| cc: | Michael Storm 16415 Jacinto Port Blvd. Houston, Texas 77015 Fax: 281-864-2116 |
| If to Purchaser: | E-Next Generation, L.L.C. 1400 Smith Street Houston, Texas 77002 Attention: Ben Jacoby Fax: (773) |

# ARBITRATION

## Negotiation of Disputes and Disagreements»

.  In the event of any dispute or disagreement arising out of or relating to the implementation or performance of this Agreement, which the parties hereto have been unable to settle or agree upon within a period of thirty (30) Days after the dispute or disagreement arises, each party shall nominate a senior officer of its management to meet at a mutually agreed time and place not later than forty-five (45) Days after the dispute or disagreement has arisen to attempt to resolve such dispute or disagreement.  Should a resolution of such dispute or disagreement not be obtained within fifteen (15) Days after the meeting of senior officers for such purpose, or if such meeting does not take place within sixty (60) Days after the dispute or disagreement has arisen, either party may then by Notice to the other submit the dispute to arbitration in accordance with the provisions of Section 26.2.

## Arbitration Resolution»

.  With respect to arbitration resolution, the parties agree that:

##### In the event of dispute between Purchaser and Seller concerning the interpretation of any provision of this Agreement or the performance of any of the terms of this Agreement such matter or matters in dispute shall be finally settled under the arbitration rules of the American Arbitration Association by three arbitrators, one appointed by each party, and the third, who shall be the chairman, will be selected by the two appointed arbitrators, and failing agreement, by the chairman of the American Arbitration Association.  The language of the arbitration shall be English and the place of the arbitration shall be New York, New York;

##### The decision of the arbitrators shall be final and binding upon the parties;

##### If any dispute to be referred to arbitration under this Agreement raises issues which are, as mutually agreed, substantially the same as or connected with issues raised in any other dispute between the parties (and their successor in title and assigns), then such latter dispute shall constitute a “Related Dispute”;

##### If a Related Dispute has already been referred to arbitration in accordance with arbitration provisions identical (mutatis mutandis) to this clause:

or, if the dispute under this agreement has already been referred to arbitration under this clause, then:

###### the dispute under this Agreement shall be referred to the arbitrators appointed to determine the Related Dispute; and

###### the arbitrators shall have power to join one or more defendants or third parties or consolidate actions as provided by Applicable Law.

## Continuation of Work»

.  Pending final resolution of any dispute, Purchaser and Seller shall continue to fulfill their respective obligations hereunder.

## Not Used.

## Not Used.

# LIMITATION OF LIABILITY

## Maximum Liability»

.  Seller’s maximum aggregate liability for claims by Purchaser arising out of Seller’s performance of this Agreement whether arising from tort (including negligence), breach of contract or any other cause of action, including Liquidated Damages, shall be one hundred percent (100%) of the Maximum Liability Amount; provided, however, that this limitation on liability shall not include any liability for or apply to any of the following categories of liability of Seller:

###### under Section 20.1 (Indemnification);

###### under ARTICLE XXIV (Liens and Claims);

###### under Section 15.2.2 (Intellectual Property Claims); and

###### resulting from the gross negligence or willful misconduct of Seller, its agents, employees or Vendors;

which liabilities shall not be limited.  All liability of Seller with respect to any Unit shall terminate six (6) years after delivery of the Unit to the Delivery Point as determined pursuant to Section 10.2, and all liability of Seller under this Agreement shall terminate six (6) years after the last Unit is made available at the Delivery Point as determined in accordance with Section 10.2.

## Consequential Losses»

.  Except for Liquidated Damages and cancellation fees specifically provided for herein, in no event, whether as a result of breach of contract, breach of warranty, tort liability (including negligence or strict liability), strict liability, or otherwise, and whether arising before or after completion of the Scope of Work, shall either party be liable to the other party for special, indirect, exemplary or consequential losses of any nature whatsoever, including losses or damages caused by reason of unavailability of the Equipment, shutdowns or service interruptions, loss of use, loss of profits or revenue, inventory or use charges, cost of purchased or replacement power, interest charges or cost of capital or claims of a party’s customers.

## Releases Valid in All Events»

.  Except as otherwise specifically set forth herein, releases, disclaimers and limitations on liability expressed herein shall apply even in the event of the negligence, strict liability, fault or breach of contract (including other legal bases of responsibility such as fundamental breach) of the party whose liability is released, disclaimed or limited.

## Seller’s Advice or Assistance»

.  If Seller furnishes Purchaser with advice or assistance which is not related to the Equipment nor required  by this Agreement, the furnishing of such advice or assistance will not subject Seller to any liability whether in contract, warranty, tort (including negligence), strict liability, indemnity or otherwise.

# DRUG AND ALCOHOL-FREE WORKPLACE

The parties desire to provide a safe and productive work environment.  The parties believe that the use, possession and/or distribution of illegal/unauthorized drugs and alcohol presents a serious threat to the safety of employees, visitors and others at the job site, or other premises owned, leased, or occupied by Purchaser.  All Seller’s and Seller’s Vendors’ employees associated with the Scope of Work under this Agreement must agree to compliance with Purchaser’s drug and alcohol policy Number 1200-2, dated September 11, 1995 including:

while on or entering the Site or other premises owned, leased, or occupied by Purchaser, search of personal and professional possessions, including but not limited to automobiles, trucks, briefcases, lunchboxes, and person for illegal drugs.  Failure to consent to such search shall be grounds for immediate removal from the Site or other premises owned, leased, or occupied by Purchaser;

drug testing at any time while on the Site or other premises owned, leased or occupied by Purchaser.  Failure to do so or failing any such test shall be grounds for immediate removal from the Site or other premises owned, leased, or occupied by Purchaser; and

failure of a Seller’s or Vendor’s employee to agree and abide by these requirements will be grounds for immediate removal from the job site or other premises owned, leased, or occupied by Purchaser from any work site or location under the control of Purchaser that is associated with the Scope of Work under this Agreement.

# PROJECT PLANNING AND CONTROLS

Exhibit K sets forth the Project Planning and Control system for tracking the progress of the Scope of Work.  Seller shall establish a program, submit reports and data as set forth therein.

# MISCELLANEOUS

## Validity and Enforceability»

.  The invalidity or unenforceability of any portion or provision of this Agreement shall not affect the validity or enforceability of any other portion or provision.  Any invalid or unenforceable portion or provision shall be deemed severed from this Agreement, and the balance of the Agreement shall be construed and enforced as if the Agreement did not contain such invalid or unenforceable portion or provision.  Notwithstanding the provisions of the preceding sentence, should any term or provision of this Agreement be found invalid by any governmental authority having jurisdiction thereof, the parties shall immediately renegotiate in good faith such term or provision of the Agreement to eliminate such invalidity.

## Governing Law»

.  This Agreement, its interpretation and any disputes relating to, arising out of or connected with this Agreement, shall be governed by the laws of the State of New York, without regard to its conflicts of law provisions (other than Section 5-1401 of the New York General Obligations Law).

## Entire Agreement»

.  This Agreement, and the Exhibits attached hereto constitute the entire agreement between the parties with respect to the subject matter hereof, and there are no oral or written understandings, representations or commitments of any kind, express or implied, not set forth herein.  This Agreement supersedes all prior agreements between the parties with respect to the subject matter hereof.

## Agreement Modification»

.  No oral or written modification of this Agreement either before or after its execution shall be of any force or effect unless such modification is in writing and signed by the party to be bound thereby.

## Waiver»

.  The waiver by any party of any breach or failure to enforce any of the terms, covenants or conditions of this Agreement shall not in any way affect, limit, modify or waive the future enforcement of such terms, covenants or conditions.

## Headings»

.  The headings contained herein are included solely for the convenience of the parties and are not to be used as a basis for interpreting the various sections of this Agreement.

## Third-Party Beneficiaries»

.  The provisions of this Agreement are intended for the sole benefit of Purchaser and Seller, and there are no third-party beneficiaries, other than assignees contemplated by the terms herein.

## Counterparts»

.  This Agreement may be executed in counterparts, each of which when so executed and delivered shall be an original, and all of which, when taken together, shall constitute one and the same instrument.

## Equal Employment Opportunity»

.  To the extent performance if any Scope of Work is performed in the United States, the parties hereto agree that the provisions of Executive Order 11246, as amended, and the Rehabilitation Act of 1973 (Section 503, Public Law 93-112, as amended), the Vietnam Era Veteran’s Readjustment Assistance Act of 1974, as amended (including the provisions of the “Equal Opportunity” clauses), and the regulations promulgated pursuant to the above, are hereby incorporated into this Agreement by reference as if fully set out.

## Cooperation on Site»

.  To the extent Seller is required to perform services on Site it shall cooperate with other contractors on Site so as to coordinate work and schedules.

## Nuclear Material»

.  The Equipment sold hereunder is not intended for application (and shall not be used) in connection with the use or handling of nuclear material or the construction or operation of a nuclear installation.  Purchaser warrants that it shall not use such Equipment for such purposes, or permit others to use such Equipment, while such Equipment is owned by Purchaser, for such purposes unless such use is agreed to in writing by the Seller.  If, in breach of the foregoing, any such use occurs, Seller disclaims all liability for any nuclear or other damage, injury or contamination, and Purchaser shall indemnify Seller against any such liability, whether arising as a result of breach of contract, warranty, tort (including negligence), strict liability, indemnity or otherwise.

IN WITNESS WHEREOF, the parties have caused this Agreement to be executed as of the date and the year first above written.

E-Next Generation, L.L.C. as Purchaser By: Name: Title:

GE Packaged Power, Inc. as Seller By: Name: Title: