## TW Bullets 5/11

# Red Rock Expansion – The first of the 7 expansion contracts was received executed from the customer (Western) this week.  Thanks to Legal and Regulatory for their support in getting the terms finalized.  Below is a status update on the remaining contracts.

| Red Rock Expansion Project, Contract Status |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Counterparty | MMBtu/d | Term/Yrs. | Deal Maker | Contract sent | Executed | Status |
| PPL | 20,000 | 30 | JF | Yes |  | Customer reviewing contract |
| Western | 10,000 | 15 | ML | Yes | Yes |  |
| Frito Lay | 8,000 | 15 | LL | Yes |  | Customer reviewing contract |
| US Gypsum | 4,500 | 12.25 | LL | Yes |  | Negotiating credit issues & customer reviewing |
| Newark Group | 800 | 5 | LL | Yes |  | Has pulled out, capacity offered to Oneok |
| BP Energy | 15,000 | 5 | LL | Yes |  | Customer reviewing contract |
| Oneok | 1,700 | 1.8 | ML | Yes |  | Customer reviewing contract |
| Calpine | 40,000 | 15 | JF | Yes |  | Customer reviewing contract |
| Total | 100,000 |  |  |  |  |  |

Negotiated Rate filing – Much of the week was spent with Facility Planning, Legal and Regulatory preparing the response to FERC’s 3rd set of questions on these negotiated contracts.  Phone tapes were received from Richardson that support TW’s position; no tapes were available from Sempra.  Our response is due to FERC on May 11.