ENRON RISK ASSESSMENT AND CONTROL

DEAL APPROVAL SHEET

| DEAL NAME: Caledonia Southern (SOCO)Transmission Counterparty: Business Unit: Enron North America Business Unit Originator: Mitch Robinson Public Private Merchant XStrategic Conforming Nonconforming | Date DASH Completed: September XX, 2000 RAC Analyst: Investment Type: Capital Funding Source(s): Equity Expected Closing Date: October XX, 2000 Expected Funding Date: October XX, 2000 Board Approval: Pending Received Denied N/A |
| --- | --- |

RAC Recommendation: Proceed with Transaction    Returns below Capital Price   Do not Proceed

#### APPROVAL AMOUNT REQUESTED (in 000’s)

Capital Commitment		$13,000

Bid Bond Amount		NA

# EXPOSURE SUMMARY

This transaction:		$13,600

Total			$13,600

## DEAL DESCRIPTION

The thrust of the project is to capitalize upon the strategic location of the Caledonia peaker within the dual interconnect region between TVA and Southern Company (SOCO).  The purpose of this connection is to allow a direct connection from Caledonia to the SOCO system.  The project is beneficial for the following three reasons: (1) the SOCO over TVA premium (2) transmission constraints in TVA (3) TVA transmission costs.  First, forward curves from the East Power Trading Desk indicate a premium to SOCO over TVA for at least the next three years, from 2001 through 2003.  Second, approximately 20 days per year occur where Caledonia can not sell power into SOCO because of TVA transmission constraints.  Third, this project allows Caledonia to avoid TVA transmission costs.

The project completion is scheduled before the summer peaking season of 2001.The best case completion date is June 1; mid case completion date is July 1; and worst case completion date would be after July 1.

A new 500kv line will be erected from the Caledonia generation station to a new substation to be located within the Southern Company service territory.  The line length will be approximately 3.2 miles, and line losses will approach zero given the short line length.

Interconnect studies by TVA and SOCO are underway to determine transient stability and load flow.  Completion of the studies is scheduled for November 2000.  Enron internal studies and third party studies indicate that the project will not effect reliability or flow capability for SOCO or TVA.

## TRANSACTION SOURCES AND USES OF FUNDS

|  | Sources |  |  | Uses |
| --- | --- | --- | --- | --- |
| Subordinated Debt | $ |  | Capital Expenditure | $12,700 |
| Enron Equity | $13,600 |  | Options | $900 |
| Total | $13,600 |  |  | $13,600 |

## RETURN SUMMARY

| Return Components (in 000s) : | PV @ Capital Price | ### Cumulative ### IRR |  | Capital Price Components |  |
| --- | --- | --- | --- | --- | --- |
| Cash Outflows | ($13,600) | - |  | Risk free rate (%): | % |
| Fees | $0 | - |  | Equity/Credit premium (%): | % |
| Intermediate Cash Flows | $8,628 | % |  | Country Premium (%): | % |
| Terminal Value | $1,020 | % |  | Transaction-Specific (%): | % |
| Total NPV | ($3,951) | % |  | RAC CAPITAL PRICE: | % |

| E-Rating |  |  | Relative upside ratio |  |
| --- | --- | --- | --- | --- |

Return Analysis:

Cash outflows of $13.6MM represent the equity investment.  Intermediate cash flows represent the sum of annual returns discounted at 10% over three years.  The terminal value represents a 10% salvage value of the initial investment which is then discounted at 10% over three years yielding $1,020,000.  Both the annual cash flows and the terminal value are discounted over three years given the extent of the forward curves used in modeling the revenues.  The summation of the discounted cash flows and terminal value less the cash investment  is equivalent to $2,980,000.  The estimated simple payback is 3 years with the terminal value incorporated.

Formula Legend:

Terminal Value = Investment * % for salvage value

Terminal Value = $13.6MM* 10%

Terminal Value = $1.36MM

Discounted Terminal Value = Terminal Value / (1 + discount rate) life

Discounted Terminal Value = $1.36MM / (1.1) 3

Discounted Terminal Value = $1.02MM

## TRANSACTION UPSIDES/OPTIONALITY

## (Include chart to show impact if appropriate)

Calpine and CoGentrix have indicated an interest in using the New Sub to interconnect to SOCO.  Possible 50-75% of New Sub costs shifted to Calpine/CoGentrix in 4Q2001.  New Sub is estimated at $3.7MM

EXIT STRATEGY (Merchant investments only)

Exit strategy is not applicable because this is a strategic deal and not a merchant deal.

# MILESTONES

$0.4MM on 9/10/00		circuit breaker option

$2.0MM on 9/15/00		transmission towers

$0.5MM on 9/15/00		land options

$0.17MM on 9/15/00		circuit breaker purchase

$0.83MM on 11/15/00	circuit breaker purchase

$9.1MM on 12/15/00		circuit breaker purchase, R.O.W., transmission E&C, switchyard

$500k					contingency (materials & labor)

$100k					contingency (Distribution service to New Sub)

$13.6MM				Total

## RISK MATRIX (Maximum 5)

| DESCRIPTION | MITIGATION/COMMENTS |
| --- | --- |
| TVA/SOCO Rejects Interconnect | Sell breakers and poles. Because the queue for ABB breakers is long and TVA requires ABB breakers, the resale value of the breakers is high. Conservative to probable resale assumptions for the breakers range from 50% to 70% of the purchase price. Limited resale opportunity for poles implies a resale value from 25% to 50%. Value at Risk on 12/1/00: $2.9MM. |
| Equipment Risk | Breakers and poles for essential segments delivered first. |
| Construction Risk | Construction of essential elements completed first |
| Land Option Risk | All options completed by 10/1/00. Value at Risk on 10/1/00: $.5MM (the cost of the option). |

KEY SUCCESS FACTORS

|  | NA | # Poor | # Fair | # Good | # Very Good | ##### Excellent |
| --- | --- | --- | --- | --- | --- | --- |
| Core Business |  |  |  |  |  |  |
| Strategic Fit |  |  |  |  |  |  |
| Upside Potential |  |  |  |  |  |  |
| Management |  |  |  |  |  |  |
| Risk Mitigation |  |  |  |  |  |  |

OTHER RAC COMMENTS:

| # APPROVALS |  | Name |  | Signature |  | Date |
| --- | --- | --- | --- | --- | --- | --- |
| Regional Mgmt. |  |  |  |  |  |  |
| Tax |  |  |  |  |  |  |
| Legal |  | Mark Haedicke |  |  |  |  |
| RAC Management |  | Rick Buy |  |  |  |  |
| Enron Capital Management |  | Andy Fastow/Jeff McMahon |  |  |  |  |
| ENE Management |  | Jeffrey Skilling |  |  |  |  |
| Other |  |  |  |  |  |  |

Global Finance Summary (addendum to DASH)

| - Transaction Summary: | Amount ($000) |
| --- | --- |
| Total Deal/Project Capital Commitment | $13,000 |
| Less: Financing | -0- |
| Less: Syndication | -0- |
| Net Enron Investment | $13,000 |

- Investment terms and pricing:			 Market	 Above Market	 Below Market

Describe (if necessary):

- Financing terms and pricing:			 Market	 Above Market	 Below Market

Describe (if necessary):

- Legal or practical liquidity restrictions:		 Unrestricted	 Legally Restricted	 Practically Restricted

Describe (if necessary):

- Any recourse to Enron (other than investment):			 Recourse		 No Recourse

Describe (if any):

- Business unit intent to syndicate:			 None		 Partial		 All

Describe (if necessary):

- Intended Enron hold period:

- Likely Syndication Market:			 Industry/Strategic Partner	 Direct Private Equity

Capital Markets		 JEDI		  JEDI 2	 Enserco

LJM 1 or 2		 Condor	 Margaux		 Other:

- Is this a JEDI 2 “Qualified Investment”?		 Yes			 No

- Business unit intent to hedge investment price risk (e.g. with Raptor)?

None		 Partial		 All
	Describe (if  necessary):

Global Finance Representative:

Global Finance Legal:													Scott Sefton

Signature			Name (Printed)						Date