ENRON RISK ASSESSMENT AND CONTROL

###### DEAL APPROVAL SHEET

| DEAL NAME: Pastoria V - Development Counterparty: Pastoria Energy Facility LLC Business Unit: ENA West Origination Business Unit Originator: David Parquet Public Private Merchant Strategic Conforming Nonconforming | Date DASH Completed: March 7, 2001 RAC Underwriter/Analyst: Karen Barbour Transaction Type: Power Asset Development Capital Funding Source(s): Balance Sheet & Off B/S Option Closing Date: March 15, 2001 Funding Date: Beginning March 15, 2001 Board Approval: Pending Received Denied  N/A |
| --- | --- |

RAC Recommendation:	 Proceed with Transaction 	   Returns Below Capital Price 		  Do not Proceed

## APPROVAL REQUESTED

- To commit $197.0 to the turbine purchase through TurboPark financing.

- To submit a binding bid on March 15 to Kern River Pipeline (“Kern”) for a 15-year term, 100,000 MMBtu/day of gas transportation capacity from the primary receipt point at Opal in the Rocky Mountains to the Wheeler Ridge delivery point, backed up by an ENA guarantee of [specify the amount and duration.]

- To request additional development cost of $1.9 million through May 31, 2001.

| VaR – gas transportation contract*1 | $34.0 million |
| --- | --- |
| Development Cost | 1.9 million |
| Total Development Cost | $35.9 million |
| Remaining Turbine Cost*2 | 178.2 million |
| Total Risk Adjusted Capital | $214.1 million |

*1:  Represents the value at risk over an estimated 45-day hedging period.

*2:  Progress payments totaling $19.8 million were previously approved and paid.  For the period ending May 31, 2001, progress payments totally $9.9 million is expected to be made.

## EXPOSURE SUMMARY

| This Transaction*3 | $35.9 million |
| --- | --- |
| Previously Approved Development Costs*3 | 48.3 million |
| Cumulative Exposure*3 | $84.2 million |

*3:  Excluding turbine cost.  See “risk matrix” for further discussion on the turbine purchase exposure. – check the $5 mm contingency.

## DEAL DESCRIPTION

- ENA previously obtained approvals to develope Pastoria, a limited liability entity through which ENA is developing a 750MW gas-fired power plant (the “Project”) in Kern County, California.  The development phase is essentially completed, with all material state and federal permits obtained.

- ENA is currently finalizing the negotiation of a Purchase and Sale Agreement (the “PSA”) with Pastoria Energy Center LLC (the “Buyer”), a wholly owned subsidiary of Calpine Corporation, for the sale of 100% interest in the Project.  The PSA is expected to be signed on March 9, 2001 and the closing is expected to occur about 30 days later.

- Prior to closing the sale to the Buyer, certain additional development costs need to be deployed in order to keep the Project on track, and to maintain the marketability of the Project should this intended sale not close.  The major upcoming developments include:

- [turbine commitment or progress payment]

- Participation in Kern’s open season to bid for a 15-year term, 100,000 MMBtu/day of gas transportation capacity.

- In the event the pending sale to the Buyer does not close by April 30, 2001, ENA plans to continue development of the project through May 31, 2001.  During that period, ENA will pursue one or more of the following alternatives:

- Continue to negotiate a long-term fixed price toll arrangement with California Department of Water Resources and concurrently arrange for an EPC Contract and construction financing;

- Continue with the marketing efforts to sell the Project;

- Arrange for an EPC contract and construction financing for a merchant plant.

- If none of the above alternatives prove to be viable by May 31, 2001, ENA will have the option to delay the project and redeploy the gas turbines to another Enron project, remarket the emission reduction credits and the gas transportation capacity.  The cumulative development expenses as of May 31, 2001, assuming no recovery on the emission credit cost and a 45-day hedging period for the gas transportation capacity contract, will be about $84.1 million.

TRANSACTION SOURCES AND USES OF FUNDS ($000)

|  | Sources |  |  | Uses |
| --- | --- | --- | --- | --- |
| Equity | $1,900 |  | Development Costs | $1,900 |
| Off Balance Sheet Funding | 178,200 |  | Turbine Progress Payments | 178,200 |
| Total | $190,100 |  | Total | $190,100 |

## TRANSACTION UPSIDES/DOWNSIDES

## RISK MATRIX

| RISK | MITIGATION/COMMENTS |
| --- | --- |
| # Development Risks - Gas Transportation - Pastoria intends to submit a bid for a 15-year term, 100,000 MMBtu/day of gas transportation capacity from the primary receipt point at Opal in the Rocky Mountains to the Wheeler Ridge delivery point. The outcome of the bid is currently uncertain. Without a gas transportation contract of this size, the Project will be difficult to market. - The Project will bear the spot market risk for the remaining 20,000 MMBtu/day of gas transportation capacity required for the project. - If ENA decides to terminate the project development subsequent to securing the Kern contract, it will be exposed to the liquidation value of the Kern contract. - purchase the remaining capacity from the spot market. | - [Ron: comfort level of securing the intended capacity from Kern – open season is all or nothing? Also, plans to secure capacity from other sources?] - ENA gas desk estimates that it will take a year to liquidate the Kern contract. The value at risk for an estimated 45-day hedging period prior to the ultimate liquidation is about $34.0 million. |
| # Development Risks - Water Supply - The Project currently has a primary, interruptible, water supply contract and is in the process of securing a firm back-up supply contract from Kern Water Bank Authority (the “Authority”) through a relatively difficult negotiation. Without the back-up supply contract, the Project will be subject to supply interruptions. - [legal concerns over the back-up contract if Azurix were to stay in?] | - ENA has finalized a term sheet with the Authority and has initiated the negotiation process on the definitive agreement. - [Ron: What’s the backup plan if this negotiation falls apart?] |
| Development Risks – Marketability - Out of the six interested investors, the Buyer offered the highest price and presented the least mark-up on the transaction documents. If the sale to the Buyer does not close, a potential sale to the other interested investors may offer lesser economic return to ENA. - The well-publicized struggles by California with rolling black-outs and its unsuccessful attempt to deregulate may result in a new business and/or political environment, including re-regulation, that may make California less attractive for potential purchasers. | - [Ron: speak of the quality of the other five bids as mitigants to market risk.] - Notwithstanding the difficult political environment, California is in critical need of new power plants. The Project, given that it is fully permitted, is expected to be attractive to serious investors in the California market. |
| Project Financing - ENA has not secured a firm EPC contract, nor has it negotiated a power purchase agreement for the output. Therefore, the timing of ENA’s ability to arrange for a non-recourse project financing is uncertain. |  |

# KEY SUCCESS FACTORS

|  | NA | ##### Poor Excellent |
| --- | --- | --- |
| Core Business |  |  |
| Strategic Fit |  |  |
| Upside Potential |  |  |
| Management |  |  |
| Risk Mitigation |  |  |

- OTHER RAC COMMENTS:

Should ENA desire to commit capital to the project in excess of that requested herein, it must seek further board approval.

| # APPROVALS |  | Name |  | Signature |  | Date |
| --- | --- | --- | --- | --- | --- | --- |
| West Origination |  | David Parquet |  |  |  |  |
| West Management |  | Chris Calger |  |  |  |  |
| Americas Legal |  | Mark Haedicke |  |  |  |  |
| Americas Accounting |  | Wes Colwell |  |  |  |  |
| Americas Tech Services |  | Brian Redmond |  |  |  |  |
| Americas Executive |  | John Lavorato |  |  |  |  |
| EWS OOC |  | Mark Frevert |  |  |  |  |
| RAC Management |  | Rick Buy / Dave Gorte |  |  |  |  |
| ENE Global Finance |  | Andy Fastow / Ben Glisan |  |  |  |  |
| ENE OOC |  | Jeff Skilling |  |  |  |  |

| Item | Costs per DASH 4/30/99 | Costs per DASH 5/22/00 | Costs per DASH 7/12/00 | Incremental Amount per this DASH | Total ENA Equity |
| --- | --- | --- | --- | --- | --- |
| Internal Costs | $1,000 | - | - | - | $1,000 |
| Tejon Payments (Signing of Land Lease Option) | 500 | - | - | - | 500 |
| Tejon Payment (Data Adequacy and Water) | 1,000 | - | - | - | 1,000 |
| Tejon Monthly Payments | 2,150 | - | - | 500 | 2,650 |
| Environmental Permitting/Development Engineering | 810 | - | 1,820 | 250 | 2,830 |
| Air District Filing Fee | 200 | - | (100) | - | 100 |
| ALTA Survey | 250 | - | (250) | - | - |
| Legal Fees | 2,000 | - | - | 500 | 2,500 |
| Air Pollution Offsets | 15,000 | - | 12,800 | - | 27,800 |
| Engineering (EPC related) | 340 | - | 227 | 100 |  |
| Purchase of Antelope Valley Transmission Queue Position | - | - | 4,000 | - | 4,000 |
| 12/15/00 Turbine Progress Payment | - | - | 9,900 | - | 9,900 |
| Advance Water Payment | - | - | 1,100 | - | 1,100 |
| Contingency | 5,000 | - | - | - | 5,000 |
| Miscellaneous | 90 | - | 410 | 200 | 700 |
| 11/15/00 Turbine Progress Payment (Catalytica Spark Spread Option Repurchase) | - | 9,900 | - | - | 9,900 |
| Azurix Back-up Water Option Premium | - | - | - | 200 | 200 |
| San Luis Obispo Air District | - | - | - | 148.5 | 148.5 |
| Gas Transportation | - | - | - | 34,000 | 34,000 |
| Total | $28,340 | $9,900 | $29,907 | $35,898.5 | $104,045 |