ENRON ENGINEERING  & CONSTRUCTION COMPANY

EPC AGREEMENT TRANSACTION PLANNER

[     PROJECT  NAME___]

Date Prepared_____ Rev. No. ___

| PROJECT NAME: |  |
| --- | --- |
| BUSINESS UNIT: |  |
| CONFORMITY WITH EXPERIENCE / STRATEGIC MARKET ENTRY: |  |
| PROJECT DECRIPTION: |  |
| COUNTRY & RISK RATING |  |
| AFFILIATE PROJECTS IN COUNTRY |  |
| THIRD PARTY PROJECTS IN COUNTRY |  |

| ISSUE OR RISK | PRIMARY ALLOCATION OF LIABILITY | MITIGATION | RESIDUAL OWNER/LENDER RISK | RESIDUAL CONTRACTOR RISK | COMMENTS OR CONSIDERATIONS |  |
| --- | --- | --- | --- | --- | --- | --- |
| - MACRO ISSUES NON US/ EUROPE |  |  |  |  |  |  |
| (a) Risk of government instability or dishonoring contracts |  |  |  |  |  |  |
| (b) Currency Risk: instability and inconvertibility |  |  |  |  |  |  |
| (c) Risk of Effective and fair courts and legal system |  |  |  |  |  |  |
| (d) Ability of existing regulatory framework to support project. |  |  |  |  |  |  |
| (e) Risk of general labor unrest or strikes |  |  |  |  |  |  |
| 2. CUSTOMER AND OFF-TAKERS |  |  |  |  |  |  |
| (a) Customer creditworthiness and reliability: - Balance sheet strength - Parent or sovereign guarantee? - Experience? - Number of owners? |  |  |  |  |  |  |
| (b) Ultimate offtaker’s creditworthiness and reliability - Balance sheet strength - Parent or sovereign guarantee? - Experience? - Number of owners? |  |  |  |  |  |  |
| 3. SPECIFIC PROJECT DEVELOPMENT ISSUES |  |  |  |  |  |  |
| - Site Risk - Who selects - When selection and acquisition is to occur |  |  |  |  |  |  |
| - geotech/geology risk |  |  |  |  |  |  |
| -manmade underground obtructions |  |  |  |  |  |  |
| -archeology, graveyards, cultural issues |  |  |  |  |  |  |
| -wildlife/ endangered species |  |  |  |  |  |  |
| -adjacent property and effect (emissions, liability) |  |  |  |  |  |  |
| - displacement of people, relocating, and retraining |  |  |  |  |  |  |
| (c) Restricted access to, interference with use of Site |  |  |  |  |  |  |
| -sufficiency of road, rail, water and air infrastructure for site access/ responsibility for right to use and damage caused |  |  |  |  |  |  |
| - pre-existing rights of others owners, lessors and lessees, rights of way, squatters |  |  |  |  |  |  |
| - interference by public disturbances on, at or in vicinity of site |  |  |  |  |  |  |
| - interference by Owner and other contractors |  |  |  |  |  |  |
| 3. AT RISK DEVELOPMENT EXPENSES IF NTP DOESN’T OCCUR |  |  |  |  |  |  |
| - EECC internal development costs |  |  |  |  |  |  |
| -EECC external expenses development costs |  |  |  |  |  |  |
| - Engineering and equipment cash flow and cancellation |  |  |  |  |  |  |
| 4. DEFINITION OF SCOPE OF WORK |  |  |  |  |  |  |
| - risk of certainty and technical sufficiency of scope definition as basis for pricing and defining obligations |  |  |  |  |  |  |
| - risk of gaps in scope, changes in scope post-pricing |  |  |  |  |  |  |
| 5. SELECTION OF MAJOR EQUIPMENT |  |  |  |  |  |  |
| - risk of certainty of equipment selection decision as a basis for pricing |  |  |  |  |  |  |
| - risk of availability of major equipment, time to commit, and cancellation charges |  |  |  |  |  |  |
| 6. DEFINITION OF SCHEDULE |  |  |  |  |  |  |
| Risk of certainty of owner estimated PNTP date. |  |  |  |  |  |  |
| Risk o f Certainty of owner NTP and Financial Close date |  |  |  |  |  |  |
| Effect of delay in PNTP/Financing/ NTP |  |  |  |  |  |  |
| 8. DEFINTION OF PRICE. |  |  |  |  |  |  |
| Certainty of and support for pricing basis |  |  |  |  |  |  |
| 9. CHANGES IN SCOPE, SCHEDULE AND PRICE |  |  |  |  |  |  |
| Owner requested additions/deletions |  |  |  |  |  |  |
| Contractor suggested additions/deletions |  |  |  |  |  |  |
| Change in Law - Risk of adequacy of legal due diligence - base date identified |  |  |  |  |  |  |
| Changes to make work comply with law in effect before Change in Law base date |  |  |  |  |  |  |
| Changes resulting from Changes in Law after base date |  |  |  |  |  |  |
| Change in Tax - risk of adequacy of tax due diligence - base date identified - risk of changes in tax after base date |  |  |  |  |  |  |
| Force Majeure |  |  |  |  |  |  |
| 10. NTP CONDITIONS |  |  |  |  |  |  |
| Risk of inadequate Owner Financing |  |  |  |  |  |  |
| Risk of unrestricted access to Site |  |  |  |  |  |  |
| Risk of performance obligations prior to NTP |  |  |  |  |  |  |
| 11. LOCAL PERMITTING (responsibility for & timely issuance) |  |  |  |  |  |  |
| (a) adequacy of EECC due diligence re impact of permits, laws and regulations |  |  |  |  |  |  |
| (b) general permit to build Plant |  |  |  |  |  |  |
| (c) permits to conduct specific construction activities |  |  |  |  |  |  |
| (d) Interconnection permits (connect to grids and fuel lines) |  |  |  |  |  |  |
| (e) Environmental effluent and emissions permits |  |  |  |  |  |  |
| (f) permits to operate Plant/certifications of Plant entering commercial operations |  |  |  |  |  |  |
| (g) import clearances |  |  |  |  |  |  |
| 12. RISK OF SUPPLY OF AND PAYMENT FOR CONSTRUCTION UTILITIES AND DELAY |  |  |  |  |  |  |
| - power supply |  |  |  |  |  |  |
| - water supply |  |  |  |  |  |  |
| - on-spec fuel and delivery point |  |  |  |  |  |  |
| - waste water disposal |  |  |  |  |  |  |
| 13. TAKING OVER/ SUBSTANTIAL COMPLETION |  |  |  |  |  |  |
| Entitlement to Revenues from testing power |  |  |  |  |  |  |
| If operations are permitted prior to Substantial Completion, entitlement to Revenues from operations prior to Substantial Completion (ie, while contractor is still on LD hook) |  |  |  |  |  |  |
| Risk of objectiveness Conditions to Taking Over |  |  |  |  |  |  |
| Risk of owner achieving commercial operations under off-take agreement |  |  |  |  |  |  |
| Risk of obtaining any operating permits |  |  |  |  |  |  |
| 13. LIABILITY FOR PERFORMANCE DELAY |  |  |  |  |  |  |
| Risk that Performance Guarantees are within capability of equipment and design |  |  |  |  |  |  |
| Risk of Completion at less than full guarantees for: - performance - efficiency |  |  |  |  |  |  |
| Risk of damages in excess of liquidated damages for failure to meet Performance Guarantees |  |  |  |  |  |  |
| Schedule Guarantee is within capability of equipment, design and construction |  |  |  |  |  |  |
| Risk of schedule delay in Substantial Completion in excess of cap on delay liquidated damages |  |  |  |  |  |  |
| LIMITS ON LIABILITY |  |  |  |  |  |  |
| Overall Liability is subject to an aggregate cap, except for third party indemnity for personal injury and property damage |  |  |  |  |  |  |
| Overall liability for Liquidated Damages are subject to subcaps |  |  |  |  |  |  |
| Liability for consequential damages |  |  |  |  |  |  |
| WARRANTY |  |  |  |  |  |  |
| Duration of exposure, and latent defects, etc. |  |  |  |  |  |  |
| Remedies for warranties are limited to repair & replace and are stated to be exclusive |  |  |  |  |  |  |
| Consequential losses that owner incurs during Warranty work |  |  |  |  |  |  |
| Risk of Warranties (including evergreen) are subject to clear sunset |  |  |  |  |  |  |
| All implied warranties are excluded and remedies for warranties are limited exclusively to those in the Contract. |  |  |  |  |  |  |
| INDEMNITY |  |  |  |  |  |  |
| INSURANCE |  |  |  |  |  |  |
| Adequate coverage and appropriate deductibles provided by Contractors Comprehensive General Liability Policy |  |  |  |  |  |  |
| Builders All Risk - contractor places, or places jointly with owner - owner bears risk of loss - covers business interruption - waives subrogation against Contractor and Subcontractors, and names them as insureds - [contractor obligation to proceed with repair work conditioned on carrier commitment to pay for such work.] - DOES NOT include contractors’ CGL |  |  |  |  |  |  |
| Contractor does not provide coverage for: - Errors and Omissions - Pollution |  |  |  |  |  |  |
| All insurance is jointly brokered and placed, Contractor is named an insured |  |  |  |  |  |  |
| Subrogation is waived against Contractors and Subcontractors |  |  |  |  |  |  |
| OPERATIONS |  |  |  |  |  |  |
| Adequate number of operators |  |  |  |  |  |  |
| Operators adequately trained, experienced and competent |  |  |  |  |  |  |
| Scope of Contractor obligation to train clearly defined and limited |  |  |  |  |  |  |
| Operators take instruction from Contractor during start-up and commissioning |  |  |  |  |  |  |
| FORCE MAJEURE |  |  |  |  |  |  |
| Force majuere definition of events beyond control, with illustrative, not exhaustive listing of events. |  |  |  |  |  |  |
| Political force majeure, including state action, war, general civil, labor unrest, etc., impacts: - Schedule - Cost - Other |  |  |  |  |  |  |
| Other force Majeure, including natural events etc., impacts: - Schedule - Cost - other |  |  |  |  |  |  |
| Suspension or termination by Owner |  |  |  |  |  |  |
| Suspension of Termination by Contractor |  |  |  |  |  |  |
| Changes in Law after base date |  |  |  |  |  |  |
| TAXES AND CHANGE IN TAX |  |  |  |  |  |  |
| Income taxes |  |  |  |  |  |  |
| customs duties and fees |  |  |  |  |  |  |
| Sales and VAT |  |  |  |  |  |  |
| Use fees |  |  |  |  |  |  |
| Other taxes |  |  |  |  |  |  |
| Change in tax |  |  |  |  |  |  |
| DRAWINGS |  |  |  |  |  |  |
| Contractor retains ownership of design as evidenced by drawings |  |  |  |  |  |  |
| Owner right to comment/approve limited to core listed drawings |  |  |  |  |  |  |
| Owner comment/approval Cycle limited in time to fit schedule |  |  |  |  |  |  |
| Owner rights to use drawings limited to this Project only |  |  |  |  |  |  |
| TERMINATION BY OWNER |  |  |  |  |  |  |
| For Cause |  |  |  |  |  |  |
| For Convenience |  |  |  |  |  |  |
| TERMINATION BY CONTRACTOR |  |  |  |  |  |  |
| For Cause |  |  |  |  |  |  |
| Extended Force Majeure |  |  |  |  |  |  |
| Extended Delay in NTP |  |  |  |  |  |  |
| GOVERNING LAW |  |  |  |  |  |  |
| Governing law is either New York or English |  |  |  |  |  |  |
| DISPUTE RESOLUTION |  |  |  |  |  |  |
| Expert Provisions |  |  |  |  |  |  |
| - neutrality of expert |  |  |  |  |  |  |
| - efficiency of recourse to expert |  |  |  |  |  |  |
| - irrational decision of expert |  |  |  |  |  |  |
| -enforcement of decision |  |  |  |  |  |  |
| Arbitration Provisions |  |  |  |  |  |  |
| - Neutrality of rules - Neutrality and qualification of arbitrators - Irrational decision of tribunal - Award of expenses - Enforceability of award |  |  |  |  |  |  |
| Litigation provisions - Neutrality of applicable laws - Neutrality and qualification of courts - Irrational decision of court - Award of expenses - enforceability of judgment |  |  |  |  |  |  |