Enron Kids 1999 - Timeline

By 8/9/99:			Purchase pencil bags			Geneva Davis

Purchase Enron Pencils			Geneva Davis

Prepare memos to parents 			Lillian, Bert

Get parent memo printed in color		Kevin Hyatt

8/12/99				Deliver pencil bags/memos to school		Lillian

Attend teacher meeting at school to inform them of the program and how they can help					Lillian, Bert

8/16/99				Update/Revise Permission slip		Sandy Dutton

Update/Revise sponsor packet		Lillian, Bert

Provide any vendor discount info		Sharon Stringfellow

8/26 6pm				Attend Open House to inform parents 		Lillian, Bert

Permission slips go out

Mid 9/99				Get permission slips back			Lillian

Begin to Update database			Pam Rhea

Obtain gift bag donation			Lillian

Early 10/99			Take class pictures at school (10/8 9:30-11am)			Bert

Arrange for transportation(Truck & busses)	Ruth Mann

Coordinate pickup & delivery details of

packages with Transporter			Geneva Davis

Mid 10/99			Have pictures numbered & identified by Teachers and

Prepare Pictures for display			Bert

Prepare Invites to Preview Party		Sherry Butler

Work with Graphics group to get posters	Sandy Dutton

Work with facilities to book lobby, display posters, table setup, gift storage

Geneva Davis

Get volunteers to man signup tables		Emitra Nelson

By Oct 22			Send out ccmails to Rachel Tobor		Lillian

Send invites to preview party			Sherry Butler

Schedule school band to perform in EB Lobby on 11/2	Lillian

(Scheduled for 11/2 from 11-1 & 11/4 from 11:30-12:30)

11/1				Preview Party				Volunteers

11/2 - 11/12 (if needed)		Sponsor sign-up				Volunteers

Mid 11/99			Finalize uniform vendor & get students sized	Sharon Stringfellow

Send email to solicit Management donations	Sharron Westbrook

Early 12/99			Print name tags & signup sheets for sponsors to use at school	????

Finalize snacks for students & volunteers	Daryl Kitchen

Shopping Cmte finalizes any required shopping	Sharon tringfellow & Lesli Campbell

12/6  - 12/10			Gift dropoff

12/13				Deliver Gifts & Snacks to school		Truck & Volunteers

Shopping Cmte finalizes any required shopping	Sharon Stringfellow & Lesli Campbell

12/14				Party Date!				Volunteers

Shopping Cmte finalizes any required shopping	Sharon Stringfellow & Lesli Campbell

Early January, 2000		Arrange for delivery of Uniforms		Sharon Stringfellow

Mid 1/2000			Discuss extra funds				Committee