Hi Team,

Following are the items and timeline discussed in our last meeting.  Please send me any additions/corrections that are needed.

By 8/9/99:

- Purchase pencil boxes			Bert Hernandez & Lillian Villarreal

- Purchase Enron Pencils			Geneva Davis

- Purchase stick-on labels for boxes		N/A

- Print Labels for Pencil boxes		Sherry Butler, Kevin Hyatt

- Prepare memos to parents 			Lillian, Bert

- Get note printed in color			Kevin Hyatt will check with Xerox

- Prepare pencil boxes 			Committee

8/12/99

- Deliver pencil boxes/memos to school	Lillian

- Attend teacher meeting at school to inform them of the program and how they can help									Lillian, Bert

8/16/99

- Update/Revise Permission slip		Sandy Dutton

- Update/Revise sponsor packet		Lillian, Bert

- Provide any vendor discount info		Sharon Stringfellow

8/26

- 6pm Attend Open House to inform parents 	Lillian, Bert

- Permission slips go out

# Mid 9/99

- Get permission slips back			Lillian

- Begin to Update database			Pam Rhea, Bert Hernandez

- Obtain gift bag donation			Lillian

# Early 10/99

- Take class pictures at school		Bert

- Arrange for transportation (Truck & busses)	Ruth Mann

# Mid 10/99

- Have pictures numbered & identified by Teachers and

- Prepare Pictures for display			Bert

- Prepare Invites to Preview Party		Sharon Butler

- Work with Graphics group to get posters	Sandy Dutton

- Work with facilities to book lobby, display posters, table setup, gift storage

- Geneva Davis

- Get volunteers to man signup tables		Emitra Nelson/Dennis Lee

# By Oct 22

- Send out ccmails to Rachel Tobor		Lillian

- Send invites to preview party		Sharon Butler

- Schedule school band to perform in EB Lobby on 11/2	Lillian

- Send management email to Sharron Westbrook for distribution Lillian

10/25

- Send management solicitation email		Sharron Westbrook

10/28

- Prepare Packets in EB48C2 (11:30-2)	Volunteers

11/2

- Preview Party				Volunteers

11/2 - 11/12 (if needed)

- Sponsor sign-up				Volunteers

# Mid 11/99

- Finalize uniform vendor & get students sized	Sharon Stringfellow

# Early 12/99

- Print name tags & signup sheets for sponsors to use at school	Lorraine Becker

- Finalize snacks for students & volunteers	Daryl Kitchen

- Shopping Cmte finalizes any required shopping	Sharon Stringfellow & Lesli Campbell

12/6  - 12/10

- Gift dropoff (Body Shop & EB2802)		Volunteers

- Send reminder email with party schedule	Lillian

12/13

- Deliver Gifts & Snacks to school			Truck & Volunteers

- Shopping Cmte finalizes any required shopping	Sharon Stringfellow & Lesli Campbell

12/14

- Party Date!					Volunteers

- Shopping Cmte finalizes any required shopping	Sharon Stringfellow & Lesli Campbell

# Early January, 2000

- Arrange for delivery of Uniforms			Sharon Stringfellow

# Mid 1/2000

- Discuss extra funds				Committee