## Exhibit A

- Price of $56 MM US shall include delivery to the Moore Project site in Moore Township in southwestern Ontario (roughly 20 miles south of Sarnia, Ontario).

- Price of $56 MM US includes the items set forth in section 4.2 d).

- The exciter modifications to a static exciter system as required by Ontario’s grid company Hydro One, shall be made at no extra cost to Enron Canada, in the field or in the shop, at ABB’s discretion (scheduling coordinated with Enron Canada if in the field), but in no case shall the turbine delivery to site be delayed past November 2000.

- The takeover and drawings LD Option shall be exercised, with the cost included in the $56 MM.

- Duties and taxes per section 6 related to import into Canada will remain the responsibility of Seller.

- The output minimum level should be raised to 97%, and failed starts should be limited to 7 in year one and 5 in year two for less than 100 starts each year.

- The repair/replace terms of the contract shall be modified such that Enron Canada shall be able to choose, at its sole discretion, to replace parts versus repairing them, in order to maximize run-time (and the determination as to the best course of action shall be at Enron Canada’s sole discretion).

- The definition of law shall be amended to Canadian law, and the work must comply with all applicable laws. Are you asking for something in addition to 9 below?

- All equipment will need to conform to CSA and Ontario laws and codes and standards in order to be installed in Ontario, Canada, and ABB will be required to warrant accordingly.

- Per Articles 2 and 3, delivery is determined as the time that the Equipment is delivered to the Delivery Point or placed into storage at Purchaser’s request.  Under the agreement, if it was determined that the equipment was damaged prior to delivery, warranty provisions would kick in, and we would lose our rights to delay LD’s.  Delivery should be deemed to occur only at the Delivery Point (Site).

- Section 2.1 can add significant expense as it deems removal from storage to be at Purchaser’s expense, even if the equipment is put into storage due to an event of Force Majeure. What do you want to do here?

- In section 13.1(d), Seller shall be responsible for costs related to disassembly/reassembly for warranty work.

- In section 13.1(f) the references to Seller in subparagraph 1, 2,and 7 should read “by, through or under Seller or its subcontractors” to ensure that warranties apply even if a subcontractor improperly repairs the equipment.

14.	The contract should contain a put option satisfactory to Enron.  What do we want for a put option?