Pacific Gas and Electric Company

Summer 2001 Generator Interconnection Status

Monthly Report to CPUC Required under AB 970 OII

6/1/2001

Status Summary:

Of the 12 remaining CAISO 2001 Summer Reliability Generation projects in PG&E’s service area (representing 545 MW):

NEO, Chowchilla, 49 MW: First 24 MW on-line May 28 with next 25 MW soon to follow.

NEO, Red Bluff, 49 MW and Wellhead, Fresno, 18 MW, have estimated on-line dates in June.

Wellhead, near Gates and Panoche substations, 49 MW each, Negotiating GSFA language with PG&E.

Wellhead, near Tesla substation, 49 MW, On hold per the generator.

Wellhead, Stockton, 22 MW, Cancelled per the generator.

CalPeak, Vaca Dixon and Midway substations, 49 MW each, GSFA signed and PG&E lease in final negotiations.

CalPeak, Panoche substation, 49 MW, GSFA signed, PG&E lease in final negotiations and CEQA permit approved.

Panda, Lambie Industrial Park, 135 MW, Negotiating GSFA/SFA language with PG&E.

Seven ISO RFB projects, representing 303 MW—Tenaska Vaca Dixon, Mt. Poso Bakersfield, Ramco Livermore, Ramco Pleasanton, Tejas Antioch, Tejas Oakley, Wellhead Stockton—have canceled or relocated out of PG&E’s service territory.

###### Forecast:

The four projects with signed GSFAs are the most likely to be interconnected this summer.  The other nine projects are less likely to be interconnected during Summer 2001, i.e. by September 30.  Under PG&E’s original internal schedule for these Summer 2001 projects, we believed that a July 1, 2001, interconnection date was feasible if we received a signed GSFA in early November 2000.  Thus, these nine projects are at least six months behind the original internal schedule.

###### Process Description:

Table 1, below, describes the projects and gives the status of the GO 131-D NOC and Section 851 Lease/License processes, where applicable.  These columns focus on the early part of the interconnection process, prior to engineering and construction.  Table 2, below, lists some of the later steps in the interconnection process.  Some of the general steps involved with interconnecting to PG&E include:

- The generator secures a site and applies to PG&E for electric and natural gas interconnections.

- PG&E does a preliminary electric system impact study within 7 days, after which, a facility impact study and complete system impact study is completed.  This includes a general estimate of equipment needed, system impacts, if any, and cost.  PG&E offers different kinds of studies.  In addition to the 7-day process, PG&E has created an expedited electric interconnection study for 50 MW summer peakers which can take as little as 2 weeks.

- If mutually agreeable, PG&E and the generator execute a special facilities agreement, after which the generator funds, and PG&E performs, detailed engineering work and ordering of long lead-time materials.

- The generator must acquire financing, generating equipment, step-up transformer and long lead-time materials for its share of construction.

- In parallel, and before any construction begins, the generator must acquire necessary governmental permits through its CEQA lead agency, after which, in some cases (see Table 1 below), PG&E must file a GO 131-D NOC with the CPUC.

- For those projects for which an NOC is required, protests may be filed within 20 days of the date of first publication of the notice.  If protests are filed, the CPUC’s rules require the Commission to issue an Executive Resolution either approving or rejecting the protest within 30 days of the date of the utility’s response to the protest.  After the generator gets permit approval and, if appropriate, the NOC becomes effective, the generator and PG&E each performs its share of construction, funded by the generator.

- Generators using PG&E land must sign a license or, if requested, a lease.  Leases require a Section 851 filing with the CPUC.

- The generators must execute a Generator Interconnection Agreement with PG&E and a Participating Generator Agreement with the ISO.

- Generators requiring standby service or temporary construction power must apply for retail service and PG&E must arrange the service.

- Generators using natural gas must sign a Natural Gas Service Agreement.

- Generators must comply with ISO metering requirements.

Pacific Gas and Electric Company, Summer 2001 Generator Interconnection Status

Monthly Report to CPUC Required under AB 970 OII,

6/1/2001

Table 1, Project Description and Status of GO 131-D NOC and Section 851 Lease/License Processes

| ##### Pro- ject | Generator | Utility |  | Location |  |  | Unit(s) |  |  | GO 131-D notice required? | NOC | 851 Lease / License | Local agency CEQA review |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ##### ID | Name | Elec. | Gas | County | City | Substation | # | Type | MW | Yes/No | Status | Status | Status |
| (a) | (a’) | (b) | (c) | (d) | (e) | (f) | (g) | (h) | (i) | (l) | (m) | (n) | (o) |
| 1a | CalPeak | PG&E | SCG | Kern | Buttonwillow | **Midway | 1 | CT | 49 | No | NA | 1 | 2 |
| 1b | CalPeak | PG&E | PG&E | Fresno | Mendota | **Panoche | 1 | CT | 49 | No | NA | 1 | 3 |
| 1c | CalPeak | PG&E | PG&E | Solano | Vacaville | **Vaca Dixon | 1 | CT | 49 | No | NA | 1 | 2 |
| 3a | Wellhead | PG&E | PG&E | San Joaquin | Tracy | Tesla | 1 | CT | 49 | Yes | 2 (*) | NA | 1 |
| 3b | Wellhead | PG&E | PG&E | Fresno | Huron | Gates | 1 | CT | 49 | Yes | 2 (*) | NA | 1 |
| 3c | Wellhead | PG&E | SCG | Fresno | Fresno | Fresno Cogen | 1 | CT | 18 | No | 1 | NA | 2 |
| 3e | Wellhead | PG&E | PG&E | Fresno | Mendota | Panoche | 1 | CT | 49 | Yes | 2 (*) | NA | 1 |
| 4a | NEO | PG&E | PG&E | Madera | Chowchilla | Chowchilla 2 | 16 | Recip | 49 | Yes | 3 (3/12) | NA | 2 |
| 4b | NEO | PG&E | PG&E | Tehama | Red Bluff | Rawson Junction | 16 | Recip | 49 | Yes | 2 (*) | NA | 2 |
| 5a | Panda | PG&E | PG&E | Solano | Suisun City | Lambie Indus Pk | 1 | CT | 45 | Yes | 2 (*) | NA | 1 |
| 5b | Panda | PG&E | PG&E | Solano | Suisun City | Lambie Indus Pk | 1 | CT | 45 | Yes | 2 (*) | NA | 1 |
| 5c | Panda | PG&E | PG&E | Solano | Suisun City | Lambie Indus Pk | 1 | CT | 45 | Yes | 2 (*) | NA | 1 |

Table 2, Status of PG&E Interconnection Process

| ##### Pro- ject | Generator | Utility |  | Status of Interconnection Study |  | GSFA signed? | Engineering Started by Generator and PG&E? | Construction Started by Generator and PG&E? | Natural Gas Inter-connection Complete? | Generator Installed ISO Metering? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ##### ID | Name | Elec. | Gas | Elec. | Gas | Yes/No | Yes/No | Yes/No | Yes/No | Yes/No |
| (a) | (a’) | (b) | (c) | (j) | (k) | (p) | (q) | (r) | (s) | (t) |
| 1a | CalPeak | PG&E | SCG | 3 (2/28) | 5 | Yes | Yes | No | No | No |
| 1b | CalPeak | PG&E | PG&E | 3 (1/26) | 3 (1/12) | Yes | Yes | No | No | No |
| 1c | CalPeak | PG&E | PG&E | 3 (1/26) | 3 (1/25) | Yes | Yes | No | No | No |
| 3a | Wellhead | PG&E | PG&E | 3 (4/30) | 4 | No | No | No | No | No |
| 3b | Wellhead | PG&E | PG&E | 3 (4/30) | 3 (1/12) | No | No | No | No | No |
| 3c | Wellhead | PG&E | SCG | 3 (1/30) | 5 | Yes | Yes | No | No | No |
| 3e | Wellhead | PG&E | PG&E | 3 (4/30) | 3 (3/30) | No | No | No | No | No |
| 4a | NEO | PG&E | PG&E | 3 (11/20) | 3 (1/16) | Yes | Yes | Yes | Yes | Yes |
| 4b | NEO | PG&E | PG&E | 3 (1/11) | 3 (5/31) | Yes | Yes | No | No | No |
| 5a | Panda | PG&E | PG&E | 3 (4/30) | 3 (3/23) | No | No | No | No | No |
| 5b | Panda | PG&E | PG&E | 3 (4/30) | 3 (3/23) | No | No | No | No | No |
| 5c | Panda | PG&E | PG&E | 3 (4/30) | 3 (3/23) | No | No | No | No | No |

See below for explanation of column headings.

Pacific Gas and Electric Company

Summer 2001 Generator Interconnection Status

Monthly Report to CPUC Required under AB 970 OII

6/1/2001 (continued)

Explanation of Columns in Table 1:

(a) Project ID:  There are eight generators, each with up to five projects.

(a’) Generator name.

(b) Electric Interconnection Utility:  either PG&E or Edison.

(c) Natural Gas Interconnection Utility:  either PG&E or SoCalGas.

(d) County of project.

(e) City of project.

(f) Substation where interconnection occurs.

** = One of the nine PG&E substations made available to generators for 3 year Sec. 851 lease and/or revocable license.

TBD = To be determined, generator has not yet decided on the exact interconnection point.

SCE = Is an Edison electric interconnection.

(g) Number of generating units.

(h) Type of generating units: Combustion turbine or reciprocating engine.

(i) Total gross megawatts of project.

(l) CPUC GO 131-D notice required?  (yes/no).

(m) Notice of Construction (NOC) status:

1 = NA = project does not require NOC.

2 = NOC expected [date]. * = The NOC filing date is dependent on the completion of the local agency’s CEQA/permit process for the underlying generation project.

3 = NOC filed, published, and posted [date]; protest period closes [date].

4 = NOC filed, published, and posted [date]; protest period closed [date] (no protests filed).

5 = NOC filed, published, and posted [date]; protest received [date] and responded to [date].

6 = Executive Resolution due [date].

(n) Status of Sec. 851 lease application and/or revocable license for use of PG&E substation land:

1 = Preparing lease and/or license.

2 = 851 lease application filed (date).

NA = project not on PG&E land.

(o) Status of Local Agency CEQA Review:

1 = Lead agency not identified yet.

2 = Lead agency identified and application filed.

3 = Application approved.

4 = Application denied.

Pacific Gas and Electric Company

Summer 2001 Generator Interconnection Status

Monthly Report to CPUC Required under AB 970 OII

6/1/2001 (continued)

Explanation of Columns in Table 2:

(a), (a’), (b) and (c) Same as Table 1.

(j) Status of Electric Interconnection Study:

1 = Awaiting request for interconnection study from generator including electric data for generating unit.

2 = Generator data received on (date), interconnection study results expected on (date).

3 = Interconnection study completed on (date).

4 = On hold at generator’s request.

5 = Not applicable, outside PG&E service territory.

6 = Original interconnection study completed by PG&E.  Additional interconnection analysis requested by generator and estimated to be complete on (date).

7 = Project canceled, to the best of our knowledge.

(k) Status of Natural Gas Interconnection Study:

1 = Awaiting request for interconnection study from generator including electric data for generating unit.

2 = Generator data received on (date), interconnection study results expected on (date).

3 = Interconnection study completed on (date).

4 = On hold at generator’s request.

5 = Not applicable, outside PG&E service territory.

6 = Original interconnection study completed by PG&E.  Additional interconnection analysis requested by generator and estimated to be complete on (date).

7 = Project canceled, to the best of our knowledge.

(p) Has the Generator Special Facility Agreement (GSFA) been signed? (This happens after the interconnection study is done and prior to engineering work and construction commencing.

(q) Has engineering work started?  (Likely both the generator and PG&E will share in the engineering work.)

(r) Has construction work started? (Likely both the generator and PG&E will share in the engineering work.)

(s) Has the natural gas interconnection been completed?

(t) Is the ISO required metering in place?