14mar01

co-op city

plan forward

| Item no. | Action required | Responsible party | Target completion date(s) |
| --- | --- | --- | --- |
| 1 | Capex – provide updated pricing numbers, including detailed scoping and schedule assumptions – i.e., what is and is not included. - Align to enron’s mark-up of latest development agreement termsheet. |  |  |
| 2 | “cap” – provide proposed cap on capex. - look at sensitivities on cost categories such as: major equipment, bop engineered equipment, construction bulks and labor, indirect costs, contingency, escalation, and profit (8%?). - prepare risk book. - Assess change in project schedule on the derivation of this “cap” number – i.e., change in cash flows. |  |  |
| 3 | O&M costs – provide updated pricing numbers, including detailed scoping assumptions – i.e., what is and is not included. - Align to enron’s mark-up of latest development agreement termsheet? - Align to enron’s mark-up of the latest o&m termsheet. - Must determine/provide what is enron’s cost to provide a “not-to-exceed” guarantee on the o&m contract. - Look at fixed component. - Look at variable component. |  |  |
| 4 | get latest updated read from GE as to sched and cash flow requirements for gas turbines. | enron |  |
| 5 | get latest updated read from hrsg vendors as to sched and cash flow requirements for hrsgs. | enron |  |
| 6 | Project schedule – need to assess following options: (note – co-op city to make funds application by early sep01; closing projected in oct01; with funds available in mid-nov01 timeframe. Note – 6 year lock-out provision by state). - Enron locks up gas turbines and hrsgs (?) now/soon by making required payments to GE and selected hrsg vendor, respectively; paid for by co-op city should project crater. - Co-op city locks up gas turbines now/soon by making separate deal with GE. Note – problematic with hrsgs; likely have to wait until funds are available in mid-nov01 timeframe. The hrsgs are now the critical path. - Enron “works” the gas turbines availability issue to meet the target schedule requirements, but no guarantees. The ordering of the hrsgs is delayed until funds are available in mid-nov01 timeframe. The hrsgs are now the critical path. - The ordering of both the gas turbines and hrsgs is delayed until funds are available in mid-nov01 timeframe. The gas turbines are the critical path. - Need to provide explanation as to why we no longer have a time period of 18 months from ntp to cod. |  |  |
| 7 | Project financials – i.e., what this deal means to co-op city in terms of earning/risk. Need to provide: - A listing of the components of the projected earnings/cash flows from ppa and asset management contracts. - A description of the derivation of the projected earnings/cash flow from ppa and asset management contracts. - A list of assumptions re: preceding cash flows. - A description of what happens to cash flows/revenues in year 5 when ppa satisfied/expires. - Provide worst case scenario numbers. Look at several cases. Look at for years 1 and 5 (other years?) E.g., if unable to run lm6000 in year 5, can only run lm2500, no merchant power sales/revenue – is debt service covered? |  |  |
| 8 | Prepare 2 page summary of deal | enron | By cob 16mar01. |
| 9 | Redraft of first 4 pages of development agreement termsheet. | Co-op city | After receipt of enron’s 2 page deal summary. |
| 10 | Provide comments on enron’s mark-up of latest development agreement termsheet. | Co-op city | By cob 15mar01. |
| 11 | Co-op city to present/review cogen “deal structure” to/with state agencies/banks/financing entities. | Co-op city | Target of early to mid-apr01. |
| 12 | New york state housing finance committee to provide termsheet of co-op city’s debt refinancing. To include/address cogen project? | N Y state | Target of mid-apr01. |
| 13 | Co-op city board to review refinancing termsheet, including cogen project. Make go/no-go decision on enron’s involvement. | Co-op city | Target of late-apr01. |
| 14 | Meeting with con-ed. Is load flow study needed? Commercial vs. technical aspects. |  |  |
| 15 | Geotech work required. Timing? |  |  |
| 16 | Conceptual design in support of permitting effort. - timing? - How to involve/pay for pb power’s work? |  |  |
| 17 | Preliminary design in support of prep of rfp for epc contract. - timing? - How to involve/pay for pb power’s work? |  |  |
| 18 | For cost plus fixed fee plus cap – use “daughter of electrobolt” contract. |  |  |
| 19 | Epc contractors – union labor: - develop list of firms with experience in ny city. - Meet with, discuss project and its requirements. - Decide on competitive bid or “select and go” approach. Has schedule and cost implications; need to assess. |  |  |
| 20 | Get emission info from GE for lm2500, lm6000 gas turbines. |  |  |
| 21 | Get bids from pb power for following work scope: - conceptual engineering in support of permitting. - environmental permitting. - Geotech. - Preliminary engineering in support of prep of rfp package for epc contract bid. - Prep rfp package (technical and commercial)for epc contract bid. - Evaluation/negotiation support of “pc” component of epc bid. |  |  |
| 22 | Confidentiality agreement between enron and co-op city. - status? |  |  |
| 23 | Confidentiality agreement between enron and pb power. - status? |  |  |
| 24 | Make sure that o&m estimate is consistent with project’s equipment lists and sizing. |  |  |

- Listing of what enron will do:

- Enron’s development effort includes:

- Conceptual engineering in support of permitting.  Includes:

- major equipment selection.

- Schematic plant layout.

- Preliminary engineering in support of prep of rfp package for epc contract.  Includes:

- Technical write-up, including:

- Plant description.

- Fueling systems.

- Building system.

- Environmental controls.

- Utility interconnections.

- Electrical one-line drawing.

- Site plan.

- General arrangement drawing.

- Mechanical equipment list.

- Electrical equipment list.

- Heat and material balances, with guarantees.

- Quality assurance/control plan.

- Preliminary project schedule.

- Engineering calculations?

- Architectural, civil, structural engineering?

- PFDs for critical systems?

- Project execution/contracting plan?

- Project organization charts?

- Asset management.

- No fee for asset management.

- Development of project, not including pre-ntp cash payments for major equipment (e.g., gas turbines, hrsgs).

- No fee for development efforts; enron will conduct at risk so long as enron gets asset management contract if project proceeds.

- Will assist in selection process of o&m contractor.

- Will provide oversight of activities of selected o&m contractor.

- No fee for oversight of activities of selected o&m contractor.

- Listing of what enron will not do.

- Enron can not be the O&m contractor (would violate accounting rules).

- Scope:

- Add one lm2500(dual fuel), with DLN burners, with fired hrsg (n.g. only).  With inlet chilling.  With water injection for NOx control on fuel oil.

- Add one lm6000 (dual fuel), with DLN burners, with fired hrsg (n.g. only).  With inlet chilling.  With water injection for NOx control on fuel oil.

- Confirm hp, ip steam, with no reheat?????

- Which model number of gtg is correct?  Sizing?  Pricing?  Schedule delivery dates.

- Fired hrsgs include SCR catalyst (for NOx) and CO catalyst in stacks.

- CEMS.  One system for both stacks?

- Two 100% (or 3 x 50%) fuel gas compressors at 700 psig.  Need to decide.

- Refurb existing 6 mw stg (bent rotor).

- Refurb one existing 330,000 lbs/hour high pressure (500 psig) rankine cycle boiler (leaking tubes).

- No refurb of other 2 existing 330,000 lbs/hour low pressure rankine cycle boilers.

- New control room for both new and existing power plant.

- DCS - for new and existing plant.

- SCADA - for new and existing plant?

- Parts storage for both new and existing power plant; to be located inside existing boiler-house where no. 3 boiler used to be.

- Upgrade existing fuel unloading station (for no. 6 fuel) so that it can also handle no. 2 fuel oil.  Upgrades toincludefuel pumps, purification (e.g., centrifuge, duplex filters), as required.  Located to southeast of existingboilerhouse.

- Existing n.g. connection/tie-in point located adjacent southeast corner of existing powerhouse.

- Existing switchyard/substation located near southeast corner of existing powerhouse.

- Proposed site has three underground condensate and circ water lines; 36 inches or 42 inches.  Potential obstruction?

- Extend existing crane rails to east over new cogen plant to allow use of existing 35 ton crane.

- Sufficient laydown, construction trailers, and construction parking located to north of new plant area.  Prior and current use as storage area for construction materials related to work at co-op city.  Cost estimate includes allowance for adjacent storage and construction laydown area.

- Convert one 750k gallon fuel tank (tank no. 25) from no. 6 fuel to no. 2 fuel oil.

- Transmission voltage equipment.

- High generating voltage equipment.

- Hp feedwater pumps.  6.

- Treated water pumps.  1.

- Raw water pumps.  2.

- Gt lo coolant pump.  4.

- Gt generator and gear lo coolant pump.  4.

- Gt generator coolant pump.  4.

- Fuel compressor coolant pump.  4.

- St and generator lo coolant pump.  2.

- St generator coolant pump.  2.

- Demineralized water tank.  1.  Size?

- Raw water tank.  1.  Size?

- Neutralized water tank.  1.  Size?

- Acid storage tank.  1.  Size?

- Caustic storage tank.  1.  Size/

- Gt lo fin fan cooler.  4.

- Gt generator fin fan cooler.  4.

- Chillers; for gtg inlet chilling.  Needed?????existing chillers will support gas turbine inlet chilling requirements.

- Fuel compressor fin fan cooler.  6.

- St and generator lo fin fan cooler.  2.

- St generator fin fan cooler.  2.

- Waste water treatment system.

- Station/instrument air compressors.  2.

- General plant instrumentation.

- Medium voltage equipment.

- Low voltage equipment.

- Miscellaneous equipment.

- Cost estimate excludes scheduled overtime and/or shift work.

- Estimate assumes that removal and relocation of existing underground utilities by others.

- Construction:

- Site prep, improvements, clear laydown areas, repair/add to existing fencing as needed.

- Piling.

- Concrete and grout.

- Structural steel.

- Architectural.

- Buildings:

- Turbine hall; i.e., just for gtgs, with hrsgs outside.  Or power island is to be enclosed similar to existing structures (concrete and masonry brick).  ?????

- Control room for both existing power plant and new cogen.

- New switchgear room.

- Locate “warehouse” inside area of former boiler no. 3 in existing boilerhouse.

- Painting.

- Mechanical piping.

- Insulation.

- Erect major equipment.

- Bop equipment erection.

- Electrical.

- Instrumentation.

- Construction indirect costs.

- New york labor and productivity.

- Utility interconnects, such as:

- Hp steam line.

- Make-up water/water treatment plant.

- Boiler water.

- Firefighting water.

- Cost estimate based on 1 x lm2500 and 1 x lm6000.

- Cost estimate includes escalation to mid-year????? 2002.

- Cost numbers/allowances for rehab work included “above line” in epc cost estimate?  Excluded?

- Cost estimates are +/- xx% accuracy.

- Plant shutdown for tie-ins to be scheduled for contractor’s reasonable convenience.

- Electrical tie-in to existing substation via insulated/shielded cable in open cable tray.

- Project site is assumed to be environmentally free.

- No “used” equipment allowed; financing constraint.  Must be new equipment.

- No new bridge cranes.  Extend rails for use of existing boilerhouse building crane.

- No makeup water treatment system.  Connect to existing system.  Also, during construction, need potable water trucked in?????

- No diesel fire pump.  No jockey fire pump.  Connect to existing underground fire hydrant system.

- No admin building.

- No machine shop.

- No guardhouse.

- No 250 kw diesel generator set.  Neither black start nor emergency diesel generator capability required for the cogen plant.

- No new auxiliary boilers (2 x 335,000 lb/hr).

- No capital spare parts.

- No rock excavation.

- No o&m costs included.

- Existing cooling tower will support new/proposed facility.

- In case where there is low steam demand but high power demand, existing condenser is large enough to handle excess steam dump.

- Need for interconnect fee?????