POLAND ACTIVITIES

weekly update

week of 22 –28 March‘99

| Activity/Project Name | # Developments |
| --- | --- |
| Power trading license | - Guarantee Agreement between Enron Poland and Enron Europe has been signed, and one copy was delivered to URE on 26th March. - A group of Members of Parliament want to change the President of URE because he accepted too high power tariffs raise proposed by distrib. companies. |
| Construction of the ENS plant | - Delay in civil works is still increasing, but DBA agreed to start two shifts work in the crucial areas. Installation of the auxiliary boilers has been started. Repair of the steam turbine shaft has been finished, we are waiting for final report. - Mayor of Gmina Leżajsk issued the Site Development Permit for the transmission line. Landowners have 14 days for appeals. - Met Arthur Andersen and Cameron to prepare our standpoint on details of the transmission line ownership transfer to Rzeszów DisCo (RZE). Meeting with RZE will be held next week. - Arthur Andersen will complete the auditing of ENS’ books on 26.03, then all documents will be prepared for approval by the Supervisory Board. |
| Privatization – generation sector | - Summarised information on selected “autogenerators” (7 companies) was prepared and discussed. After the first direct contacts, one company (Debica) has been given up, six left. - KGHM (one of the 6) announced that they are going to sell-off their non-copper businesses and assets. In spite of on-going changes in the KGHM Management Board, it was decided to contact them urgently by sending a letter. - Met the Technical Director of Polaniec PP to discuss the latest developments in the power sector and Polaniec. Eastern Generation seems to be Enron main competitor for acquiring of the plant major stake. |
| Privatization – distribution sector | - No new developments |
| British Steel | - No new developments. |
| Power peaking tender – (new built ) | - No new developments. Monitoring the review process at PSE. |
| Power peaking tender – (import ) | No new developments. |
| Peaking tender options (interruptible power export) | No new developments. |
| PPA securitization | - Ministry of State Treasury requested us to prepare an offer to solve the problem of long term contractual obligations of PSE. |
| POGC cooperation | - swaps: no new developments. - know-how exchange: no new developments. |
| Ukraine gas import | - Met POGC on Thursday and they seem to be losing interest. We will be deciding how to go forward in the next few days. |
| Options on gas supply Bartimpex cooperation |  |
| Coal trading | - No new developments. |
| Enron Energy Services | - The Ministry of Defense (MoD) confirmed their interest to enter into a framework agreement with Enron on a concept of taking over their existing heating & utilities facilities. Meeting with MoD to discuss a framework agreement concept is scheduled on March 30th. The issue has been discussed with EES this week. Awaiting final response from EES on March 29th. |
| Flue-gas desulphurisation | - The draft of MOU with Costain/Skawina was presented to Legal Dept., first comments have been received back. |
| Low Btu gas | DISCONTINUED. |
| Crude oil product | No new development |
| Lithuania – Poland Power Interconnection | LE has decided to open the deal up to tender again. Enron will make a trip to Vilnius to follow up on past bid and consider whether it wants to continue pursuing this opportunity. |
| Technical and know-how support to MoT and PSE on the development of the competitive electricity market in Poland – Project Ruby | - No new developments. |
| Administration | - No new developments |