| #### +HUMAN RESOURCES/ADMINISTRATION |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Obtain ISO 9000 standards for systems, policies and procedures | 30 June | # GET | Contact ISO Office | Don Roberts - SGS Earl Curtis - X - 55705 | Earl Curtis is on vacation until the 26th. Will follow-up on the 27th |  |
| 2 | Establish local insurance/benefits program | 30 June | TBM | Draw an insurance package for the locally hired employees | David Miles LFUAE 06-5730050 | Draft package received from LFUAE – to be reviewed |  |
| 3 | Arrange passport-sized photos of all Enron employees and their families to be available in each personnel file. | 27 June | TZK |  | All employees and their families | In progress. |  |
| 4 | Install electrical sockets in conference room | 30 June | GET | Get quote from CMC | Edwin/John | In progress CMC will do the job. |  |
| 5 | Gaza Training | 30 June | GET | Establish training materials on Leadership and Teambuilding | Sabira - MET Tel. 2670900 | Training material finalized. Equipment for the Interactive work shop ordered though Middle East training. |  |
| 6 | Visa - Hassanein | 24 June | GET | Check with American Consulate | Mary Eileen Earl | Meeting set-up on Saturday |  |
| 7 | Sadaf bid input |  | GET/TBM |  |  |  |  |
| 8 | Establish savings plan | 1 July | TBM |  | Lawrence White (050) 6958158 | Initial meeting held on 12 June. Awaiting receipt of package. |  |
| 9 | Order lamination machine (ID size to A3 capability | 30 June | ###### GET | Solicit quotations | Bright Stationery Emirates Trading |  |  |
| INFORMATION TECHNOLOGY (IT) |  |  |  |  |  |  |  |
| 1 | Layout for Voice & Data Network | 30 June | ###### GPL | Acquire the appropriate software for the design of network. |  | Completed | Sony computer contains the software and is now used to make the layout diagrams. |
| 2 | Alcatel system compatibility with Corporate Lucent system | 30 June | ###### TBM | Facilitate contact between Houston tel. Rep. and local alcatel rep., Marie Newhouse, Kathy Link, Alcatel re. (Ashok Maheshwari) |  | Meeting set-up on Wednesday, 21 June. | Alcatel is to submit a proposal to Enron M.E. on the internetworking of voicemail system. Quotation expected on 26 June |
| 3 | Program telephones with AT&T access | 30 June | ###### GPL | Contact Alcatel to determine capability | Ashok Maheshwari 655 8637 | Ongoing.Calcatel to receive response from main office about program. |  |
| 4 | Prepare 4 kits of loaner mobile phones + documentation | 30 June | ###### GPL | - Order 4 timeport mobile phones - Purchase kits - Order SIMM cards |  | Documentation ongoing |  |
| 5 | Call forwarding on Jebel Ali office numbers | 30 June | ###### GPL/MP | - Convert multiline to single line - Arrange call forwarding: 883-6550 to 331-8717 883-6552 to 331-8487 |  | OSC has requested Etisalat for the conversion of this line |  |
| 6 | Prepare info to sell video conference equipment | 30 June | ###### GPL | - Establish price of "new" system - Prepare ad to sell it |  |  |  |
| 7 | Set-up PC & scanner/printer for Admin. Asst. at 3112 | 30 June | ###### GPL |  |  |  |  |
| 8 | Set-up scanner/printer at 3117 | 30 June | ###### GPL |  |  |  |  |
| 9 | Documentation of Remote Connectivity | 28 June | ###### GPL | For modification |  |  |  |
| #### PUBLIC RELATIONS |  |  |  |  |  |  |  |
| 1 | Convert videotape to NTSC | 24 June | GET |  |  | Tape to be received on Sat., June 24 |  |
| GOVERNMENT RELATIONS |  |  |  |  |  |  |  |
| 1 | Design database of government and private sector contacts | 30 June | TBM/SDM |  | Jeff Pena X - 56375 | In progress |  |
| 2 | Orientation for new U.S. Embassy Commercial Officer | TBD | TBM |  |  |  |  |
| #### TRAINING |  |  |  |  |  |  |  |
| 1 | Coordinate regional training | TBD | # GET/TBM |  |  |  |  |

Note:  Kindly provide your updates next Wednesday, June 28.