## Slide 1: PROPOSED APPROACH FOR SIZING THE OPPORTUNITY
Exhibit 1
Conduct initial market sizing and identify the short list of market development drivers
Develop scenarios and estimate opportunity accessible to Enron
Timing
4 weeks
2 weeks
Key activities
  Build detailed opportunity fact base (segmentation of players, size, outsourcing propensity, back-office spend, transaction economics, etc.)
    McKinsey experts and research sources
    Enron experience and learnings
    External experts, customer interviews, and data sources
  Determine size of market opportunity
    Top-down estimates based on potential buyers and adoption rates
    Bottom-up estimates based on transaction economics, savings potential, and volume flow
    Comparative estimates based on financial services and business processing outsourcing
  Disaggregate market opportunity into relevant segments
  Identify key market development drivers and outline first-cut key beliefs and implications
  Estimate market growth over time
Progress review
Final review
End product
  Size of the market with segment and growth details
  Assessment of the key drivers of market development
  Develop business scenarios (e.g., opportunity size and timing) based on the key market development drivers
    Best case, worst case, and most likely
    “What you have to believe” for each scenario
  For each key segment develop a rough first-pass Enron business case
    Economic value
    Cost to acquire and serve
    Adoption rate
    Bottlenecks (e.g., credibility, trust, etc.)
  Assess implications for moving forward with the business
  Business scenarios based on drivers
  Estimated Enron share of the prize
  Recommendations for the business
Notes: <number>
txho/ENX126/11022am ppt

## Slide 2: PROPOSED TEAM STRUCTURE
  Provide thought and problem solving leadership
  Assure pace and quality of end products
  Ensure access to McKinsey resources as needed
McKinsey expert resources as needed
  Business Technology Office
  Financial Institutions Group
  Operations Practice
  Petroleum Practice
  Electric Power and Natural Gas Practice
Exhibit 2
Steering Committee
  Greg Piper
  Sally Beck
Engagement Team
  1-2 part-time Enron resources as required
  Engagement manager
  2 associates
  Lead day-to-day problem solving activities
  Drive progress
  Critical analysis
  Synthesize learnings
  Review/syndicate with Steering Committee
  Suzanne Nimocks
  Arshad Matin
  Scott Robinson
  Adolfo Montesinos
  Provide access to Enron knowledge and data
Notes: <number>
txho/ENX126/11022am ppt