## Slide 1
ERCOT Program Mock Market Approach Nov 15, 2000

## Slide 2
Introduction
Beginning June 2001, retail choice will be introduced to the ERCOT service area. Accompanying this are a number of physical and wholesale market changes:
Physical
Wholesale
Retail
Present
..2002
Single control area. SCE centrally calculated by ERCOT ISO which then allocates regulation requirements to QSE control centers.
Single centrally operated market for ancillary services. Bi-lateral energy contracts spanning entire control area seamlessly.
Retail choice. All consumers (other than those of opt-out muni’s/coop’s) free to choose electricity provider irrespective of geography (limit 5% during pilot).
Pilot: June 2001
These transitions will be rehearsed and refined during the mock market.
10 interconnected control areas. Each regulating its own frequency and ACE.
10 individual energy &
ancillary service markets.
Reciprocal arrangements for inadvertent exchanges.
Consumers tied to retail electricity provider by geographic situation.

## Slide 3
Mock Market Objectives
In order to increase the likelihood of a successful transition in the physical, wholesale and retail areas, a mock market will be conducted during April and May 2001.
The mock market is a functioning, interactive simulation of many aspects of ERCOT market operation. Its objectives are to:
  Prove the end-to-end operation of the new market processes, organizations and technologies.
  Provide ERCOT and mock market participants the opportunity to witness various simulated market operations, thus setting expectations for subsequent go-live.
  Allow participants to rehearse their responsibilities during simulated market operation.
  Allow participants to test their own responses to retail choice requirements:
    Organizational (e.g. new or changed jobs)
    Process (e.g. new bidding & scheduling processes)
    Technology (e.g. new billing or generation commercial management systems)
The mock market will be mandatory for participants who wish to be involved in the pilot on 6/1/2001. Performance during the mock market will provide a demonstration of readiness for the pilot in June 2001.

## Slide 4
Mock Market Approach
The mock market will be conducted in two stages. The first stage will simulate the physical, wholesale and retail environments. The second stage will interact with the live physical environment and will execute new retail and wholesale functions against real data in parallel with the existing functions:
The parallel stage in particular will coordinate with early frequency control testing and consumer meter conversion activities (the latter being conducted at the same time as the mock market).
April 2001
2
May 2001
9
16
23
30
7
14
21
28
Simulation 1 Stage
Parallel Stage
Simulation
2 Stage

## Slide 5
Mock Market Simulation Stage
Each mock market stage will treat processes and information differently. For the Simulation Stage:
Processes
Mock Market Characteristics
Mock Market Information
Physical
Wholesale
Retail
The physical system will be simulated by means of a Dispatcher Training Simulator (DTS) which mimics the physical network, its dynamics (asset behavior) and its events (generation, outages, loads) from the perspective of the ERCOT EMS.
The DTS will be driven with an accurate static and dynamic wholesale network model. Any events will be scripted in accordance with scenario. Any market interaction will be according to participants (see below).
New wholesale processes will run under simulated conditions. In order to facilitate new entrants participation, load will be allocated to mock market REP’s. Those aggregates will have characteristics and history sufficient for REP’s to model their usage patterns etc.
Each scenario will describe forecast conditions and actual events (which will be revealed as they happen). Participants will behave according to conditions fabricated for each scenario (e.g. demand, weather, outages) and will submit schedules and bids and “act” accordingly.
Affiliate REPs responsible for majority of load. Simulated switching of consumers from incumbent to new entrant will be tested.
REPs will be given the opportunity to switch consumers for the purpose of allocating load.

## Slide 6
Mock Market Parallel Stage
For the Parallel Stage:
Processes
Mock Market Characteristics
Mock Market Information
Physical
Wholesale
Retail
The ERCOT EMS will interact directly with the real physical system (via participant EMS or SCADA). The environment will mimic that of early frequency control tests (stage 4).
All inputs and outputs will be real.
New wholesale processes will run under real conditions. Only those REP’s with existing consumer relationships will be permitted. Although wholesale statements will be issued existing financial mechanisms will continue to be employed (including those for inadvertent exchange)
Participants will behave according to actual conditions and will submit schedules and bids and “act” accordingly.
All load must be associated with the current load serving entity, hence no switching can take place.
ERCOT will pass on actual metered usage information for consumers to the responsible load serving entity.

## Slide 7
Simulation Data DTS Configuration
The following diagram illustrates the DTS configuration for the mock market:
ERCOT
EMS
(POS)
EMS
QSE’s
EMS
TDSP’s
DTS
T&D Status Simulation
Generation Signals (Portfolio Level)
Generation Status Simulation

## Slide 8
Market Registration
Market
Registration
Process Description: Market registration includes the processes of capturing market participant, market user, market asset and electric service identifier information and relationships (both initial information and updates). Registration activities are performed as needed rather than according to a schedule.
Assumptions:
Use ‘real’ data where possible
  The Participant and Asset Registration processes are being conducted ‘for real’ starting Nov 15 and running through March 1; this data will be used to populate the production system which will be used for mock market.
  Participant information will be “real” including present and expected future participants; Meter information will be “real” including generation, zonal and wholesale delivery point meters
  ESI-Ids are being captured in mock conversions starting in January; the intention is to use the output of one of these mock conversions to populate the registration database for the simulation stage of the mock market
For the simulation stage, some relationships will be contrived for purposes of the mock market. For example, between new entrant REP’s and consumers, between resources and PGCs, between QSEs and PGCs, and between REPs and QSEs
Full simulation of ESI-ID switching will not take place - REPs will initiate switch with an 814, but the remainder of the process will be manipulated within ERCOT’s systems
Register Market
Participant
Register Market
User
Register Market
Asset
Register Electric
Service Identifier

## Slide 9
Market Operations
Process Description: Market operations includes the processes of forecasting load, losses, congestion, administering balanced schedules and managing TCR and ancillary services markets. These processes are performed during the day ahead, adjustment and hour ahead periods.
Assumptions
The Market Operations processes will be conducted for each stage (simulation & parallel)
ERCOT will forecast load, losses and congestion based on the story-line or actual conditions.
ERCOT will allocate ancillary service obligations based on actual or specially defined QSE-Customer relationships (and the actual history of those aggregate consumers)
QSE’s will submit balanced schedules, ancillary service self-supply schedules & ancillary services bids according to the supplier/customer relationships and customer history
ERCOT will validate schedules and execute the ancillary services markets through a number of iterations with the QSE’s.
QSE’s will be able to use their automated scheduling/bidding tools to test functions and outputs if they choose.
Forecast Load
& Losses
Administer Balanced Schedules
Administer TCR
Market
Forecast
Congestion
Market
Operations
Manage Market
Bids
Procure & Price
Market Services

## Slide 10
Power System Operations
Process Description: Power System Operations includes real-time processes which match supply with demand and maintain grid system security through monitoring and control of power system assets, use of ancillary services and procurement of balancing energy.
Assumptions
The Power System Operations processes will be conducted multiple times during both stages (simulation & parallel)
During the simulation stage,
  The processes will utilize a Dispatcher Training Simulator (DTS) to simulate the physical system in concert with the scenario conditions and events.
  Participants will be expected to behave in concert with the scenario conditions (e.g., planned outage communication or emergency procedures).
During the parallel stage, the processes and participants will utilize data from the actual electrical system.
Message Exchange will be utilized to communicate with QSE’s in order that they can test downstream capabilities (e.g. Commercial Management).
Verbal communications will be utilized where appropriate for completeness of protocol and procedural testing (e.g. manual communications during link failure).
Monitor & Control
Power System
Create Daily
Operations Plan
Manage Near-Term
System Frequency
Perform Real-Time
Network Analysis
Manage Real-Time
System Frequency
Perform Study
Network Analysis
Power
System
Operations

## Slide 11
Load Profiling, Data Acquisition & Aggregation
Assumptions
For both simulated and parallel stages, the load inputs will be at a retail customer level
Load Profiling, Data Acquisition and Aggregation processes will be conducted for the period of each scenario.
It’s anticipated that ESI-Ids, historical usage and static profiles and adjustment factors will be available from data conversion.
For the simulation stage,
  The usage at ESI-ID level will be fabricated using the historical usage provided during conversion as a starting point, and applying a load ratio relative to the system load in the scenario (no 867 inputs required from utilities)
  During the simulation stage, pseudo-metered wholesale data will be available from DTS
During the parallel stage,
  the actual 867s from the utilities will be used as the load inputs
  During the parallel stage, actual metered wholesale data will be available from TDSP’s and PGC/IPP’s.
Load Profiling
Data
Acquisition &
Aggregation
Create Profile
Models
Acquire & Manage Measurement Data
Aggregate Measurement Data
Process Description: These processes create static profiles for cumulative meter data conversion, collect generation, zonal and load metered data (interval and cumulative), apply actual profiles and losses and allocate unaccounted for energy (meter inaccuracy, profile errors etc.) to arrive at a whole picture for energy flow throughout the system.

## Slide 12
Settlements, Billing & Financial Transfer
Assumptions
During the simulation stage:
  Wholesale settlement will be conducted for the period of each simulation scenario based on the fabricated meter information.
  Initial and final statements will be issued.
  Financial Transfer processes will not be conducted.
During the parallel stage:
  Wholesale initial settlement will be conducted for ERCOT internal testing purposes. Results will not be meaningful since the parallel stage will not be conducted for whole 24 hour periods.
  Real settlement will continue to be based on payback of inadvertent flows
Settlements,
Billing &
Financial
Transfer
Settle for Market
Services
Bill for Market Services
Financial
Transfer
Process Description: These processes settle and charge for ancillary services and real-time energy (balancing, OOME, RMR). They settle for inter and intra-zonal congestion management and provide the billing determinants for TDSP access fees. Settlements, Billing and Financial Transfer processes are conducted at various times after real-time between three days (initial) and six months (true-up).

## Slide 13
Issues outstanding for investigation
Simulation stage:
quality/completeness of ESI-ID and associated historical usage that will be available from mock conversions
need to provide visibility into the DTS in real time
getting wholesale level data (eg generation) from the DTS to package 2 for settlement
ability to deliver the necessary training in time for the start of this stage
Parallel stage:
ability to manipulate balancing energy bid stack in order to control the amount of regulation which is required, and hence the amount of inadvertent
ability to involve ‘new’ QSEs, i.e., QSEs representing entities other than existing control areas: need for dual telemetry links (to both control area utility and to ERCOT); impact on commercial arrangement between the generator and the utility.