## Slide 1: Doorstep Update December 14, 2000

## Slide 2: “Institutionalized” Doorstep
MRM and Global Risk Operations prepare Doorstep schedule - staffing is planned one quarter in advance
RAC Compliance sends planning notifications to participants
Doorstep is 2-5 days; review and briefing to Sally/Ted immediately upon return;
Communication to Business Unit Head, CAO, Head Trader, Business Unit Controller to finalize the report and agree on resolution target dates
Findings (significance - red/yellow/green) , target dates, and accountable parties are input into database
Automatic notifications to accountable parties 30 days in advance, and on the target date
RAC Compliance sends e-mail past due notices to accountable parties and to MRM (C.Schultz) and Global Risk Ops. (S.Wilson)
Review by MRM and Global Risk Ops of findings resolution

## Slide 3: Doorstep Update December 14, 2000
Appendix:
Open Items by Office

## Slide 4: Calgary Open Issues
Inadequate Documentation & Procedures
Observation: Foreign currency risks are managed by the respective trader within each of the trading portfolios, instead of aggregated at the FX/IR desk in Houston.
Action Plan: Issue noted for several locations - being addressed as a global issue.)

## Slide 5: Chicago ENA and Enovate Open Issues
Inadequate documentation & Procedures
Observation: Credit process between Houston Credit Group and Chicago office is not appropriately defined.
(closed????? Frank Hayden to tell us)

## Slide 6: Chicago Metals Open Issues
Credit Acceptance, Assessment & Material Contract Review
Observation: Currently credit reporting is not complete and does not include full exposure reporting, nor do traders receive daily up to date credit information. This is a Metals issue in all offices in North America. New York is in the process of hiring someone to handle the credit function. However, immediate action needs to take place to ensure immediate improvements.
Action Plan: Being addressed as global Metals issues.
Inadequate Documentation & Procedures
Observation: No master agreements with counterparties.
Observation: Sales agents are used in several foreign locations without written contracts.
Action Plan: Being addressed as global Metals issues.
Systems Environment & Infrastructure
Observation: Telephone lines are not taped and traders execute deals from home.
Observation: Stand alone access database does not interface with the AS 400. Additionally, the AS 400 does not give all needed information.
Action Plan: Some action taken; to be addressed.

## Slide 7: Frankfurt Open Issues
Management Reporting
Observation: Frankfurt counterparty exposure & P&L not easily tracked separately for management review purposes.
Action Plan: MRM is educating commercial and energy operations so they understand need and begin adequate reporting.

## Slide 8: London Open Issues
Credit Acceptance Assessment & Material Contract Review
Observation: Currently unregulated exchanges such as Nordpool & the APX are assumed not to carry credit risk
Observation: UK Power/Continental Gas/Global Products - Lack of Master Agreements in place for large number of counterparties.
Observation: The confirmation process for Pulp & Paper trades is slowed by the Credit review being performed by Houston Credit. (CHECK WITH MIKE)
Observation: No established procedure in place to provide evidence of Legal and Credit review of applicable terms and conditions for Pulp & Paper transactions. (CHECK WITH MIKE)
Observation: Coal/P&P/Weather/FX/IR - Lack of Master Agreements in place for a significant number of counterparties. Futhermore, the majority of trades are documented on counterparty paper or broker or confirmations.
Execution, Settlement & Cash Management
Observation: No automated process exists to ensure Pulp & Paper Settlements is aware of all transaction settlement dates.

## Slide 9: London Open Issues Continued
Inadequate Documentation & Procedures
Observation: Stand-alone models have not been independently reviewed and formally approved the Eastern spread option deals.
Observation: No formalized process is in place for monitoring the receipt and execution of confirmations for Pulp & Paper trades.
Observation: No formal policies and procedures are in place for hedging and monitoring FX exposures across the company; consequently not all exposures are effectively managed by the FX trading desk.
Observation: No formal procedures exist to ensure that deals maintained outside of the main deal database systems and that manual adjustments made to the face of the database are captured into the Credit Aggregation System on a timely basis for Credit Risk

## Slide 10: London Open Issues Continued
Position Capture & Management
Observation: No front-end deal capture process for UK & Continental Gas Trading:1) Documentation inputs deals into system via Gas Trading written log; 2) No subsequent review of system deal ticket
Observation: No front-end deal capture system for Global Products trading - Risk Management inputs deals into system via manually completed deal tickets.
Observation: Trade capture issues exist for Coal trading: 1) Transactions not entered into risk systems on a timely basis; 2) Deal information incomplete on deal tickets; 3) No front-end deal capture system exists; handwritten deal tickets entered by Risk Management into TAGG and Right Angle; 4) Deals manually input by Logistics into scheduling spreadsheets.
Observation: Invoicing for physical Coal deals is performed outside of Right Angle using Excel spreadsheets as Right Angle does not have functionality to include the details which clients require on invoices.

## Slide 11: London Open Issues Continued
Systems Environment & Infrastructure
Observations: Continental Power deal database (Enpower) does not satisfy power scheduling needs resulting in the use of stand-alone spreadsheets for scheduling purposes.
Observation: No standard Documentation system exists for all products.
Observation: Trades are conducted on mobile phones on a limited basis.
Observation: Deal entry fields in Enpower are completely manual and can be overwritten subsequent to initial deal input.
Observation: FX exposure is difficult to monitor for those products using TAGG due to the inability of TAGG to process non-US$ exposures.

## Slide 12: Oslo Open Issues
System Environment & Infrastructure
Observation: Foreign currency risks are managed by the respective trader within each of the trading portfolios, instead of aggregated at the FX/IR desk in Houston.

## Slide 13: Panama Open Issues
Execution, Settlement & Cash Management
Observation: Physical product is being dispatched prior to confirmation being sent to and agreed by the counterparty.
Action Plan: Waiting to resolve future office operations.
System Environment & Infrastructure
Observation: No taped trader phone lines.
Action Plan: Waiting to resolve future office operations.

## Slide 14: Sao Paulo Open Issues
Position Capture & Management
Observation: Cuiaba WTI positions are not centrally managed with global crude positions.
Action Plan: Waiting to resolve contractual outcome; position is in liquids book, VaR and P/L is in southern cone power and gas book.
System Environment & Infrastructure
Observation: Commercial phone lines are not taped.
Action Plan: To be determined.

## Slide 15: Singapore Open Issues
System Environment & Infrastructure
Observation: A significant number of trades take place on non-recorded phone lines via cellular phones or home phones.
Action Plan: Working on it.

## Slide 16: St. Louis Metal Open Issues
Credit Acceptance, Assessment & Material Contract Review
Observation: Overall credit function is weak.
Action Plan: Being addressed as global Metals issues.
Inadequate Documentation & Procedures
Observation: No Master agreements with counterparties.
Observation: Sales agents (fewer than 5) are used in several foreign locations without written contracts.
Action Plan: Being addressed as global Metals issues.
System Environment & Infrastructure
Observation: Telephone lines are not taped and traders execute deals from home.
Observation: Stand alone Access database does interface with the AS 400. Additionally, the AS 400 does not give all needed information.
Observation: Certain coordination functions are still being performed by Logistics personnel in St. Louis, mainly due to the system’s limitations of the AS 400. This point is mentioned separately due to the segregation of issues problem but the follow-up is the same as the observation above.
Action Plan: Being addressed as global Metals issues.

## Slide 17: Sydney Open Issues
Inadequate Documentation & Procedures
Observation: Strategic Residue Auction (SRAs) positions are not captured in Enpower and are valued in Excel pivot tables. Also, valuation of SRAs have subjective inputs which need to be reassessed on a more active basis.
Action Plan: Positions will be put into RisktRAC for daily monitoring by end of Q1 2001.

## Slide 18: Mariner Open Issues
Inadequate Documentation & Procedures
Observation: The company does not have the ability to calculate its net open volumetric position on a daily basis.
Segregation of Duties & Functional Responsibilities
Observation: The Vice President of Marketing executes derivative contracts, manages the Company’s hedging position, confirms these contracts and produces management reports on the Company’s hedging position.

## Slide 19: Seoul Open Issues
Credit Acceptance Assessment & Material Contract Review
Observation: Delivery requirements under term contracts have no out of Force Majeure if volumes are unable to be purchased.
Observation: Foreign counterparties are not subject to standard credit investigations performed by the Finance Department
Inadequate Documentation & Procedures
Observation: An estimate to actual review is not documented to show the Company’s projected contract price with the actual contract price and the resulting P/L impact.
Management Reporting
Observation: Projected income/loss is not included in the 12-month rolling report.