## Slide 1: Texas Choice
RMS 1.4 Migration Workshop
Strawman Plan
October 16, 2001

## Slide 2
Meeting Results
On October 16, 2001, market participants representing TDSPs, ERCOT, affiliated and non-affiliated Retailers and PUCT Staff met to develop a strawman for 1.4 migration plan.
This following pages represents the major points and results from this meeting.
Meeting participants selected Option B Rev 01 as strawman for an integrated time line for market opening.

## Slide 3: Agenda
Review Meeting Agenda and Objectives
Briefly Review Four Options
Suggest Other Options
Detail Review of Each Option
Select the Best Option by 2:30pm Today
Wrap-up
Adjourn at 3:00 pm Today

## Slide 4
Objectives
Produce integrated time line for market opening which will be voted on at RMS October 25, 2001 meeting.
    Today’s Objective: Select ONE 1.4 Migration Plan Option as strawman
    Tomorrow’s Objective: Develop mass customer move time line as strawman

## Slide 5: Option A
Move to Texas SET version 1.4 during weekend of 12/15/01
ERCOT shuts down their 814 in-bound queue for 7 calendar days starting 12/8/01
7-days allows completion of 814 cycle before conversion
TXU TDSP attempts to develop a modified 867.03 so they can submit 867.03 to support settlements
TXU TDSP has a 3 week moratorium on switches and billing their trading partners
Remainder of MPs move to version 1.4
Notes: <number>
<footer>
<header>
<date/time>

## Slide 6
Option A
Starting December 3rd, MPS agreed to reduce the volume of mass ESI ID changes.
ERCOT turns off all TDSPs in-boxes and not just TXU’s

## Slide 7: Option A
Advantages
Disadvantages
Allows 2 weekends if migration experiences problems
Majority of MPs can move during this weekend
Migration occurs 2 weeks before mass customer move begins
TXU TDSP might not have the resources or time to create a modified 867.03
TXU TDSP has a 3 weeks moratorium on all EDI transactions
TXU moratorium creates backlog of usage transaction (1.5 million) and ESI Id transactions (500k).
TXU TDSP can not bill their trading partners until January 2, 2002.

## Slide 8
Option A

## Slide 9
Option A Rev 01
Moratorium between 12/14/01 – 01/02/02
    814; Full market moratorium on all switch initiated transactions. TDSPs might be able to continue sending 814.20
    867; TXU TDSP does not sending in 867.03 until 1/2/02. Wholesale Settlement estimated for 10 day (13/14/17/18/19/20/21/26/27/28).
    AEP, Reliant, TNMP & Entergy move v1.4 & no backlog impacting Settlements
    810/820; TXU TDSP can not bill their trading partners because lack of 867.03 v1.4 and can’t produce 810 v1.4

## Slide 10
Option B
Move to Texas SET version 1.4 during weekend of 12/22/01
ERCOT shuts down their 814 in-bound queue for 7 calendar days starting 12/15/01
7-days allows completion of 814 cycle before conversion
TXU TDSP has 2 week moratorium on all EDI transactions
Remainder of MPs move to version 1.4

## Slide 11: Option B
Allows 1 weekend if migration experiences problems
Majority of MPs can move during this weekend
Move is 1 week before mass customer move begins
TXU not required to create 867 modification
TXU TDSP has a 2 week moratorium on all EDI transactions
Migration is immediately before a holiday potentially impacting resources
TXU TDSP will have 3 days of meter reads in backlog potentially impacting settlements
Advantages
Disadvantages

## Slide 12
Option B

## Slide 13
Option B Rev 01
TXU TDSP and their Pilot Trading Partners must
work out invoicing arrangements for 5 business
days during the time period of the moratorium
Other TDSP can issue 810’s on the 12/26/01
Point of no return is December 1 (needs
to be validated by MPs); Go or No Go.
Clearly defined criteria to open the market must be defined. ERCOT Staff proposed strawman at today’s ERCOT Board Meeting.
Market agrees to reduce ESI ID maintenance transaction volume starting December 3rd
CRs urged to plan Jan’ 02 switch volume because of 2-1/2 week moratorium

## Slide 14: Option B Rev 01
Advantages
Disadvantages
If market delay, TX TDSP moratorium becomes longer
ERCOT turns off all TDSPs mail boxes
TXU can’t send 867/810’s for 5 days
TXU TDSP has a 2 week moratorium on all EDI transactions
Migration is immediately before a holiday potentially impacting resources
Allows 1 weekend if migration experiences problems
Majority of MPs can move during this weekend
Move is 1 week before mass customer move begins
TXU not required to create 867 modification
Gives ERCOT extra week to test 1.4 code

## Slide 15: Option B Rev 01
Advantages
Disadvantages
Moratorium will prevent the customer of opting out of Pilot loosing the ability to revert back to the TDSP
Switches cannot be effectuated during the moratorium resulting in the inability of customers switching

## Slide 16
Option B Rev 01

## Slide 17: Option C
Move to Texas SET version 1.4 during weekend of 12/29/01
All MPs move to 1.4 together
ERCOT shuts down their 814 in-bound queue for 7 calendar days starting 12/21/01
7-days allows completion of 814 cycle before conversion
No fall back weekend if migration has problems
AEP’s Texas release also has Ohio & Virginia changes that must be in by 1/1/02.
8

## Slide 18: Option C
No major transaction moratorium for TXU TDSP
Allows more testing or recovery time if Flight 1001 late
Moratorium could correspond with mass customer move
No fall back weekend if there are problems
If 1 TDSP or ERCOT has problem market is directly impacted
Probably fix problems in production when there is now 10 million ESI ID compared to around 12% of ESI IDs in the pilot
Possible resource constraint because of holiday weekend
Advantages
Disadvantages

## Slide 19
Option C

## Slide 20: Option D
If pilot continues past 1/1/02, TDSPs bill at bundled rates until migration to open market
Pilot caps continue
Still must select Option A, B or C for migration
TXU TDSP moratorium on transactions is gone

## Slide 21: Option D
Allows more testing or recovery time if Flight 1001 delayed
Less resource constraints
TXU TDSP could reprogram their pilot release to include 1.4 version eliminating transaction moratorium
Decision date to continue pilot must be made by December 15
Decision date for migration must be made two weeks before migration date
AEP TDSP has integrated Ohio & Virginia changes for 2002 with Texas 2002 changes. AEP must reprogram their 1/1/02 release
Advantages
Disadvantages

## Slide 22
Option D

## Slide 23: Next Steps
RMS Approves 1.4 Migration Plan at October 25th meeting.
Communicate Migration Plan to TAC, ERCOT Board and all MPs.
Develop, approve & publish Go-No criteria before December 1st decision point
TXU TDSP & ERCOT investigate approaches to avoid 867.03 5-day backlog

## Slide 24: Wrap-Up
17