## Slide 1
Enron North America SAP Controls Project
Project Timeline
May 1, 2000
Business Risk Management

## Slide 2: Process Flow
Standard SAP
Processes &
Functions
(Common Design)
Custom
Business Unit
Processes &
Functions
Custom
Business Unit
Processes &
Functions
Process &
Functions
Outside
SAP
Process &
Functions
Outside
SAP
Overall Process Flow
Outside SAP - Manual processes or processes handled by another application.
Custom Processes & Functions - SAP functions customized to meet the needs of the business process.
Standard SAP Processes & Functions - Standard processes that are delivered by SAP.
Enron North America
Scope of Work

## Slide 3: Process Components
Proposed In Scope
  Detail Review & Analysis
  A/P and Cash Disbursements
  A/R and Cash Receipts
  Bank Accounts and EDI
  Intercompany Transactions
  High Level Review to Determine Extent
  of Utilization
  Cash Flow Forecasting and Reporting
  Planning and Budgeting
  Cost Center Reporting and Allocation
Out of Scope
  Capital Budgeting
  Cash Management and Investments
  Asset Acquisition to Retirement
  Inventory Management
  Purchasing and Procurement
  Project Definition Through Close
  Human Resources
Process Review
  Meet with affected process owners to verify common control design and identify gaps
  Make appropriate changes to existing process maps
  Attend Functional testing to observe functioning of critical controls
  Facilitate resolution of expectations gaps related to controls
Enron North America

## Slide 4: Technical Components
Interfaces
  Meet with SAP team / legacy system developers to identify interface flow and controls
  Map interfaces with risk / control points
  Observe functional testing to ensure functioning of critical controls
  Report progress of interface accuracy and success throughout test cycles
  Out of Scope
  783.D EBS-Canada
  799.D EBS-Citibank NY Citibank DE Bank of America TX
  873.D CBM to CS by Profit Center (C0293)
  775.D HL&P Utility Invoice (AP)
  776.D SW Public Service Utility Invoice (AP)
  777.D Arizona Public Service Utility Invoice (AP)
  837.D PHH Cindant MasterCard to SAP
  843.D Interfacing GPG & ENA Data Existing Interfaces
  351.D SAP Payment info to Unify
  Proposed In scope
  745.D Unify AP Invoices to SAP
  838.D SAP Intercompany AP Invoice to Unify
  744.D Unify AR Invoices to SAP
  761.D Unify Intercompany AR-AP Invoice to SAP
  800.D Lockbox - Bank of America TX
  874.D Check Printing for ENA - Canada (C0293)
  791.D Unify AR-AP Accrual & Reversal to SAP
  849.D SAP to Credit Aggregation System
Enron North America

## Slide 5: Technical Components - Contd.
  Proposed In Scope
  763.D SAP Extend AP Vendor Master Data
  738.D MSA AR Open Items to SAP
  737.D Unify AR Open Items to SAP
  811.D GL Balance Conversion (Enron - N/A)
  842.D GL Balance Conversion (Enron - Canada)
  819.D Asset Master Load (Enron - N/A)
Enron North America
Conversions
  Meet with SAP team to identify converted data and verify conversion structure
  Assess conversion adherence to standard controls
  Out of Scope
  765.D SAP Employee Receivables Account Group Open
  767.D HR Master Data Employee Rec to SAP
  815.D PS/IO Balance Conversion (Enron - N/A)
  806.D Work Center Create/Change - Enron - N/A
  807.D Project /WBS Create/Change - Enron - N/A
  808.D Network Activity Create/Change - Enron - N/A

## Slide 6: Process Project Team
Enron North America
(A) Involved at a high level to ensure leverage of business knowledge

## Slide 7
Project Timeline
Enron North America
May
1
July
1
June
1
Roles Review -
Kate Agnew, Carrie Applewhite
Compare listing of incompatible roles with current listing of ENA roles
Communicate issues to site manager, corporate coordinator and security administrator
Conduct follow-up on issues resolution
Account Mapping -
Kate Agnew, Craig Wescott
Obtain and review system exception reports to verify completeness and accuracy of account mapping
Resolve account mapping exceptions and discrepancies
Conduct follow-upon issue resolution
Canada Process Analysis - Kate Agnew, Jared Heep
COMPLETE
FIT 2
FIT 3
COMPLETE
Deliver formal written results to site manager and process owners
System Lock-down Scope Completion
“Go Live”

## Slide 8
Project Timeline
Enron North America
May
1
July
1
June
1
A/P and Cash Disbursements Process
Andy Willis
Noor Kaissi
Kate Agnew
Utilizing existing process model, validate selected ENA business processes. Analyze and prioritize new business risks and controls
Identify and communicate process “gaps” to site manager
Communicate process gap analysis, issue resolution, and formulate action plan
Conduct follow-up review to ensure resolution of high-risk issues were addressed
FIT 2
FIT 3
Deliver formal written results to site manager and process owners
System Lock-down Scope Completion
“Go Live”

## Slide 9
Project Timeline
Enron North America
May
1
July
1
June
1
A/R and Cash Receipts Process
Gillian Boyer
Kate Agnew
Tom Dawson
Utilizing existing process model, validate selected ENA business processes. Analyze and prioritize new business risks and controls
Identify and communicate process “gaps” to site manager
Communicate process gap analysis, issue resolution, and formulate action plan
Conduct follow-up review to ensure resolution of high-risk issues were addressed
FIT 2
FIT 3
Deliver formal written results to site manager and process owners
System Lock-down Scope Completion
“Go Live”

## Slide 10
Project Timeline
Enron North America
May
1
July
1
June
1
Intercompany Process
Noor Kaissi
Russ Montgomery
Kate Agnew
Utilizing existing process model, validate selected ENA business processes. Analyze and prioritize new business risks and controls
Identify and communicate process “gaps” to site manager
Communicate process gap analysis, issue resolution, and formulate action plan
Conduct follow-up review to ensure resolution of high-risk issues were addressed
FIT 2
FIT 3
Deliver formal written results to site manager and process owners
System Lock-down Scope Completion
“Go Live”

## Slide 11
Project Timeline
Enron North America
May
1
July
1
June
1
Bank Accounts and EDI Process
Mary Ann Missman
Alywin Fruge
Utilizing existing process model, validate selected ENA business processes. Analyze and prioritize new business risks and controls
Identify and communicate process “gaps” to site manager
Communicate process gap analysis, issue resolution, and formulate action plan
Conduct follow-up review to ensure resolution of high-risk issues were addressed
FIT 2
FIT 3
Deliver formal written results to site manager and process owners
System Lock-down Scope Completion
“Go Live”

## Slide 12
Project Timeline
Enron North America
April
24
July
1
June
1
Unify Interfaces - Bobby Joseph
Kevin Kosub
Meet with SAP and Legacy developers
Document interface controls
Validate information
Monitor/communicate results
FIT 2
FIT 3
System Lock-down Scope Completion
“Go Live”

## Slide 13
Project Timeline
Enron North America
April
24
July
1
June
1
Cash Interfaces - Bobby Joseph
Tracey Judson
Meet with SAP and Legacy developers
Document interface controls
Validate information
Communicate results
FIT 2
FIT 3
System Lock-down Scope Completion
“Go Live”

## Slide 14
Project Timeline
Enron North America
April
24
July
1
June
1
Credit Interfaces - Bobby Joseph
Kevin Kosub
Meet with SAP and Legacy developers
Document interface controls
Validate information
Communicate results
FIT 2
FIT 3
System Lock-down Scope Completion
“Go Live”

## Slide 15
Project Timeline
Enron North America
April
24
July
1
June
1
Conversions - Bobby Joseph
Kevin Kosub
Tracey Judson
Meet with conversion team leads
Review methodology documentation
Review execution/conversion documentation
Communicate Results
FIT 2
FIT 3
System Lock-down Scope Completion
“Go Live”

## Slide 16: Key Business Observations
Reconciliation of cash application within SAP to primary account records maintained in Unify Settlements
Ensure system ability to properly net trade Accounts Receivable and Accounts Payable
Determine effective process for administering Prior Month Adjustments (PMAs)
Resolve segregation of duties and process issues with ECT- Canada
Ensure effective process design with regard to intercompany transactions
Enron North America

## Slide 17: Process Timeline
Objectives
Roles Review
Compare listing of incompatible roles with current listing of ENA roles
Communicate issues to site manager, corporate coordinator and security administrator
Conduct follow-up on issue resolution
Account Mapping
Obtain and review system exception reports to verify completeness and accuracy of account mapping
Resolve account mapping exceptions and discrepancies
Conduct follow-up on issue resolution
Timeline
Complete
Complete
May 1 - May 5
May 3
May 4 - May 9
May 15 - May 19
Enron North America

## Slide 18: Process Timeline
Objectives
Process Analysis
Validate selected processes. Analyze and prioritize new business risks and controls
Identify and communicate process “gaps” to site manager
Issue Resolution
Communicate written deliverable to site manager and process owners
Conduct follow-up review to ensure high-risk issues were addressed
Timeline
May 1 - May 17
May 17 - May 19
May 22 - June 30
June 2
June 19 - June 23
Enron North America

## Slide 19
Project Timeline
Enron North America
May
1
July
1
June
1
Roles Review - Kate Agnew, Carrie Applewhite
Compare listing of incompatible roles with current listing of ENA roles
Communicate issues to site manager, corporate coordinator and security administrator
Conduct follow-up on issues resolution
Account Mapping - Kate Agnew, Craig Wescott
Obtain and review system exception reports to verify completeness and accuracy of account mapping
Resolve account mapping exceptions and discrepancies
Conduct follow-upon issue resolution
Process Analysis
Utilizing existing process model, validate selected ENA business processes. Analyze and prioritize new business risks and controls
Identify and communicate process “gaps” to site manager
Communicate process gap analysis, issue resolution, and formulate action plan
Conduct follow-up review to ensure resolution of high-risk issues were addressed
Canada Process Analysis - Kate Agnew, Jared Heep
COMPLETE
FIT 2
FIT 3
COMPLETE
Deliver formal written results to site manager and process owners
System Lock-down Scope Completion
“Go Live”