## Slide 1: QSE Program Managers’ Meeting - Nov 15th, 2000

## Slide 2: Topics
  Context
  Schedule Review
  Package status
  Program Team
  Statistics

## Slide 3: Context
Feb 1: Full Volume Test Completed
Apr 7:
SoW / Contract Completed
Apr 30: Business Architecture Developed
7/00
2002
10/00
7/01
4/01
1/01
Mar 1: Package 1, 2, 3 Integration Testing Completed
Sep 1: Full Acceptance Test Completed
Mar 15: Cross Package Integration Test Completed
Jun 1: Pilot Cutover Completed
Apr 1: Mock Market Initiated
Mar 28: Business Test Completed
Aug 1: Package 1 and 2 Design Competed
Jun 1: Package 3 Requirements Completed
Oct 15: Package 3 Design Competed
Nov 30: Package 1 and 2 Build Competed
Jan 1: Package 3 Build Competed
May 25: Mock Market Test Completed
May 15: Package 2 Requirements Completed
May 1:
PMO Established
Jun1:
Warranty Period Ended
We Are Here
Jul 1:
Early Delivery of Frequency Control
Sep 1:
TCH Data Validation Tool Completed

## Slide 4: Schedule Review - Milestones
- Complete
- Complete and Signed-Off
- In Progress (Potentially Delayed)
- In Progress (on target)
- Today’s Date
- In Progress (Late)

## Slide 5: Schedule Review - Activities
Prime / Integration
Completing protocol/design reconciliation.
Market Participant Interfaces:
Security architecture developed and published
Programmatic Interface: specification and test environment developed, Package 1,2,3 XML specification complete and published.
Transaction Clearinghouse: EDI standards defined and published. XML Implementation Guides drafted and available on request.
Portal: Release 1 and Release 2 (Oct 31) developed. Release 2 currently available for viewing. Public component of the portal will be delivered in the Portal Release 3 (1/31).
Market Participant Training
Market Participant curriculum drafted. Will be available for publication after ERCOT final review.
Market Participant Testing
Continuing test of EDI conversion files from the 6 IOU utilities (Reliant, TXU, AEP, TNMP, Xcel, Entergy)
Test environment for Programmatic interface available since 10/2 (minimal use to date)
Drafted EDI/XML certification test approach (not yet published; discussed with Test Planning Group)
Drafted Mock Market approach and discussed with QSEs - ongoing refinement

## Slide 6: Schedule Review - Activities
Package 1 - Operations Systems
Completing Build for Package 1 (POS/MOS systems) - targeted for 11/30.
Completing System Validation and Testing Plan (SVPP) - targeted for 11/30.
Network database conversion essentially complete - ESCA continuing upload to Package 1 solution - targeting 11/24. Running power flow solution to confirm accuracy of converted data
1-Line Conversion underway - targeting 12/31/00 completion date for initial conversion.
Supported successful EFC test on Oct 24 – EFC testing support complete.

## Slide 7: Schedule Review - Activities
Package 2 - Commercial Operations
Completing Build (Transaction Clearinghouse, Siebel, LODESTAR, STC (Application Integration, ND Auto (Load Profiling), MV-90 (Meter Data Acquisition), Portal) targeted for 11/30
TCH Data Validation tool completed and signed-off. Utilizing environment to support EDI technical connectivity testing.
Profile data evaluation report completed and preliminary profile models delivered (Aug 31). Final Weather Zone and Segment Definitions delivered to ERCOT (Oct 31). Final profile models to be delivered 12/31.
Conducting product test (136 test scripts); developing integration test model (56 test scripts).
Package 3 - Data Archive / Data Warehouse
Completed Package 3 Design - 35 OLAP reports, 28 dynamic extracts, 8 scheduled extracts.
Building package 3 solution - targeted completion 12/31.
Working on Package 3 test model development (product, package)
Preparing to publish extract descriptions.

## Slide 8: Project Staffing - Organization

## Slide 9: www.texaschoiceprogram.com
Statistics for the Week of 11/4/2000 to 11/11/2000
Participants Requesting NDA for Market Design Documents
AEP/CSW
AES New Energy
Austin Energy
Automated Power Exchange
Brazos Electric
Bryan Utilities
Calpine
CPS – San Antonio
Dynegy
Enron
Garland
LCRA
LODESTAR
Rayburn
Reliant
Southern Company
STEC
Structure Consulting
Tenaska
TXU
Winfield Tech.
Xi Technologies Corporation

## Slide 10: www.texaschoiceprogram.com
Historical Statistics - 10/02/2000 to 11/11/2000

## Slide 11: EDI Technical Connectivity Statistics