## Slide 1: Market Information Forum ADS Phase 2 Update
Presentation to
Stakeholders
Greg Ford and Kristen Kelley

## Slide 2: Review of ADS Phase 1
ADS Design and Development (December 1999 - March 2000)
ADS Testing and Release (April - May 2000)
Trained over 93 Market participants simultaneous with Testing
ADS Deployed on June 1, 2000
ADS Stable by June 2, 2000 (about 10:30 am)
Over 42 Market Participants Connected to ADS

## Slide 3: Since ADS Phase 1 was Deployed
Increased ADS Connections (New Scheduling Coordinators and Generator Operators ADS installs)
Requests to Update ADS Access Control List (ACL)
Requests for Additional SmartCards and Personal Access Readers
Distribution of SmartCard Docking Stations (as needed)
Requests for new ADS features
Decreased ADS Help Desk Inquiries

## Slide 4: Since ADS Phase 1 was Deployed
Internal measures for ADS Access Server stability (Interim and long-term)
Internal investigation into SmartCard Reader stability
Identify enhancements of ADS system architecture (e.g., Query Service)
Transition resources into ADS Phase 2 team
Compile Phase 2 list of features and functionality

## Slide 5: ADS Phase 2 Process
Draft Initial Scope of Phase 2 Items
Stakeholder Review and Comments (Week of 8/21 or 8/28)
Finalize Phase 2 Scope
Determine Phase 2 Tasks and Schedule
Announce Schedule for ADS Phase 2 (Mid to Late September)
Notes: Reminder: ADS version to be released concurrently with 10-minute settlements
Market Participant Client Screen Enhancements
  Fields
  Re-ordering
  Prevent Instruction window from inadvertently closing
Query/Download File - Consistent data fields
Access Control Capabilities - Interchange

## Slide 6: ADS Phase 2 Process
Develop ADS Phase 2 Functionality (Begin October 2000)
Test/Regression Test Phase 2 Functionality
Training on New Features
Market Simulation (as required)
Two-week Notice for Phase 2 Release
Deployment of Phase 2 - Possible Staged Release

## Slide 7: ADS Phase 2 Project Management Team
Greg Ford (916) 351-2344 gford@caiso.com
Kristen Kelley (916) 608-5828 kkelley@caiso.com