## Slide 1: Enron Metals – AS/400 Technology Transfer
Project Initiation February 2001
Steve Whitaker, Change Management Group
Robert Campbell, IT Development
DRAFT FOR DISCUSSION

## Slide 2: Background
Core Enron Metals systems run on an AS/400 platform
  Platform not mainstream Enron architecture
  System is difficult to integrate
  System is high maintenance
  Small development pool
  There are operational issues
It is certain that the current system cannot grow with the business
Our AS/400 system is not a good long-term investment.

## Slide 3: Reasons for Change
Undocumented system
Difficult to make enhancements – application and data tightly coupled, changes in one area does have unforeseen impacts on other areas
Difficult to resource – high dependency on “key-man” developers (2 key resources have resigned)
Operational Issues
  Resource bottleneck – Huge demand is being built up with serious operational risk considerations
  System difficult to integrate with Enron upstream / downstream systems
  System not flexible enough to move with the business.

## Slide 4: Objectives
Create a more streamlined, maintainable and efficient application architecture for Enron Metals (and Softs?)
  Migration of functional components off existing AS/400 Platform in a logical manner that will maximise business benefit whilst mitigating the risk of business interruption
    Not necessarily the complete decommissioning of the AS/400 – there may be some components where it is the best alternative
    We need to have greater development optionality
  Move to an environment that is consistent with Enron’s technical architecture – e.g. Oracle/SQL Server
  Develop an application architecture that is consistent with the business model for Enron – e.g. stripe concept for Middle Office

## Slide 5: Scope: Products, Markets & Functionality
Products and Markets
Futures
Traded options
Traded average price options
Averaging contracts
London Metal Exchange
  Lead
  Silver
  Tin
  Zinc
  LME Index available for futures and traded options only.
COMEX
  Aluminium
  Copper
London Bullion Market
  Silver
  Gold
LIFFE
  Coffee
  Cocoa
New York Board of Trade
  Coffee
  Cocoa
OTC
  Physical Metal Contracts
  Foreign exchange Contracts
Aluminium Alloy
Aluminium
Copper
Nickel
Gold
Silver
Sugar
Sugar
Functionality
Deal Capture
Price Entry
Automated feeds
  LME commodity prices, volatilities, interest rates and foreign exchange rates gained via the LCH’s LME External Interface for settlement and COB
  NYBOT Softs prices are obtained via an automated text file import from the web.
Manual price entry from dedicated screens
  Administrative users enter additional market/commodity prices, FX and interest rates manually from sources such as the FT etc.
Valuation / Risk / Position Management
Intra-day and overnight Mark-to-Market valuations
Futures and averaging cards produced intra-day
Option position “Greek” matrixes showing “what-if” scenarios.
Interfaces
LME External Interface (TCP/IP)
Mercur risk management system
SAP.
EnronOnline Bridge (TIBCO)
Cconstant trade feed from EOL via TIBCO bridge.
Compliance
Overnight regulatory processes to calculate:
  Position Risk Requirement (PRR) CAD 2.
  Counterparty Risk Requirement (CRR)
  CFTC/PERTS Large position report downloads
  Softs equity summary report downloads
  LME Large position reporting - automatically transferred via the LCH’s gateway to LME compliance.
Reports / Invoicing
Created and sent to clients during the day and overnight
  Trade confirmation
  Position evaluation
  Settlement
  Margin reports
  Physical stock invoicing etc.
Enquiry Tools
The user interface provides enquiry screens allows internal customers to run standard and adhoc account, trading and stock queries.
External clients can view a reduced set of reports via the web based application J-Walk.
Accounting
Trade settlement
Ledger balance postings
Invoicing
Commission analysis
Loans
Standing orders etc.
Client Communication
Automation of telex, fax or email
Credit / SPAN Margining
Overnight process calculates initial and variation margin for LME trades using SPAN margining
  Customers’ credit and margin positions assessed against SPAN
  Call invoices produced and sent automatically.
Physical Business
Stock control and allocation
Weight adjustment
Warrant price fixation
Off balance sheet financing
Physical position analysis.
Static Data Management
Prompt date diaries
Stock port listings
Metal brand specs etc.

## Slide 6: Scope: Location, Architecture, Departments and Businesses
Locations
Europe
UK
  London
  Liverpool
Germany
  Essen
  Dusseldorf
  Hamburg
  Frankfurt
Spain
  Bilbao
Sweden
USA
New York
Houston
St Louis
Los Angeles
Chicago
Canada
Montreal
Asia/ Pacific
Tokyo
Korea
Departments
Front Office
Middle Office
Risk Management
Documentation
Trade Accounting
Working Capital
Invoicing/ Settlements
Back Office
RAC
IT
Development
Operations
Architecture/Infrastructure
Data
Reference data
Corporate data
Migration and data conversion.
System interfaces
Upstream
Downstream e.g. SAP/Mercur.
Impacted systems
New systems/components
Enhancements to existing systems.
Architectures
Technical architecture
Application architecture
Business architecture and processes.
Businesses
Trading
  Physical Trading
  Financial Trading
Brokerage
Warehousing
Recycling

## Slide 7: Current Risks for Development
The scale and complexity of work is being underestimated
Insufficient IT resources to complete work within timeframes
Poor data quality and processes in existing systems prevent the new business processes from operating effectively
Line responsibilities and other priorities mean that business users are unable to devote enough time to the work
Perceived lack of buy-in from business representatives given the scale of operational risk/ business threats
Lack of cross departmental management framework leads to co-ordination and communication breakdown
Commercial pressure to deliver short term solutions and enhancements diverts focus and resources away from overall goals.

## Slide 8: What Do We Need To Do?
Deliver value as early as possible with minimal risk
  Incremental change not BIG BANG
  Prioritise according to Business needs/musts
  Solution should not compromise the existing business - parallel
Business and IT working as one team
  Collective achievement of collective goals not individual achievement of individual goals
  Create joint incentives for success
    Incentivise ALL with appropriate risk/reward trade off.
CEO & Senior Management sponsorship and continuous involvement
Development and adherence to a Framework that will enable structured thinking and informed decision making, without compromising individual entrepreneurship
  Efficiency not bureaucracy
  Open and frequent status reporting and measuring of performance
  Rapid problem resolution
  Continually challenge the overall direction
  Clear accountability and responsibility
  Do not attempt to manage and control everything all at once.
Take care to apply what we have learnt from previous initiatives.

## Slide 9: Future Risks for Development
New business acquisitions shift the focus and priority of the work
Lack of required skills for a more structured initiative:
  Dependency on key technology resources
  Not enough depth of experience at delivering large projects and complex programmes
  Insufficient infrastructure/ control to deliver something this complex
  Inter and Intra project dependencies are not understood.

## Slide 10: Next Steps
What should we plan to do in the short term?
  Drive the project through the formal approval process
  Determine the business priorities and hence functionality to be delivered as part of release 1
    E.g. Inventory Management
  Confirm the architecture approach and overall scope
  Develop a roadmap and programme plan
  Establish roles & responsibilities and make individuals accountable NOW
  Set up the project’s framework and establish steering committee
  Develop detailed plans for release 1
  Communicate the intent
  Mobilise the project
Deliverables – 15 March 2001
  Business justification
  Project justification
  Roadmap and programme plan
  Detailed Release 1 plan.
Who should do this?

## Slide 11
APPENDIX
Approach and Plan

## Slide 12: Approach – Architectural Concept
Current architecture
AS/400 – “System Isolation”
  System boundaries are too wide – it does “everything”
AS/400 – Shortcomings
  Tight coupling of applications and data
  System developed by a small development team, suffers from rigid development “style”
  Too many operational tasks are handled by developers having to change programs
Parallel execution
Minimise operational risk
Build the new architecture in parallel to the current AS/400
Leverage IT expertise in areas we are good at
Build on a platform currently supported elsewhere in the business
Implement Enron minimum IT control standards
Port data real time to an “Enron” type database through a data pipe
Break project up into releases
Deliver separate functional components
  Facilitates managing the project
  Demonstrate progress
Lose obsolete functionality
Determine what is essential and what is “nice to have”
Don’t switch off any AS/400 functionality until new functionality is proven
Use components developed for other systems where appropriate
Replace/ improve current functionality
Build up functionality supported off the AS/400 over time
Revisit and confirm priorities before each new proposed release
Decommission AS/400 processes once new functionality is stable
End-game determined as we get a better understanding of the AS/400 components that remain
  Could decide to decommission the whole system
  May wish to keep some streamlined functionality e.g. Deal Capture
System Boundary
Release 1
Release 2
Release 3
Release n

## Slide 13: Approach – Release Based Programme
Q2
Q1
Q3
2001
Q1
Q4
Q2
2002
Q3
Q4
External
Dependencies
Existing
Initiatives
Legal
SAP Integ
Off Balance Sht
Current Project
Approach Used
Planning &
Mobilisation
Release Based Approach
EML Mnemonics
PROJECT APPROVAL, PROGRAMME PLANNING
AND MOBILISATION
Indicative Only
Roadmap and Programme Management
Release 1
Release 3
Release 2
Release n

## Slide 14: Approach – Release Based Programme
We are failing by concentrating on independent projects
  There are huge interdependencies and priorities which need active management.
Develop a release strategy/ roadmap to show a possible route to the end game
  Break it down into manageable pieces
  Revisit regularly to ensure its continued validity
  Once a release has been agreed plan this in more detail – leave future releases to be planned later
    Do not attempt to plan everything all at once – things will change far too quickly.
Organise the work as a series of phases/ releases
  Enables us to focus on shorter term objectives
    3-6 months
    Focused delivery of a new service (or set of business functions) to Metals
  Appoint a Release Manager to ensure this delivery takes place according to plan.

## Slide 15: Approach – Roles & Responsibilities
Enron Metals
Commercial and Commercial Support
Release Acceptance
Requirements
Release Management
Business Requirements
Integration Tested
Release
Integration Tested Release (Service)
Service/Operability
Requirements
Service Level Requirements
New Systems
Development
Existing Systems
Development
Systems
Integration
Tested Service
Service Implementation
Service Delivery
Business Management
Business Change
Programme Management
Business Process Requirements
System Tested Application
Release 1
Release 2
Release 3

## Slide 16: Approach – Roles & Responsibilities: Business
Business Management
  Developing the initial function and service definition i.e. what is going to be in a release - in consultation with Commercial and Commercial Support
  Developing the detailed business requirements and the business acceptance criteria that reflect these requirements
  Developing the communications plan
  Marketing and launching the new release
  Supporting the business acceptance process
  Defining the roll-out approach.
Business Change
  Developing the new procedures that need to be operated in conjunction with the new systems
    Tested in Business Integration Testing
  Managing the training of the business users in the new service
  Executing Business Integration Test
  Organising the setting up of a customer help desk (if necessary).

## Slide 17: Approach – Roles & Responsibilities: IT Development
New Systems Development
  Supports the core build of the application and architecture software - through to system test.
Existing Systems Development
  Undertakes all development work associated with the existing systems impacted by the new release - again through to the system test of these modifications.
Systems Integration
  Looks across all system development projects
  Establishes the process by which the various systems - and associated manual procedures - will be integrated within a single release
  Development of an integration test environment, and after system test is complete, the execution of the integration test cycles
  Support the development of the conversion utilities and interim software that will be needed during the cutover of the production environment to the new release.

## Slide 18: Approach – Roles & Responsibilities: IT Operations
Service Implementation
  Project-based team responsible for managing the impact of the new release on the production environment.
    develop the new service model
    define the changes necessary to service delivery
    develop the service acceptance criteria
    define the service level agreement (SLA) that will formalise the relationship between service delivery and the business for the live service
    accept the new release from systems integration
    train service delivery personnel
    support the Business Integration Test of the new release.
Service Delivery
  Supports the production environment
    On-going function rather than a project
    Accept the Business tested release from Service Implementation and support its live operation.

## Slide 19: Release Plans & Deliverables - Indicative
Release 1 – September 2001
BUSINESS MANAGEMENT
BUSINESS CHANGE
RELEASE MANAGEMENT
PROGRAM MANAGEMENT
EXISTING SYSTEMS ENHANCEMENT
1. Release Requirements Analysis
2. Project e Development - AS/400 Pipe Interface
SYSTEMS INTEGRATION
SERVICE IMPLEMENTATION
SERVICE DELIVERY
NEW SYSTEMS DEVELOPMENT
1. Release Requirements Analysis
2. Project a Development- Data pipe
3. Project b Development – Enron database
4. Project c Development – Inbound interfaces
5. Project d Development – Inventory Management
IT OPERATIONS
IT DEVELOPMENT
BUSINESS
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Elaboration
Construction
Transition
Communication plan
Communication
Release Launch
Business Acceptance
Business Acceptance Criteria
Functional Specification
Release Operability Requirements
System Test
Integration Test Complete
Migration Plan
Integration Test Plan
De-commissioning Approach
Business Integration Test
Acceptance
Criteria
Accepted Software Release
Business Integration Test
De-commissioning Plan
Release
Acceptance
Convert
Production Systems
Live
Service
Release
Acceptance Criteria
Release
Requirements Definition
New Business Processes
Business Processes Converted
Confirmed Release Requirements
Indicative Only
User Acceptance Test
Technical Specification
Functional Specification
System Test
Technical Specification
System Test
Functional Specification
Technical Specification
System Test
Functional Specification
Technical Specification
Confirmed Release Requirements
System Test
Functional Specification
Technical Specification
Business Integration Test
Today