## Slide 1
Jose LNG
November 05, 2000

## Slide 2: Proposed Project Structure
Project
Gas Supply
PDVSA-Gas
EPC Contract
Turn-Key
PDVSA-Corp
Guarantee
Site & Pier
PDVSA-Gas
PDVSA-Gas to provide
gas supply and site
All PDVSA-Gas obligations
are backed by parent
O&M Contract
Turn-Key
EE&CC to provide Turn-Key for the project. EPC price and EPC contract in final negotiation. Other potential EPC contractors explored. Check EPC slide for complete summary of pros/cons of using EE&CC
Turn-key $580MM
Approx. 4% of EPC
ENRON to provide O&M services to project. Several options available for adding third parties to O&M Contract. Most O&M activities could be contracted to third parties, while keeping a core senior management team at the project level for relationships and expansions
Equity Financing
Debt Financing
ENE
PDVSA
Off-Take
Agreements
$210MM
30% Equity
$490MM
70% Equity
ENE
PDVSA
75%-$157MM
25%-$53MM
ENE to continue sell-down strategy to accomplish off-Balance Sheet treatment and MTM.
Debt from bank and bond market. Basic assumptions are: T-650; 14-y tenor,; fees of 200+50; coverage ratio 1.50x
25% off-take (75,000MMBtu/d)
Net Off-take 300,000MMBtu/d
Off-take to be split between
ENE & PDVSA
75% off-take (225,000MMBtu/d)

## Slide 3
Price Exposure Analysis
Terminal
Services
PDVSA Corp.
Gas Supply
O&M Fee
CPI based
Off-Take
ENE-PDVSA
Equity
Return
Debt
Principal/Interest
$0.65 @ HH
$0.15 @ flat 1%
$0.15 @ CPI
Basic Price
Minimum Price
Bonus Structure
HH + Basis
$ 0.20 @ CPI
$ 1.25 Flat
Pricing to match
All inlet gas: Basic price, floor and bonus
O&M costs escalation
Capital recovery and return (Flat)
70% Flat
30% @ CPI
Various Hedging
Instruments
ENA
MOL
EXMAR
Leir Hoergh
70% Flat
30% @ CPI
Jose LNG
Project
LNG Markets
EPC
Price
$
$

## Slide 4: Economics - Liquefaction Toll
Basic Assumptions

## Slide 5
Dec. 2000
Execution all Documents
GSA LC - $20MM
(construction)
EPC - Cancellation Fees
for owner and Completion Guarantee for EE&CC
Equity commitment - FC may be bridge financing
PDVSA equity option starts
Off-take final commitment
May 2004
Commercial
Operations
Feb. 2001
Permits Obtained
July 2001
Financial Closing
PDVSA Option
GSA LC - $30MM
(operations)
EPC - Performance Guarantee from EE&CC
- Up to 7 mos -
Project Timeline
ENE’s
Commitments
GSA LC - $1.25MM
(pre-construction)
GSA LC - $4MM
(pre-construction)
April 2001
Executed EPC Contract NTP
May 2001
Executed O&M
Shipping Arrangement
O&M - Cancellation Fees
Shipping commitments
Jan. 2002
PDVSA Option
PDVSA option expires
Estimated
Key Dates
Nov. 2000
Participation Agreement Completed
LNG Off-take - structure established/ final commitment before FC

## Slide 6: Potential Economic Upsides
NYMEX gas SWAP: 10 cents are worth $55MM NPV
Better Basis Market: 10 cents are worth $55MM NPV
PDVSA Mkting Fee: 10 cents are worth $33MM NPV
Financing: Refinancing for 4 additional years is worth $25MM
Pipeline Option: Could be worth 5 cents or $25MM NPV
Discount Rate: 1% is worth $15MM NPV in sell-down
Terminal Value: ?
Expansions: ?
Tax Optimization: ?
Other: Arbitrage trading, O&M profits, EPC profit

## Slide 7: EPC Options
Option 1 - EE&CC to be the EPC contractor of the Project
Pros
  Speed: fast-track engineering and construction process (4 months FEED study). Negotiation on advanced stage of development (EPC contract and not-to-exceed price within 4-5 weeks)
  Experience: EE&CC’s ACCRO experience in Venezuela very valuable (adjacent to LNG site)
    Strong relationship with several local providers (labor component)
    Experience cryogenic team assigned for this job within EE&CC
  Technology: fits application perfectly (small-scale plant). B&VP is widely recognize as a top cryogenic/extraction industry player
  Profits: significant profit making activity if performed under budget ($39MM in profits, plus contingency)
Cons
  EPC Price: important delay on obtaining not-to-exceed EPC price. Difficult to determine FOB price from marketing companies to project (unknown EPC price until FEEDs are completed)
  Performance: issues on several jobs performed by EE&CC recently (all completed w/ troubles)
  Accounting: issues on MTM during construction (currently under study/probably manageable)
  Exposure: ENE exposed during construction of the facility (profit & contingency should account for this)
  Affiliate Transaction: potential transfer pricing issues with PDVSA and other partners

## Slide 8
Option 2 - To bid EPC contract among top EPC contractors in the business
Pros
  Exposure: ENE may not be responsible for completion guarantee (depending on level of LDs from Contractor)
  Competition: proven track record of selected Contractors and competitive bid guarantee attractive EPC price (although it will be unknown for at least 5-6 months)
Cons
  Speed: significant delay in obtaining final EPC Price and EPC contract
    At least two FEEDs studies will have to be paid by ENE and other partners (estimated cost is $4.5MM/each)
  Exposure: unlikely that EPC contractors are willing to take elevated LDs (as per current EPC contract)
  Competition: Only a handful of players in the industry (two technologies available other than BV&P’s PRYCO)
    Philip’s only available through Bechtel (exclusive partnership)
    APCI is available through a number of contractors. Technology is designed for large plants
  Performance: issues/problems similar to EE&CC’s are typical in this industry
    Lack of proper supervision and large change orders are common with most large projects and Contractors
EPC Options (cont.)

## Slide 9
Option 1 - ENE to be the Turn-Key O&M contractor of the Project (current plan)
  Pros
  Plant Optimization: significant increase in probability that plant will be able to produce more LNG if operated by owner (owner will look for small improvements to optimize plant operations)
  Communication: ENE needs to maintain management team for communication channel with PDVSA (commercial team). Numerous options available for sub-contracting pieces O&M at any given point
  Flexibility: logistics are critical in LNG plants. O&M provider will have flexibility to ease logistic issues
  Operability: coordination with EPC contractor in pre-NTP phase is critical for operational friendly plant
  Cons
  Accounting: issues for lease model present depending on LDs (probably able to structure around)
  Limited Experience: ENE has never operated a LNG liquefaction plant (not necessarely difficult)
  Exposure: ENE exposed to LDs agreed in O&M contract (only if not pass to sub-contractors)
Option 2 - To bid O&M contract among experience contractors in the business
  Pros
  Exposure: limited exposure to ENE (it will depends on LDs obtained from O&M contractor)
  Accounting: easy to avoid lease treatment due to O&M situation
  Experience: O&M contractors to be selected will have significant LNG experience
  Cons
  Flexibility: O&M contractor will not necessarily be looking to provide flexible production scheme
  Plant Optimization: motivation of O&M contractor for certain plant improvements is less likely
  Financing: ENE will have to find strong O&M contractor capable of backing significant LDs
  Communication: ENE is less likely to have
Operations and Maintenance

## Slide 10
Next Steps
4th Q’ 2000 extremely pivotal. Scheduled to conclude Venezuela in country agreements and permits, and finalize Elba Island documents
Specific near term activities
  Complete Jose LNG Venezuela agreements
  Finalize Elba Island documents (Doug Arnell and Les Weber)
  Advance conversations with El Paso (Cove Point) and CMS (Lake Charles)
  Decision on EPC Contractor (EE&CC vis-à-vis third party contractor)
  Follow-up with Banks for project financing package (Larry Lawyer and Martin Rees)
  Approach possible Equity investors after all key contracts are in place
Internal approval process:
  Decision on approach for PDVSA’s Participation Agreement (LNG off-take arrangement)
  Marketing/pricing approach with EGM/J. Shankman/ENA
    Are we prepared to be 100% off-takers
  RAC
Expenses to date
  $13.5MM for the full four year. Includes Elba Island and Cove point efforts
  Need AFE increase to move forward. AFE increase will depend on EPC effort

## Slide 11: Gas Purchase - PDVSA Contract
Main Characteristics of GSA
Volume: 350,000 MMBtu/day
Base Price: $0.85/MMBtu
Escalation:
17.5% @ USCPI
17.5% @ 1%
65.0% @ commodities to be selected mirroring off-take
Reference prices: NYMEX gas $2.33/MMBtu
WTI $18.15/bbl
Brent $16.82/bbl
Floor Price: $0.85/MMBtu (PDVSA has monthly Puts @ reference prices de-escalated at CPI and 1%)
Bonus: During the first 12 years
PDVSA gets 12.5% of: LNG FOB Price - ($0.70/MMBtu + $1.55/MMBtu * En)
where LNG FOB Price includes hedges and En the escalator for the base price
PDVSA has semi-annual Puts with strike prices that make the threshold ($0.70/MMBtu + $1.55/MMBtu * En) smaller than the FOB obtained with the swapped price
During the last 8 years
PDVSA gets 40% of: LNG FOB Price - ($0.70/MMBtu + $1.55/MMBtu * En)
where LNG FOB Price is based on spot market and does not include hedges
PDVSA has semi-annual Calls with strike prices that make the un-swapped FOB price greater than the threshold ($0.70/MMBtu + $1.55/MMBtu * En)