## Slide 1: Timeline Objectives and Process for Effective Completion of 2001 Audit Projects
AA formally confirms upcoming audit project to EAS Leader
A
B
F
C
E
Pre-Audit Phase
Pre-Audit Phase
Audit Execution Phase
Post-Audit Phase
A
EAS Leader initiates notification process with Primary Process Owner (approx. 2 wks before project kick-off)
B
Audit Execution Phase
C
Conduct opening meeting with Primary Process Owner and key contacts (approx. 1 wk prior to start of fieldwork)
Continuous communication of audit issues and recommendations with process owners and EAS
D
E
Conduct Audit Closing Meeting: review draft report, confirm action plans, responsible party & target dates
Post-Audit Phase
D
F
AA submits final report and template with critical issues for Issue Tracking (within 2 wks of Audit Closing Meeting)
G
EAS follows up on status of action steps in order to close out issues (within 3 wks of closing meeting)
Enron Wholesale Services
G & H
I
H
Conduct Management Closing Meeting on monthly basis to review reports and discuss status of critical issues
Confidential
EAS evaluates service delivery process through informal & formal feedback (i.e., Customer Feedback Survey)
I
J
J
EAS Leader provides quarterly updates on progress of implementations
DRAFT