## Slide 1: Project Dolphin
Project Update - 19 January 01
Confidential

## Slide 2
Key Project Issues - Reviewed with Frevert
(new issues in italics and underlined)
ADNOC/UOG alignment
Upstream
    Production Sharing Agreement
      Block Location
      Capex: Compression, utilities, total capex
      FOB price and escalation
    Exxon/Mobil influence
Pipeline
    Capital costs
    Financeability
Marketing
    Landed sales price (controlled by Abu Dhabi government); potential squeeze on Marco
    Seasonality management and cost
    Access to onshore distribution system
Partnership Issues
    FEED/EPC organization integration and control
PDA Re-negotiation
    Sell-down timing and limits

## Slide 3
Current Focus Areas
Upstream PSA Term Sheet - Agreed Target Execution: 15 Feb
  FOB price and escalation
  Production block
  Estimated Capex
  Cost recovery and profit oil splits
  Compression and utilities plan
End-user volumes, pricing, and margins
PDA restructuring/JOA negotiations - impacts sell-down value
ADNOC/Dolphin alignment and management team
Early gas/local alternative supplies

## Slide 4
Enron Cash Requirements - 2001
Shareholder G&A ($250/month) $3.0MM
Shareholder Legal Costs (PDA) $1.0MM
Dolphin G&A Cash Calls $0.0MM
Dolphin Third Party Cash Calls $1.0MM
Pre-FEED Study Cash Calls ($3MM) $1.2MM
FEED and Appraisal Drilling Cash Calls $8.0MM
Total Potential Cash Requirements $14.2MM
Note: FEED and appraisal drilling is estimated at $90MM total ($20MM in 2001 and $70MM in 2002) and is scheduled to commence after PSA/GSA execution in September

## Slide 5
2001 Milestones
Sheet
Date for
(~$3MM)
Enron
Contract
for Enron
February
March
April
May
June
September
October
November
December
15-Feb
14-Mar
13-Apr
26-May
15-Sep
1-Oct
1-Dec
PSA Term
PDA
Preliminary
Final
PSA/GSA
Targeted Start
Sell-down
Anniversary
Notification
Execution
Date
Withdrawal
Execution
FEED
Withdrawal
Date
Commencement
Pre-FEED
(~$90MM)
Commences
Key deliverables prior to April Go/No Go Decision
Upstream terms agreed/reasonable progress on PSA and JOA
Market volumes, pricing, and margins agreed
UOG/ADNOC alignment on implementation plan
PDA restructured to enhance upstream value and liquidity
Partnership in agreement on management team and organization