## Slide 1: Caledonia--Southern
Interconnect Proposal
August 24, 2000

## Slide 2: Caledonia--Southern Details
Description
  A new 500 kV line will be erected from the Caledonia utility to a new substation located within the Southern Company service territory.
  Line length: 3.2 miles
  Completion Date: Summer 2001
  Estimated Payback
    Simple = 2 years
    NPV @ 10% =2.5 years

## Slide 3: Caledonia--Southern Details
Purpose
  Allow a direct connection from Caledonia to the Southern Company (SOCO) system.

## Slide 4: Caledonia Second Interconnection One Line Diagram
Existing Facilities
New Facilities
Legend
Lowndes
Caledonia
NewSub
To West Point
To Miller
Mississippi
Alabama

## Slide 5: Caledonia--Southern Details
Benefits
  1) Reduce reliance on TVA firm transmission to serve SOCO market.
  2) Mitigate TVA counterparty risk (legal, regulatory, etc.)
  3) Reduce Caledonia’s transmission costs.
  4) Gain Into-SOCO market access (make Into-SOCO EOL markets)
  5) Potential Green Jacket hedge

## Slide 6
Installed Cost
  Estimated $13MM
Cost Commitments Schedule
  $0.4MM on 8/28/00 (circuit breaker option)
  $2.0MM on 9/01/00 (transmission towers)
  $0.5MM on 9/15/00 (land options)
  $0.17MM on 9/15/00 (circuit breaker purchase)
  $0.83MM on 11/15/00 (circuit breaker purchase)
  $9.1MM on 12/15/00 (remainder)
    $2.3MM Circuit breakers
    $2.5MM R.O.W
    $2.0MM Transmission E&C
    $2.3MM Switch yard
    $9.1MM Total

## Slide 7
Financial Benefits

## Slide 8
Additional Potential Revenue
  Calpine and CoGentrix have indicated an interest in using the New Sub to interconnect to SOCO. Possible 50-75% of New Sub costs shifted to Calpine/CoGentrix in 4Q 2001. New Sub is estimated at $3.7MM.

## Slide 9
Risk Summary
  Risk 1: Utility Risk
  Risk 2: Equipment Risk
  Risk 3: Construction Risk
  Risk 4: Land Option Risk
  Risk 5: Regulatory Risk

## Slide 10
Risk Explanation/Mitigation
  Risk 1: Utility Risk
    Both TVA and SOCO are scheduled for completion of interconnect studies by 11/15/00.
    Mitigation strategy--sell equipment (Breakers & Poles) if significant upgrades are required.
    Value at Risk on 12/1/00: $2.9MM

## Slide 11
Risk Explanation/Mitigation
  Risk 2: Equipment Risk
    Schedule impacting equipment will be delivered first (breakers & poles).
  Risk 3: Construction Risk
    Schedule impacting construction will be completed first (switchyard).

## Slide 12
Risk Explanation/Mitigation
  Risk 4: Land Option Risk
    All participants are discussing a R.O.W option
    All options will be completed by 10/1/00.
    Value at Risk on 10/1/00 = $2.1MM

## Slide 13
Risk Explanation/Mitigation
  Risk 5: Regulatory Risk
    Regulatory changes (such as flow based transmission, RTOs, ISOs, etc.) could occur, affecting the ability of the project to meet its objectives. None are currently scheduled to be implemented in 2001, 2002, or 2003.

## Slide 14
Caledonia--Southern
Interconnect Proposal
Supplemental Notes
August 24, 2000

## Slide 15
Risk Explanation/Mitigation
  Risk 1: Utility Risk
    At risk money prior to 12/01/00 is limited to:
      $1.4MM circuit breakers
      $2.0MM transmission poles
      $0.5MM land options
      Total=$3.9MM
      With conservative resale assumptions, this is reduced to a Value at Risk of $2.9MM.

## Slide 16
Risk Explanation/Mitigation
  Risk 1: Utility Risk cont.
    Circuit breakers--The queue for ABB HV breakers is long and several IPP projects are planned/scheduled for the TVA system. Since TVA requires ABB breakers, the opportunity for resale is high.
    Probable resale value of queue spot: >70% of purchase
    Conservative resale value of queue spot: >50% of purchase
    Net value at risk: 50% of $1.4MM = $0.7MM

## Slide 17
Risk Explanation/Mitigation
  Risk 1: Utility Risk cont.
    Transmission Poles: The queue for steel poles is high, however, the opportunity for resale is more limited.
    Probable resale value: >50%
    Conservative resale value: >25%
    Net value at risk: $1.5MM
    Land options--All money is at risk & cannot be recouped. $0.5MM
    Total net at risk on 11/15/00: $3.9MM

## Slide 18
Assumptions
  1) 300 hrs./year to SOCO or FL
  2) TVA transmission costs $1.65/MWH
  3) TVA losses @ 3%
  4) Forward curves
    Summer ‘01 forward curves: $120/MWH
    Summer ‘02 forward curves: $93/MWH
    Summer ‘03 forward curves: $80/MWH
  5) SOCO-TVA premium
    2001: $20/MW-hr
    2002: $15/MW-hr
    2003: $10/MW-hr.
  6) 20 days per year where transmission from TVA to SOCO is not available
  7) Capacity of Caledonia at peak: 500MW

## Slide 19
Formula Summary
  Increase sales to SOCO/FL = #days/yr * hrs/day * MW * $/MW
    final units: $/yr
    = 20 days*16 hrs/day*500 MW*$X per MWH
    2001: 20 days*16 hrs/day*500 MW*$20 per MWH = $3.2MM
    2002: 20 days*16 hrs/day*500 MW*$15 per MWH =$2.4MM
    2003: 20 days*16 hrs/day*500 MW*$10 per MWH =$1.6MM
  Decrease transmission fees to TVA = MW * $/kw/mo * mo/yr
    final units: $/yr
    =500 MW * $1.65/kw/mo * 4 mo.
    2001 to 2003 = 500 MW * $1.65/kw/mo * 4 mo.=3.3MM

## Slide 20
Formula Summary
  Decrease transmission losses to TVA = % loss * MW * hrs/yr (power price fwd curve $/MWH + TVA SOCO premium $/MWH)
    final units: $/yr
    =.03 * 500MW * 300 hr/yr ($120/MWH + $20/MWH)
    2001: =.03 * 500MW * 300 hr/yr ($120/MWH + $20/MWH) = $0.6MM
    2002: .03 * 500MW * 300 hr/yr ($93/MWH + $15/MWH) =$.5MM
    2003: .03 * 500MW * 300 hr/yr ($80/MWH + $10/MWH) =$.4MM

## Slide 21
  Increase sales to SOCO/FL=
  20 days/yr*16 hrs/day*500 MW*$X per MWH=
    2001: $3.2MM
    2002: $2.4MM
    2003: $1.6MM
  *Reduction in total TVA transmission costs (see later “Formula slide”)
    2001: $3.9MM
    2002: $3.8MM
    2003: $3.7MM
  Total financial gain
    2001: $7.1MM
    2002: $6.2MM
    2003: $5.3MM