## Slide 1
MG Integration
Update Report
18th August 2000

## Slide 2: Old MG structure
Business units put together for flotation in September 1999 but never integrated
Currently integrating:
  MG Financial (“MGL”)
  MG Physical (“MGMCC”)
  MG Scrap (“MGMR”)
  Rudolff Wolf - metals, softs, FX?

## Slide 3: Trading v Origination Offices
Chicago, Montreal, St Louis
  Working to make these Origination only with NY as Trading hub
RW Hamburg now originating only
Tokyo being wrapped into Enron trading office
Melbourne being wrapped into Sydney trading office
Notes: Para saw MG Oil!

## Slide 4: Segregation of Duties
Historical multi-tasking across Commercial and Support divide, and within Support
Historical under-investment in Support
No surplus of staff in Enron London
Segregating in London as move offices
Segregating in New York as we recruit
Layering in experienced Risk Management personnel and recruiting to back-fill

## Slide 5: Prepayments
Former Soviet Union and China are important suppliers of metals
Monitoring implemented
CACS process implemented for new prepayments
Russia
  Outside FSU $8.3M
  Finished product $1.7M
  Unfinished product $7.6M
  Unsecured $3.2m
Other countries $19M

## Slide 6: Inventory
High inherent risk due to
  High value
  Huge diversity
  Geographical dispersal
OBS financing
Information flow being audited

## Slide 7: Other
IT approach
  Stabilise existing platforms
  eCommerce priority
  Resource impact
Credit
  Rudolf Wolff impact
  Resource impact

## Slide 8: Lessons for next integration
Deal team to consider integration (involve Commercial Support) and price in to deal decision
Make it very clear on Day1 that Enron management are in charge
Set up Decision Management Group with authority, including target management
Take quick decisions on non-core businesses
Put any sub-acquisitions on hold
Comprehensively staff dedicated integration team immediately