## Slide 1
Coal Plant Development East Origination Project Development Group
November 14, 2000

## Slide 2: Coal Plant Development
Development Issues
Market Overview
Project Specifications
Siting
Permitting
Equipment Procurement/Lead Times
Construction
Greenfield Development Timeline and Budget
Brownfield Development Timeline and Budget
Preliminary Economics
Conclusion/Recommendations

## Slide 3: Project Specifications
Ideal Facility Size
  2 x 250 MW
Technology
  Circulating Fluidized Bed (CFB)

## Slide 4
Market Overview
Plant Resources
  385,886 MW of existing coal-fired generation (IOU’s)
  55,513 MW of existing coal-fired generation (IPP’s)
    See Attached Map of Existing Non-Utility Owned Coal-Burning Generation Facilities
  5,311 MW of coal generation under development
    See Attached Map of Planned Coal-Fired Generation Facilities

## Slide 5
Coal Plants Under Development

## Slide 6
Market Overview
Positive Regions for coal-fired Electricity Generation
  Coal producing states
    See Attached Maps of Existing Coal Mines and U.S. Coal Resources
    IN, MN, MT, SD, & WI have a statutory comprehensive Environmental Impact Study (EIS)
    Some states may use “needs analysis” to block projects (IN)
Negative Regions for coal-fired Electricity Generation
  Eastern Seaboard
  California
  Florida

## Slide 7
U.S. Coal Resources

## Slide 8
U.S. Coal Production
Top 15 Coal Producing States
Thousand Short Tons

## Slide 9: Siting
Fuel Supply
  Proximity to delivered coal (mine, rail, barge)
  Availability of adequate long-term reserves/supply
  Existence/viability of necessary infrastructure (rail, barge)
  Desired BTU and sulfur requirements of coal
Water Availability
  Required capacity of 9,600 GPM for 750 MW CFB
  Quantity & Quality impact on supply/discharge permits
  Proximity to surface, ground, & municipal supply sources

## Slide 10: Siting
Transmission/Interconnection Capacity
  Desired size of 750 MW (3 x 250 MW units)
  Preferred voltage is 230 kV, 345 kV or 500 kV
  Define Interconnect & upgrade costs and schedule
Environmental issues
  Proximity to sensitive areas (PSD Class 1, parks, etc.)
  Influence of Federal Land Manager
  Existence of wetlands, historic areas, NIMBY groups
  Appropriate PSD Classification (Attainment versus Nonattainment)
  NOX and SO2 Trading Environment

## Slide 11: Nonattainment Areas
Permitting Issues
  Must use Lowest Achievable Emission Rate (LAER) technology in Nonattainment areas
  A PSD permit in a Nonattainment area must obtain emissions reductions as a condition for approval
    Must offset the emissions increase from the new source
    Must provide a net air quality benefit
    Generally obtained from existing sources located near the proposed source
    May potentially have to purchase NOX, CO, VOC, and/or PM10 offsets

## Slide 12: Offset Prices
NOX Offsets
  $2,000-$3,000/tpy (moderate)
  $5,000-$6,000/tpy (severe)
VOC Offsets
  $2,000 per ton (moderate and severe)
No visible price for CO and PM10.5
Most expensive states in which to purchase offsets
  California, Pennsylvania, New York, Georgia

## Slide 13: NOX SIP Call
Regional NOX Emission Reductions (NOX SIP Call) required in the following states by May 1, 20041:
1SIP Call Initially scheduled to be in place by 2003

## Slide 14: NOX SIP Call States

## Slide 15: Trading Programs
NOX Allowance Trading
  Under the NOX SIP Call, must purchase allowances if the state-granted number of allowances is exceeded
  Only applicable in the 23 NOX SIP Call states
  Only applicable during the May 1 - September 1 “ozone season”
  Cost of Allowance: Approximately $400 -$500/ton
SO2 Allowance Trading
  Under the EPA’s Acid Rain Program, must purchase SO2 allowances if the federally-granted number of allowances is exceeded
  Applicable in all states, year-round
  Cost of Allowance: Approximately $150/ton

## Slide 16: Siting
Local Approvals
  “Buy-in” of government bodies (local/state)
  Support of local labor unions (if any)
  Support of local economic development agencies
  Support of local and state coal producer(s)
  Appropriate zoning for site (industrial or conditional use)
  Manage local and state opposition groups

## Slide 17
Siting
Site Development Condition
Advantage Disadvantage1
Greenfield: Limited environmental No infrastructure
risk No zoning
Brownfield: Existing infrastructure Environmental risk
Existing zoning(possibly) Demolition/clean up risk
Existing water supply
Re-powering: Existing infrastructure Environmental risk
Existing zoning Demolition/clean up risk
Existing water supply Higher cost
Existing permits/credits Lower flexibility from
current owner
1 Public opposition likely with all alternatives.

## Slide 18
Potential Sites (To Date)
Phipps Bend (Hawkins County, TN)
  Located in Northeastern Tennessee
  Site was former TVA planned nuclear plant location
  Listed on TVA interconnection page as preferred site
  TVA interconnect request currently being prepared for 750 MW
FMPA/Lakeland sites (Florida)
  RFP issued for additional coal-fired generation
  3 Florida sites identified
  RFP bid package has been requested

## Slide 19: Federal Permits
Air
  First Year Operating Permit
  Title V Permit
  Title IV Acid Rain Permit
  EPA: Prevention of Significant Deterioration (PSD Air Permit)

## Slide 20: Federal Permits
Water
  US Army Corps of Engineers: Section 404 Wetlands
  US Coast Guard: several permits required for coastal sites using ship or barge to provide coal
  National Marine Fisheries Service
  EPA: Stormwater Discharge Permit
  US Army Corps of Engineers: Permit to construct a Dock in an existing harbor, Permit to Dredge, Permit to Dump Dredging Spoils
  316 (a) Demonstration for Thermal Discharge
  316 (b) Water Intake Demonstration (New Federal Regulations being proposed)
  National Pollutant Discharge Elimination System (NPDES) Permit

## Slide 21: Federal Permits
General
  US Fish & Wildlife Service
  Solid Waste Disposal Permits
  Federal Aviation Administration (FAA): Notice of Proposed Construction or Alteration
  FERC
  Advisory Council on Historic Preservation
  NEPA Process triggered by non-delegated NPDES and/or Corp of Engineers Action
  EPA: Risk Management Plan
  EPA: Spill Prevention Countermeasure and Control

## Slide 22: State/Local
Air
  Prevention of Significant Deterioration (PSD) Permit to Construct (if state has delegated authority)
Water
  Section 401 Water Quality Certification
  State SPDS: Permit to discharge sanitary wastewater; permit to withdraw potable water
  Concession for use of a maritime zone; permit to construct a dock and permit to dredge
  Water Allocation Permit

## Slide 23: State/Local
General
  Power Plant Siting Board/Public Service Commission
    Permit to interconnect to the grid
  Certificate of Public Need
  Department of Transportation: endorsement of construction of intersection/rail access
  Certification of Conformity with Coastal Zone Management Plan
  Planning/Local Zoning Board: zoning, visual, stack height, noise and land use
  State Historic Preservation office
  Local DPW: Sewer Connection and Sewer Extension Permits
  Local Fire Department: Fire and Safety Permits

## Slide 24: Additional Environmental Issues
Mercury Requirements
  EPA study confirms that coal-fired power plants are a major contributor to U.S. mercury emissions
  In December 2000, EPA is expected to announce if it will regulate mercury from existing power plants with a 2003 promulgation date and a 2008 compliance date
PM2.5 Health Effects and the Levy study
  Currently no formal EPA standards for control of very fine particulate
  Levy study links power plant particulate emissions with cases of Asthma and premature death in the surrounding population

## Slide 25
Permitting Timeline and Budget
Timeline
  Approximately 3 years to obtain necessary permits, given no extreme public opposition
Budget
  ENA/ENSR notional estimate to achieve permitting for a new CFB plant at $4-6 MM

## Slide 26: Equipment Procurement/Lead Times
Steam Turbine
  18-22 months from order to delivery
  $100/kw (equipment only)
Boilers
  18-22 months from order to delivery
  $200/kw (equipment only)
Air Pollution Control Equipment:
  Long lead time because EPA is forcing backfits onto existing facilities
  $250/kW (equipment only but variable with technology)

## Slide 27: Equipment Procurement/Lead Times
Coal Handling Gear:
  Long lead time possible if limited domestic capacity is absorbed by growth in coal-fired power
Main Transformers:
  Lead time of up to 1 year possible for high voltage (500 kV+)
  $15/kw (equipment only based on 230 kV high Voltage)

## Slide 28: Drawdown Schedule
Drawdown Schedule for one 250 MW unit. Units 2 and 3 are staggered by 2 months each so that Unit 2 is complete in Month 67 and Unit 3 is complete in Month 69.
Assuming $1,300/kw for a 3x250MW unit plant1.
1Total Project costs = $1300/kw * 1000kw/MW * 250MW = $325 MM/unit * 3 units = $975 MM

## Slide 29: Construction
Primary Plant Construction
  Month 1: Start Preliminary Engineering necessary for permit applications
  Month 27: Release Engineering
  Month 27: Start Long Lead Procurement
  Month 39: Mobilize on Site
    Assuming all permits have been received
  Month 72: COD
Ancillary infrastructure
  Fuel handling/supply
  Ash disposal
  Water intake/discharge
  Rail/Barge delivery system

## Slide 30: Greenfield Development Timeline
Permitting
Construction
Month 27: Release Engineering & Start Long Lead Time Procurement
Month 39: Mobilize on Site
Month 72: Commercial Operations Date
Month 1: Start Preliminary Engineering necessary for permit applications
Year 1
Year 5
Year 2
Year 4
Year 3
Year 6

## Slide 31: Greenfield Development Budget
Preliminary Engineering
  Includes initial site surveys, geotech, drainage, etc.
  $3-4 MM
Siting
  $500,000
Permit Applications
  ENA/ENSR notional estimate to achieve permitting for a new CFB plant at $4-6 MM

## Slide 32: Greenfield Development Budget
Month 1-6
Month 7-12
Month 13-18
Month 19-24
Month 25-30
Month 31-36
$3.5 MM
$50,000
$350,000
$100,000
$3.75 MM
$1.25 MM
Preliminary Engineering
Siting
Permitting

## Slide 33
Preliminary Economics
Installed Costs $1,300/KW
Plant Heat Rate 10,500 BTU/KWh
Est. Run Hours per Year 8,000 hours
Annual Fixed O&M: $ 7.23 MM
Annual Variable O&M: $ 5.54 MM
Est. Energy Dispatch Cost:1 $14.05/MWh
Est. Revenue per Year2: $ 120 MM
1Assuming $1.25/MMBTU Coal Cost plus variable O&M of $0.92/MWh
2Assuming $20/MWh Market Price for Baseload electricity
Est. Revenue per Year = 8,000 run hours * 750 MW * $20.00/MWh

## Slide 34: Dispatch Profiles
$14.05
$24.34
$32.34

## Slide 35: Conclusion/Recommendations
Evaluate buy-in costs with and further identify IPP’s with latter-stage development projects for acquisition in order to:
  Accelerate our learning curve
  Reduce risk of development dollars spent
  Increase chances of having a successful development option