## Slide 1: Gas & GNO Consumption Bands
October 19, 2001

## Slide 2: Gas Consumption Bands
Process:
Secure and analyze customer list
Request contracts, transaction agreements, etc.
Read documentation and capture pertinent information, inclusive of the contract term, the band percentage(s), the contract and band prices, the band’s billing period (monthly / annual), and the band’s scope (aggregate / site)
Analyze invoicing detail
Input information into an Access database (modified KPMG database)
Analyze results, and obtain approval to invoice
additional charges
Generate and process invoices

## Slide 3: Gas Consumption Bands
Achievements:
Reviewed GAS system reporting to determine potential customers with banding stipulations
Created the initial repository for the contract information, which will be downloaded into Access
Cataloged and filed copies of contract documentation – over 600 documents

## Slide 4: Gas Consumption Bands
Hurdles:
Staffing
Obtaining systems access – Email, Documentum, Livelink, etc.
Locating / securing documentation – contracts, transaction agreements, rollovers, etc.
Receiving the second half of the invoicing detail from the Altra system
Obtaining pricing information

## Slide 5: Gas Consumption Bands
Findings:
There are approximately 625 customer from the GAS and Altra system with consumption bands
Reviewed the documentation for 10 customers, and determined the majority of the contract data was missing
The primary documentation retrieval process has been focused on current activity

## Slide 6: GNO Consumption Bands
Process:
Read documentation and capture pertinent information
Input information into an Access database or in Excel

## Slide 7: GNO Consumption Bands
Achievements:
Defined banded customers
Determined customers previously billed
Identified customers not invoiced, and established a call up process to invoice customers when need

## Slide 8: GNO Consumption Bands
Hurdles:
Defining baseline
To many groups involved in the process – baseline, site profile desk, legal, power and gas accounting, service management, etc.
Obtaining pricing information
Contract language, to subjective