## Slide 1: Cuiaba Project Development Overview
Jose M. Bestard
March 1999

## Slide 2: Purpose of Presentation
Provide General Overview of the Cuiabá Development process and some of the lessons learned.
  To win you need to be different than your competitors
    Go where the others dare not go
    Find a competitive edge.
  Pioneers open the path and pay the price
    Very long and torturous development process
  Be prepared for evolution.
    Where we are, and how we got here is different than originally expected
“Necessity is the Mother of Invention”
-- Only Enron had the core skill sets to tackle this challenge --

## Slide 3: Structure of Presentation
Project Overview and Early History
Getting Ready to Bid
Bid Assumptions and Basis
Negotiations
Project Challenges
  Devaluation and indexation
  Gas Supply
  Bolivian Precedents
  Site selection
  EPC contracts for the power plant
    Water systems
    Technology risks
  Diesel Requirements for Phase I
  EPC contracts for Pipeline
  Evolving rules, institutions and actors
Project Financing
Remaining Aspects

## Slide 4
Cuiabá I - Overview
480 MW BOT Combined-Cycle Power Plant in the State of Mato Grosso
Completion Expected
  Phase I 150 MW Diesel Fired April 99
  Phase II 300 MW Gas, Simple Dec 99
  Phase III 480 MW Gas, Combined May 00
390 Mile (628 km), BOO 18 Inch Natural Gas Pipeline Connecting to km 242 of the BBPL in Bolivia - Operational at Phase II
  Future- 7.5 MMcm/day capacity with compression
  Initial capacity 2.8 MMcm/day for power plant and LDC in the State
Capital Cost = $200 MM Pipeline + $350MM Power Plant = $550MM
21-year PPA with Eletronorte (Includes 1 year of construction)
20-year Gas Supply from YPF with EI supply option for 25% of gas requirements

## Slide 5
Santa Cruz
Robore
Rio Grande
Rio San
Miguel
GasOriente
Boliviano
Gas Trans
Boliviano
Transportadora Brasileira
Gasoduto Bolivia-Brasil
GasOcidente do
Mato Grosso
Transredes
Campo Grande
Cuiabá - PE
Cáceres
BRAZIL
PARAGUAY
BOLIVIA
1. PE
2. Gas Mat
3. Gas Bol
PANTANAL ENERGIA
Enron 65.625 %
Shell 21.875 %
Transredes 12.500 %
GasMat
Enron 50.0 %
Shell 37.5 %
Transredes 12.5 %
GasBol
Enron 20.0 %
Shell 20.0 %
Transredes 60.0 %
Cuiaba Integrated Project

## Slide 6: Early History
July 94.- MOU between the Bolivian and Brazilian Governments to evaluate possibility to supply energy to Mato Grosso utilizing Bolivian Gas
Aug 95.- Portaria MME/MMF creates commission to evaluate
Dec 95.- Commission Recommendations
  450 MW in Cuaiba in two stages by 2001. Gas delivered at less than US$ 2.75/MMBtu
  Model IPP with a bid; Cemat as the Buyer; alteration of exiting contracts with Furnas and Eletronorte; delay of Manso and Itiguira
  Negotiations with Petrobras to include this project within the scope of the BBPL
Enron side strategy - 94-95
  A 450 MW power plant, in JV with Cemat.- Negotiated Open Book Model. Eletrobras as off-taker performing energy contract mix for the state.
First Half 1996
  JVA with Cemat; State Assembly had to pass Law.
  Preliminary technical studies conducted. DNAEE feasibility studies.
  MOU for Eletrobras participation as partner and off-taker submitted.
Aug 1996.- MME Brito opposes this path and calls for “least price” bidding

## Slide 7
Almost made it !!! --- Eletrosul scandal presses Minister Brito to cancel the negotiated deal with Cemat and Eletrobras -Aug 96

## Slide 8: Getting Ready to Bid
To conserve our preparation advantage we pressed for speedy bid.
Eletronorte prepares to bid 110 MW to issue RFP by November
  450MW are needed to anchor the gas spur. Petrobras provides an expensive estimate.
  Bid structure is for block of energy to allow Hydro and Bolivian exports.
  Brito intercedes at last moment to assure that a gas pipeline could be built. Bid is delayed for a 450 MW, but in three phases
New bid is issued in Feb 97 for 60 day response. Postponed once.
Petrobras still has monopoly control of pipeline
  We made independent preparations to provide the full supply, but considering that politically the spur could be incorporated in the BBPL scope.
Very active in the Q&A of the Edital!!!
  Explaining issue ahead of time. Many answers were negative!!
Pursued Preliminary EPC contracts for fast start

## Slide 9: Bid Assumptions and Bases (April 97)
The following eight slides capture the most significant points at the time of the bid.
The Pipeline structure was the big unknown because of the Petrobras monopoly situation (we assumed that the Brazilian pipeline would follow the BBPL partnership structure).
The week before the bid…….
  El Paso wanted proportional participation in the Power plant. We did not agree and they decided to submit a competitive bid.
    Our price submission was reduced “must win” status to enter in Brazil
  Petrobras decided to give Enron and El Paso the same gas terms (not BBPL)
    We decided to provide our own independent bid and invite Petrobras if required by Law
  All pipeline model prices were modified the night before the bid !!!!
  Eletronorte answered indexation questions adversely !!!

## Slide 10: EDC ExCom - IPP Project Structure (April 97)
Enron
IPP
Project Co.
EPC Contractor
Turnkey EPC
Contract
50% w/ control
25%
denotes ownership
denotes contract
Key
PPA
JV O&M
Enron
Lenders
Shell
Eletronorte
Others (Petrobras
and Eletrobras)
20%
C.I.G.
5%
Fuel Supply &
Transportation Services
Agreement
P/L Spur Co. and
YPF/Petrobras
Eletrobras
Guarantee
Notes: <number>
<footer>
<header>
<date/time>
11

## Slide 11: EDC ExCom - IPP Turnkey Bid Strategy (April 97)
Continue evaluation of turnkey terms, including sourcing and tax impact with Siemens and Westinghouse.
EPC Turnkey Term sheet being negotiated.
Aspects that put upward pressure on the turnkey price:
  First phase - 150 MW block has to be in commercial operations within 12 months of PPA signing. Only Siemens and Westinghouse can meet the schedule with early commitments.
  Site location, logistics of moving equipment and skilled labor.
  Fast schedule for first unit on diesel, conversion to gas for second unit and delayed schedule for last block.
  36-month deferred construction drawdown schedule.
Get a turnkey contractor that will meet the target price or “go naked”

## Slide 12: EDC ExCom - Pipeline Project Structure (April 97)
P/L Spur Co. *
(Bolivia/Brazil)
EPC Contractor
Turnkey EPC
Contract
denotes ownership
denotes contract
Key
TSA
JV O&M
Enron
Lenders
Shipper (IPP)
Fuel Supply
Agreement
YPF/Petrobras
Bolivian P/L Spur Co.
Brazilian P/L Spur Co.
Enron 42.5%
Shell 42.5%
Petrobras 9%
BTB Group 6%
Enron 12%
Shell 12%
Petrobras 51%
BTB Group 25%
*
Notes: <number>
<footer>
<header>
<date/time>
11

## Slide 13: EDC ExCom -Cemat Spur Pipeline Phase 1 Project Overview
Bid requires LOI for gas supply and transportation
606 km. P/L from Santa Cruz, Bolivia to Cuiaba, Brazil
Volume: 2.3 MMCMD
Diameter: 18”
Est. transportation tariff: $1.60/MMBtu (target)
Construction start date of May 1998
Completion date of July 1999 (for Phase 2 of IPP)

## Slide 14: ExCom - Cemat Power Project (April 97) Guarantees and Penalties for Delay Provided by IPP
Bid Guarantee
$5.7 MM LOC
$22.9 MM LOC
PPA
Execution
(6/07/97)
Bid Award
(5/07/97)
Bid
Submittal
End of
20 Year Term
Commence
Construction
(30-60 Days)
(12 Months)
Delay Penalty of
$114 k/day
Plant Performance Penalty
$229 k/day
Unit 1 Bonus of
R$12,000/MW/month
for early start-up
Performance Bond (480 MW)
(7/98)
Comm. Ops.
SC Unit 1
(7/99)
Comm. Ops.
SC Unit 2
(7/00)
Comm. Ops.
CC Unit 3
Notes: <number>
<footer>
<header>
<date/time>

## Slide 15: EDC ExCom - Project Risks (April 97)
RISK
IPP Permitting Risk
Spur P/L construction delays due to environmental permits.
Bolivian govt.. inaction in granting P/L concession.
Spur P/L ROW acquisition
Gas supply/ P/L completion risk for phase 2 of IPP.
MITIGATION
Excused for acts of Brazilian Govt. authority.
Apply lessons learned from BBPL environmental permitting process.
Enron Corp. guarantee of IPP penalties to Eletronorte. IPP plant performance and delay penalties of $343 k/day. Loss of entire performance bond of $14.3 MM after 42 days.

## Slide 16: EDC ExCom - Project Risks (April 97)
RISK
Currency Risk - all project payments and costs are nominated and payable in Brazilian reais.
Enron delay in completion date.
MITIGATION
Pursue appropriate hedging strategy. Guaranteed capacity and energy tariff adjusted annually by the general price index (IGP). Dollar index the fuel components. Add +/- 5% economic equilibrium clause in PPA. Exposure to the extent that IGP does not track forex fluctuations.
Turnkey EPC Contract with delay damages and termination provisions which mirror damages in PPA. Insurance to cover physical damage loss.
More details about Currency Mitigation
Link U.S. Dollar debt and equity portion of capacity payments to IGP-M
  Approximates escalation at U.S. inflation rate over long term
  Does not adversely effect power price evaluation
Modify PPA to allow IPP to reopen Reais power price based on economic
equilibrium (including currency devaluation)
Index portion of energy price comprised of fuel costs from foreign suppliers to U.S. dollar
(based on law of sales of foreign company to Brazilian company and prior precedents)
Modify PPA to trigger change to U.S. Dollar indexation as soon as legally possible
Notes: <number>
<footer>
<header>
<date/time>

## Slide 17: EDC ExCom - Key Bid Exceptions (April 97)
Continue to pay capacity payments under force majeure
Eletronorte/Eletrobras buyout formula to include carrying costs and assuming contractual obligations of the IPP
Dollar and price indexation for gas supply payments in accordance with BBPL
Economic equilibrium clause (pending Eletronorte response to question)

## Slide 18: Competitive edge
All - Speed. Bid now!!!!!
  DNAEE feasibility study; site selection; Confab MOU; Gas MOU; Terms Sheet for EPC.
  Permitting steps in Brazil: 1) Feasibility studies 2) Preliminary License 3) Construction License 4) Operating License
Bolivian electricity exports.
  Levelize tax advantages:State - ICMS exemption; Municipal- ITBU,ISS,ITBI
  Capacity to be measured at delivery points. Line-out contingencies
  More difficult logistics for GT transportation
Local (El Paso)
  Early gas supply; Lower cost transportation.

## Slide 19: VICTORY!!! And the El Paso Legal Challenges
May 7 97.- Two bids were submitted.
  Enron US$ 41.20; El Paso US$55.40 (including diesel phase)
    Biggest Factor was putting 80% of the gas as a capacity payment not energy payment
    Second, Moving gas delivery to Phase II a year earlier than required in the Bid.
May 26 .- Enron submits a “Recurso Administrativo” to the El Paso bid. This starts a legal limbo of challenges and counter challenges that finally concludes at the end of July
  Commonly used in Brazil if a party did not adhere strictly to the rules
After effects: “Atmosphere of legal terrorism”

## Slide 20: Negotiations
Aug 11 97.- Start of negotiations
  Reading PPA; simultaneous translations; EN controls drafting; El Paso in the background all the time.
  They accept our Bid, but not the “Desvios”
  Aug 21 97.- Impasse, Issues and solutions drafted and sent to Eletronorte.
  Went around negotiations committee to Eletronorte and Eletrobras
Sept.- Issues not resolved. Several threats “Sign or we call El Paso”
  Indexation; Termination payments; Force Majeure;Arbitration; Guarantees
Oct.- Started “non-negotiations”, solo visits to Eletronorte
  Letter defining the issues
  Oct 30- Break-through on possible approach
Nov.- Resolving the “Legal Impediment”
  Legal Opposition to quantification, trigger points; accepted the restoration of the “initial conditions”
  Nov 17- Contract signed

## Slide 21: Negotiations - September Journal
Status at the beginning of the second month
Journal during the month
Sometimes it gets very dark before the light !!!

## Slide 22: Devaluation and PPA indexation
Restoration of initial economic-equilibrium for aspects outside the control on the parties
General “economic-equilibrium” is bounded by:
  Real Plan. Prohibits indexation in contracts; Decree 857 .- Permits pass-through of Foreign Contracts obligations
  Edital Rules. Denied US$ indexation or tied to the BBPL Rules, except for currency protection for gas after 5% movement
Concern with Enforceability:
  Legal Challenges
  Privatization transfer
Eco-Equil
Edital Rules
Real Plan

## Slide 23
Various Tariff adjustments under the PPA

## Slide 24
Dollar component indexed at CPI times FX
Reais Component
indexed at IGP-DI
US$ component of tariff awaiting Loan Commitments

## Slide 25: Securing the Gas Supply
Initially assumed that Petrobras would supply gas from the BBPL contract.
Secured terms from YPF/Andina to qualify the bid.
Petrobras offered terms for Argentinean gas and spur to be constructed inside Brazil, from Campo Grande.
Made our own independent proposal. Offered Participation to Petrobras on the Spur. Petrobras rejected.
Blessing!! Doing every thing on our own
Gas supply structure evolved over several months due to accommodate partners option and economic equilibrium:
  Initial disagreements with Transredes and Shell over interpretation.
  Secured EI option to provide 25% of the Gas and the capacity expansion of the spur
  Needed to create an economic equilibrium “fire-wall”
  Result: Had to negotiate transportation agreements with four companies, three gas commodity agreements, three interconnection, and one operation balancing agreement.

## Slide 26: Cuiaba Project - Model Structure -Pre-Bid
EN
Payments
Power Plant
Model
Pipeline Model
Bolivia
Brazil
Gas --YPF/Andina
YABOG
GTB
Notes: 1

## Slide 27: Dispatch Impact on Gas Commodity Payments
EPE less YPF
1. Enron can
Re-market
Expected 87% dispatch
Eletronorte Payments to EPE
Contracted Levels
Dispatch Levels
100%
80%
55%
55% 100%
3.
EPE payments to YPF

## Slide 28: Cuiaba Project Structure I -April 17, 1998
Eletro-
norte
EPE Ltd
TGS CI
GasBol
GasMat
BoliviaYPF/
Andina
YABOG
GTB
Hedge
Other
Sources
So Cone Gas
(Enron) CI
1
1
2
3
4
Notables
1. TBS eliminated --for regulatory reasons, not to complicate/ draw attention to transaction beyond P/L companies.
2. So. Cone Gas (100% Enron owned) provides 100% of requirement for EPE; @ 1.21 x CPI-.25% w/2% floor.
3. There will be no consortium; EPE is importer of record; and receives invoice from TGS; pays TGS at fixed price w/escalator; One PSI/COFINS tax as planned
ECT
Shell
27.5%
Enron
72.5%
Other
Markets
5
OBA
Transredes
4. At least 75% of Gas to be supplied from YPF; at most 25% of gas to be supplied by other sources
5. Sell gas below 55% TOP; capacity release.
6. Operating Balance Agreement: Nominations
that are requested within 29hrs of dispatch.
6
Notes: 1
6
2

## Slide 29: Final Contractual Arrangement Dispatch Impact on Gas Commodity Payments
TBS can
Re-market
Expected 87% dispatch
Eletronorte Payments to EPE
Contracted Levels
Dispatch Levels
100%
80%
55%
0% 55% 100%
3.
TBS payments to So.Cone (YPF Terms)
TBS less So. Cone
EPE less TBS

## Slide 30
Estrutura Contratual do Projeto
YPF
Argentina
YPF
Argentina
Produtores de Gás
Transredes
YABOG
Gas
TransBoliviano
Gasoduto
Bolívia Brasil
Transporte
Transporte
Transborder
Gas Service Ltd.
Transborder
Gas Service Ltd.
Transportadoras
Fornecedores de Gás
GasOriente
Boliviano
GasBol
GasOcidente
do
Mato Grosso
GasMat
EPE
EPE
Gerador de Energia
Comprador de Energia
LEGENDA
Fluxo físico de Gás/Energia
Serviços contratuais
Transporte
Venda de gás
Eletronorte
PPA
Eletronorte
CCE
Venda de Gás
Argentina
Bolívia
Brazil
Transporte
Southern Cone
Gas Ltd.
Central Bank Presentation

## Slide 31: Bolivian Precedents and Constraints
Law required to authorize Border crossing for the Spur pipeline
  Opposition of former President. Had to gain support of new president
Different Partner interpretation of project development rights
  Ours, they had a minority option to participate in our project.
  Theirs, it was a development project with Transredes ownership percentages.
Continual “political pressure” for Bolivian exports.
Continual linking on alleged commitments arising from YPFB/Enron agreements on BBPL
Requirements to negotiate Transportation agreements with four different companies
Impact. We thought we could negotiate all agreements fast
Reality.- Transredes agreed to participate Sept 98.
All dealings with Transredes, GTB and Gas Bol have been arms-length!!

## Slide 32: Site selection
Getting access to a good site is one of the key competitive aspects.
  Economics of water cooling, equipment delivery, site development, fuel delivery, transmission interconnection. ROW corridors, Permits, getting title.
Cuiaba Site changed several times.
  Wrong municipality; interference with airport expansion,future industrial zone.
    Note: Foreigners need a Federal authorization to hold agricultural land, or in frontier zone.
Got option to buy from local ally in future industrial zone.
  Route of Transmission ROW considered; Possible CEMAT Joint-Use
Cooling Water uncertainty - River or Wells????

## Slide 33: EPC Contracts for the Power Plant
“Naked Bid”.- Had terms from Siemens and Westinghouse, both not meeting the bid assumptions.
Aug 97.- Siemens Power Plant EPC. Phase I CO Sep 5, 1998
Transmission and Substation with Siemens and Amper
EE&CC “wrap contract” for both power and pipeline.
Contingencies
Technology Assurance guarantees - due to new Siemens GT technology
Water treatment out of original scope
Controversies
Changes of Owner Engineer after the “wrap contract”
Siemens/Amper division
Diesel Fuel flash point and quality
Maintaining capacity output during Phase II
Delays for Phase I - Meeting Guaranteed performance
Quality of Phase I construction. Meeting Permit requirements
Delay in technical data for developing Operating Accord.

## Slide 34: Diesel Contract for Phase I
Needed to harmonize the difficult logistics with the dispatch requirements of Phase I
  Petrobras REVAP refinery produces a special blend of diesel to meet Siemens specs.
  Dedicated 5,000m3 tank at terminal
  1690 Km distance to Cuiaba.- 6 days round trip
  Minimum take 79m3 per day. Max 1100 m3 /day
  Specific rules to avoid contamination during transport
  Acceptance testing procedures at the plant
  8500m3 Storage at plant.
  Plant to be dispatched as a peaker
Solution:
  Eletronorte agreed to dispatch for the minimum take.
  We will keep a four day supply on site for emergencies -- 4500m3
  Operating Accord establishes the yearly forecast. Eletronorte can deviate on a weekly basis ±15%.
  We are relieved of obligation if they dispatch more than the 15% limit and the 4 day supply runs out

## Slide 35: EPC Contracts for Pipeline
Secured the pipe for fast track contract with MOU with Confab.
Had initial terms with Techint for Pipe construction. Unable to finalize Contract. Negotiated Contract with Consortia of Pruessag and Bolinter/Conduto.
Contracts “wrapped” by EE&CC
Have delayed the start of construction several times:
  Oct 98 Feb 99 Current May 99
  Pipe already in fabrication and delivery
  Five construction “spread” (different fronts) are currently planned to compress the schedule
  Very naïve schedule assumed that we would get the Bolivian permits by Oct 98 given the political opposition

## Slide 36: Evolving rules, institutions and actors
During the development phase there have been a number of significant events that have caused delays or paths to develop the project.
  The decision of Brito to hold a bid, not negotiate
  The Bolivian elections of 1997
  The privatization of Cemat
  The decision of MME and Petrobras not to include this project as part of the BBPL scope.
  The change of DNAEE to Aneel
  The decision of Petrobras and Eletrobras not to participate in the Project.
  The emergence of ANP as an independent agency

## Slide 37: Project Financing
Bad Timing !!!!
  PIM out in August 98 just in time for the currency crisis
  No Commercial bank interest. OPIC; KFW/Hermes; BNDES
Key Due Diligence aspects
  Economic Equilibrium; Eletrobras system privatization; new market rules.
  EPC contract wraps and damages.
  Harmony of transportation agreements
  Consent documents
  Environmental impact on pipeline sensitive areas
  Emissions during diesel Phase
  Future Gas LDC in Mato Grosso. Flow of Funds
Central Bank rules for Currency transactions
  Monthly remittances
  Take-or-pay payments

## Slide 38
Fluxo Conceitual de Caixa
ELETRONORTE
EPE
Tarifa de Eletricidade
Pagamentos Externos
Pagamentos Internos
EPE O&M (R$)
Fornecimento de Energia
Serviço da dívida EPE R$
Dividendos ao acionistas brasileiros
Pagamentos de gás à TGS
EPE O&M (US$)
Serviço da dívida EPE (US$)
Dividendos aos acionistas estrangeiros
Central Bank Presentation

## Slide 39
Operando em capacidade plena e no momento de serviço da dívida máximo, a EPE efetuará os seguintes pagamentos mensais
PAGAMENTOS INTERNOS R$ 1 milhão
PAGAMENTOS EXTERNOS Equivalentes a R$ 10 milhões
Salários/Escritório
O&M Diversos
Manutenção Menor
Serviço da Dívida em Reais
Gás Commodity
Transporte de Gás
Seguros e Gerenciamento
Manutenção Maior
Serviço da Dívida em US$
Transferências Mensais Regulares da EPE
Central Bank Presentation

## Slide 40: Remaining Aspects
Establish Compensation Account (Eletrobras Liquidity guarantees)
Commercial Operation of Phase I
Development of River Water Intake and treatment
Permitting and Construction of Transmission interconnection Phase III
  Phase II entering construction
Concession approval Pipeline Bolivia
  Indigenous people agreement; decree to perfect ROW
Pipeline in Brazil
  ROW decree; Funai agreement, archeological survey
Secure Financing
  Due diligence finalization
  Consent documents; Common loan agreements
  Commitment letters; Conditions Precedent
Implement Economic-Equilibrium Annex 11
New!!! - Privatization of Eletronorte/Furnas