## Slide 1: SAP-Financials Data Warehouse Project Update
Notes: <number>
<footer>
<header>
<date/time>
1
1

## Slide 2: SAP-Financials Data Warehouse Project Update
Benefits
  Provide the SAP reporting functionality the Business Units need
  Limit the extracts from SAP R/3
  Use Common Data Definitions across Enron Enterprise
  Leverage-off HRIS and EBS models (proof of concept)
  Provide an open architecture allowing Business Units to leverage their development resources and tools of choice to make new formatted reports and enable end user ad-hoc analysis.
Tactics to Minimize Risks
  Clear Project Objective(s)
  Provide SAP information to the businesses without delay
  Data Integrity / Clean Data
  Manage Expectations

## Slide 3: SAP-Financials Data Warehouse Project Update
Objectives
  Develop a reporting solution for the ENRON Business Units which will make SAP R/3 data available in a more open, accessible environment.
  Create the database and reporting/analysis tool architecture necessary to support the development of formatted reports, ad-hoc queries and other analysis by the Business Units.
  Provide the appropriate level of system access and tools to the various skill levels of users including IT Developers, Power Users and End-Users.
  Get corporate and/or Business Unit IT resources working on an initial set of formatted reports.
  Set-up the on-going organization (or collection of Business Unit decision makers) that will prioritize on-going report development requests.

## Slide 4: SAP-Financials Data Warehouse Project Update
Timeline
Phase One - August, 2000
  Provide access to SAP data contained in the Acta "Cost Analysis" and "Accounts Receivable/Accounts Payable" Rapid Marts for reporting and analysis.
  Provide access to SAP data contained in as many of the other Acta Rapid Marts for reporting and analysis as possible, without affecting the August, 2000 delivery date. (These Rapid Marts include: Inventory Management, Project Systems and Profitability Analysis).
Phase Two - January, 2001
  Provide access to the balance of the SAP R/3 data, as determined by the Business Units.
Phase Three - TBD by Business Unit Needs and Budgets
  Supplement the SAP R/3 data with information from other Business Unit legacy systems, as needed.

## Slide 5: SAP-Financials Data Warehouse Project Update
Timeline - Phase I
Timeline - Phase II
  August to end of January, 2001
  TBD (Prioritized business needs will drive iterative delivery dates).

## Slide 6: SAP-Financials Data Warehouse Project Update
Update / Accomplishments to-date
  Purchased Acta Extraction Tool and Rapid Marts.
  Identified and signed Acta partner, Sense Corp. Consulting who will configure Acta Rapid Marts (phase one).
  Obtained promise of support from Enron Net Works’ UNIX Hardware Group.
  Received and installed one of two Acta servers necessary to begin SAP extractions. (Database Server due July 24th).
  Held Reporting Tool Demonstrations and obtained Business Units’ choice for reporting and querying tool.
  Signed Enron-Enterprise License for BRIO Reporting Tool (any project in any Business Unit can use it for free).
  Initiated Reporting Council (8 Representatives have been named).

## Slide 7: SAP-Financials Data Warehouse Project Update
Next Steps
  Obtain and install Acta Database server.
  Begin Configuration of Rapid Marts (eight weeks).
  Conduct on-going SAP/Acta Extractions as Rapid Marts come on-line.
  Implement “Reporting Council” to identify and prioritize reporting needs across Enron Business Units.
  Build team of technical SAP Data Analysts (from COE) and BRIO Report Developers
  Begin creating formatted reports using BRIO development tools and Rapid Mart Data.
  Test reports and server performance of existing (DEV/QA) environment, then order appropriate servers for the Production environment.
  Begin Phase II analysis (balance of SAP data) in parallel.

## Slide 8: SAP-Financials Data Warehouse Project Update
Project Team (10 - 13 People)
  Data Warehouse Architect/Project Manager
  1-2 COE SAP Basis Resources
  3 FTE COE Data/System Analysts
  Oracle DBA
  2 ACTA Works Extraction Developers
  2-4 Reporting Tool Developers

## Slide 9: SAP-Financials Data Warehouse Project Update
Budget
  Total Budgeted: $3,795,000
  Phase I: $3,135,000
  Phase II: $ 660,000
  Total to-date: $ 432,276

## Slide 10: SAP-Financials Data Warehouse Project Update
Software Costs: (July, 2000)
Acta Works (data extractions) and four Acta Rapid Marts: Cost Analysis, Accounts Receivable / Accounts Payable, Inventory Management, and Profitability Analysis. (Beta versions for Project Systems, Asset Mgmt, and FERC are provided with no additional cost). $400,000
Informatica Extraction, Transformation and Loading Tool $150,000
Recommended Reporting and Ad-hoc Querying Tool. (Business Units may elect to purchase their own reporting tool to meet their specific needs).
BRIO $2,4000,000 for first 3 years - per year cost $800,000
Total Software Year One $2,950,000
Subsequent Years $900,000

## Slide 11: SAP-Financials Data Warehouse Project Update
Hardware Costs (July, 2000)
Acta Works UNIX Servers $100,000
(1 Production and 1 QA / Development).
Data Warehouse SUN Enterprise Servers $700,000
(1 Production SUN 6500 and 1 SUN 4500 for QA/Development)
Reporting Tool / WEB NT Servers $ 45,000
(2 Clustered for Production and for 1 Development)
Total Hardware $845,000
Grand Total: Hardware and Software Year One $3,795,000
Subsequent Years’ Software $900,000