## Slide 1: Clean Energy Solutions (CES) LLC
Holds exclusive license on NOxTech
50% owned by EGM
  Provides marketing, structuring & commodities
50% owned by Mitsui-Babcock
  Expertise in boilers/process/manufacturing
  Provides implementation on all projects
  Ultimately provides performance guarantees
  Paid $2.25 mm + $1 mm of future development costs
Could be vehicle for other technologies

## Slide 2: TVA Transaction Summary
Phase 1:
  1 MW test in Scotland on TVA Coal
  Off-ramp for TVA and/or EGM
  Scheduled for July 28
  TVA pays for full cost of test
Phase 2:
  200 MW demo at Kingston 9 (November 2001)
  Mitsui-Babcock implementer for design, engineering & manufacturing
  TVA pays for full cost of demo (whether it is successful or not)
  Installation by TVA in Q4 2001
  No NOxTech process performance guarantee
  Test completed in Q1 2002
  EGM receives performance bonus based on SCR avoided cost (if successful)
    Estimated EGM profit on first demo = $3 million
  Phase 2 demo for each of three TVA Groups of identical boilers

## Slide 3: TVA Transaction Summary
Phase 3:
  TVA option to purchase additional units within TVA Group
    Identical units (typically 3 or 4 other units) in each TVA Group
    TVA must notify EGM within 90 days of Phase 2 completion
    EGM not compelled to install Phase 3 units if Phase 2 not successful
  TVA pays full cost of installation
    Good cost estimates from Phase 2 demo
    Phase 3 units identical to Phase 2 demo
  No process performance guarantee
    TVA utilizes performance from Phase 2 as indicator
  Total potential units = 13
    Units installed over 2-3 years in outages set by TVA with 8 months notice
  EGM receives performance bonus based on SCR avoided cost
    Estimated EGM profit on all units = $20-$30 million
    Minimum EGM profit = $0.5 million per unit

## Slide 4: Risks
Cost
  Cost reimbursable
  No EGM risk
Schedule delays
  Damages: $7000/day; maximum of $1MM/unit
  Back-to-back with Mitsui-Babcock (MB)
  Performance bond with MB for 100% of damages
Process guarantee
  No performance guarantee on NOxTech system
  Pressure part guarantee
    Back-to-back with Mitsui-Babcock
    Damages; maximum of $600,000/unit
    Performance bond with MB for 100% of liquidated damages
  Performance bond with Mitsui-Babcock
    $10 million on first demo unit
    20% of contract value for subsequent units
    Covers all Mitsui-Babcock guarantees & warranties

## Slide 5: Risks
Construction (Cost & Delays)
  TVA manages all construction
  TVA bears all construction risks (cost and delays)
  No risk to EGM
Intellectual property (NOxTech patent)
  CES LLC holds “Freedom to Operate Opinion”
    Over 400 patents reviewed by McCutcheon Doyle
    Very low risk of infringement (1%)
  Damages limited to “lost profits” of other patent holders
    Lost profits likely calculated as lost royalties
    Reasonable royalty of $0.2 to $2 million per unit
  $100 million Intellectual Property indemnity to TVA
  “Probable” intellectual property exposure less than $1 million

## Slide 6: Business Outlook
Integrate with other EGM businesses
  Emissions trading
    “Allowance peakers”
    Create/fill L-T allowance positions
  Fuels: coal & gas (used in NOxTech process)
  Power
  Financing
Acquire/develop/commercialize other technologies
  NOx, SO2, Mercury and Particulate Matter
  Heat rate improvements
Potential CES market opportunity
  NOx SIP Call = $200 million (2002-2004)
  UK Market
Create vehicle/mechanism to capture full value
  FASB 125/140 structure
  IPO/Private placement