## Slide 1
Project Doorstep
EES – Europe
Office visited- March 13 - 20, 2001
Report Issued- March 23, 2001
Confidential

## Slide 2
EES –Europe Project Scope/Team
Project Scope:
We performed an on-site review of processes, procedures and controls performed in London, Oxford and Madrid that support the activity related to Enron Energy Services (EES) Outsourcing, Enron Direct and Enron Directo. Our procedures included interviews with key commercial and commercial support personnel. Included in this review was a test of transactions, contracted by Enron Direct and Enron Directo, from deal execution to settlement in the Oxford and Madrid offices. We did not review ETOL, Torpy and Eurpac activities.
Door Step Team Members:
Sheila Glover - Energy Ops
Vlady Gorny - MRM RAC
Veronica Valdez - MRM RAC
Katie Bosdet - Arthur Andersen

## Slide 3
EES – Europe Executive Summary
EXECUTIVE SUMMARY
Enron Direct - Oxford
Effective sales operation in attracting customers.
The Oxford operation has taken on a number of initiatives to address significant growth in volumes, customers and sites.
Conservative pricing of customer contracts.
NETA requirements in 2001.
Enron Directo - Madrid
Efficient and tight operation.
Experienced and knowledgeable personnel.
Immature retail market in Spain.
EES – London Outsourcing
One deal in the portfolio (City Reach), wholesale risk only - hedged with the desk
Neccessity to implement a Retail/EAM/O&M portfolio framework before expansion of Outsourcing business

## Slide 4
EES –Europe Interviewees
London Office:
Michael Brown - COO, Enron Europe
Matthew Scrimshaw - EES, President and CEO
Charles Crossley Cooke - Head of Middle Market
Stuart Rexrode - Head of EES Outsourcing
Graham Dunbar – Financial Controller
James New/Chris Costares - Risk Management
John Parker - Risk Manager, EES Outsourcing
Paul Day, Murray Harrington - Audit Managers, Arthur Andersen
Enron Direct, Oxford:
Enrique Gimenez, General Manager
Mark Holloway - Operations Director
Rob Hill - Customer Services Director
Ian Stockbridge - Credit Control Manager
Phil Reilly - Finance Manager
Hayley Woolford - Direct Sales Manager
Louise Boland, Pricing
Chris Murray, Information Technology Support Manager
Enron Directo, Madrid:
Jose Luis Gomez Banovio - General Manager
Jose Luis Novo - Sales, Pricing
Antonio Benitez - Operations Manager
Paulino Martinez - Controller

## Slide 5
EES – Europe Findings (1)
Detail Comments Provided in Addendum Notes
Items to be addressed
Action Steps)
Target date
Person responsible
  • Credit/Collection Processes
– AR aged balances
1. Produce reports to understand the facts
30-Apr-01
Ian Stockbridge/Phil Reilly
2. Set 5 Objectives to measure against
30-Apr-01
Ian Stockbridge/Phil Reilly
– Queries (APQs)/Billings/Collections
1. See below re: Query resolution
2. New Budget Plan product
30-Apr-01
Lucy Corfield
3. Bill customers with APQ
31-Mar-01
IT
4. Collect DD more frequently
15-Apr-01
Lucy Corfield/Ian Stockbridge
5. Credit Card Payments
31-May-01
Phil Reilly
  Criteria and procedures for credit evaluation
  Define credit policy and obtain approval from Corporate Credit
  Expand testing to further investigate: 1)missing invoices on system, 2) no contract available
1. Issue Credit policy
30-Apr-01
Ian Stockbridge
2. Restructure chasing priorities
30-Apr-01
Ian Stockbridge
• Customer Services
– Backlog of customer queries (~8,600
1. Customer Services prioritise by value
31-Mar-01
Rob Hill
outstanding queries)
2. Opening ETOL resolution centre
31-Mar-01
Rob Hill/Mark Holloway
– Rate of query resolution
3. Extended Training Programme
31-Mar-01
Rob Hill
4. Motivation Scheme
31-Mar-01
Rob Hill
See detailed plan attached
Further testing will be done by London
30-Apr-01
Graham Dunbar

## Slide 6
EES – Europe Findings (2)
Detail Comments Provided in Addendum Notes
Items to be addressed
Action Steps)
Target date
Person responsible
• IT Strategy
– Development of ED model (centralization vs.
1. Centralised Management
30-Apr-01
Dan Maitland
decentralization)
2. Best practices incorporated
30-Apr-01
Dan Maitland
– Scalability of RM processes for ED businesses
See below
-
-
– Personnel retention
1. Retention contracts
Ongoing
Charlie Crossley Cooke
2. Spread knowledge throught IT
Ongoing
Dan Maitland
• Risk Management Processes
– Capture and quantify exposure of the retail risks
1. Assess book calculations under NETA
31-Mar-01
Louise Boland/Chris Costaras
embedded in the ED model
2. Rebook deals for NETA
31-Mar-01
Chris Costaras
3. Improve process for running book
30-Jun-01
IT/Chris Costaras
4. Review PMA's (see below)
Ongoing
Phil Reilly/Louise Boland
– Large actualization adjustments to P&L
1. Analyse PMA's to date
31-Mar-01
Graham Dunbar
2. Identify areas of concern
31-Mar-01
Graham Dunbar
3. Review Ledgers for errors
31-Mar-01
Phil Reilly
4. Review Book Calculations (NETA)
31-Mar-01
Louise Boland
5. AA Statutory Audit
09-Apr-01
Arthur Andersen

## Slide 7
EES – Europe Follow-up Items
EES EUROPE
Implementation of Action Steps
  Policies
  Procedures
  Metrics
Implementation of NETA Requirements
New EES Outsourcing deals with significant non-commodity risks