## Slide 1: EnVision Status Reporting and Accountability Review Steve Whitaker Version 0.3 28 March 2001
Notes: 1
1
1

## Slide 2: Problem Statement
Since EnVision was conceived we have seen a number of changes:
  Overall scope has increased considerably
    No longer simply a program of initiatives for the Middle Office
    Now covers:
      Middle Office
      Financial Operations
      Remote Offices
      RAC
      Architecture and Integration
      E-Business.
  This is in line with the need to provide status reporting for all IT projects – not just those within the Middle Office
  As a result the EnVision meeting has now become too large and dysfunctional
    Initial momentum has slowed down and we are loosing traction
      Majority of the meeting is not relevant for individuals
    Discussions are too detailed and we labour on specific points
    We are not seeing enough commitment or accountability for the deliverables being asked
    We have a retrospective focus.

## Slide 3: Requirements
Senior Management needs to be able to make executive calls on projects, priorities and resources based on consolidated, key information
  Clarity on list of projects being addressed
  Prioritisation capability
    Distillation of pertinent facts
    Need to be able to make a call on where resources should be focused
  Timeline for delivery
    Understanding of why things deviate from plan
      Technical
      Resources not focused
      Requirements not defined etc.
  Clarity of resources available
    Commitment of available resources
    Resources dedicated to projects
      Who is working on what
    Need more accountability for deliverables
    Understanding and approval for resource re-allocation
    Move towards more professional resource management
      Business and IT
  Understanding of where your money is being spent.

## Slide 4: Going Forwards
We need to create a vision for our application development, tied to an overall direction
  We need to be able to create a vision and set direction for the people who work for us
  Department heads should be able to set direction within an overall framework
    Create a vision – not so far in the future (6-12 months)
      What are we trying to achieve
      What are your inputs
      What are your outputs
    Information flow through departments
    How that information should be processed
    Interactions and handoffs to other departments
    Determine and direct the projects required to get there
      Operational, Strategic, Maintenance and Speculative
    Establish your core objectives
      Not just your line objectives
      Additional focus required on process improvements and application development
    Measure ourselves against that vision
  IT need to be able to commit to clearly defined deliverables
    Deviations from this needs to be raised and communicated
    We need to achieve a better balance between crisis management and project delivery
  OBVIOUSLY NOT FORGETTING THAT WE DO NOT WANT ANY UNECESSARY BUREAUCRACY
    Re-think the organisation and framework that WAS EnVision in light of the expanded scope
      Still need an overall framework
      Meetings need to be smaller, snappier and more focused
    Performance metrics need to be established
      Equal responsibility between Business and IT.

## Slide 5: Proposed EnVision Framework
Other Areas Supported by IT
Cross Prioritisation
Fernley Dyson
Ted Murphy
Michael Brown
Mark Pickering
Steve Whitaker - Chair
FinOps & Tax
Melissa Allen - chair
Nuala Bennetts
Diccon Vokins
Phil Yoxall
Remote Offices - TBC
Naomi Connell
David Williams
Barry Sangster
James Britton
Middle Office & Reg Rptg
Mike Jordan - chair
Ian Sloman
James New
Brian Hudson
Phil Yoxall
Paul Bromley
Sam Kemp – Global Data
RAC
David Hardy
Tricia Donnelly
Phil Yoxall
Commercial & Risk Management
Power
Commercial &
Risk Management
Gas
Metals - TBC
Mike Jordan
Andrew Cornfield
Howard Carter
Nigel Grace
Bob Campbell
EnronCredit - TBC
John Paskin
Richard Sage
Bryan Seyfried
David Wall
EGM - TBC
Cindy Horn
Iain Greig
Kevin Sweeney
Programmes
Departments
Architecture & Integration
EES
E-Business
EBS
Departmental priority calls
Departmental issues
Resource re-allocation
Agreed consolidated status
Cross Departmental priorities
Cross Departmental issues
Cross Departmental Resource allocation
HR

## Slide 6: Proposed EnVision Framework
Commercial & Risk Management – Every two weeks
  Already exist for Power and Gas
    Prioritise tasks for next two weeks
    Assess deliverables due and status against those deliverables
      This period/ next period
    Provide an indication of resource/ task allocation over next two weeks
  Proposed changes - NONE
    Utilise already effective meetings
    Information to be collected by Project Office for:
      Dissemination to potentially impacted areas - downstream
      Consolidation for Cross Prioritisation
    Need to assess Power meeting post NETA.
Programmes - Various
  We should not enforce a different meeting structure for programmes of work that already exist, namely:
    Remote Offices – scoping and planning
    EnronCredit – re-planning
    Metals – scoping and planning
    EGM - ongoing
  However, we will request status to enable consolidation where applicable
    Most programmes will want to use the project office anyway as we will still perform status consolidation
  Programme representatives do not have to attend the Departmental Meetings unless
    They wish to raise a specific issue that concerns that department - optional
    Alternatively raise this with the project office to ensure that it is tabled at the appropriate forum.

## Slide 7: Proposed EnVision Framework
Departments – Every two weeks
  Middle Office and RAC combined – Replace existing EnVision meeting
  FinOps to have its own meeting – Already scheduled
  More work required prior to meeting
    Project Office
      Greater involvement in projects rather than just status collation
      Chase actions, deliverables and issues on an ongoing basis rather than just prior to a meeting
      Creation of a report pack that is specifically for each meeting – not everything under the sun
    Business & IT
      Review of report pack prior to meeting – don’t just prepare your status – we do NOT need a meeting for this
        You will need to confirm the priorities for resources at the meeting
      Timely resolution of issues
      Focus on key deliverables
  Objectives of meeting
    Agree status and new timelines where applicable
      We will not go through ANY status at the meeting unless it is in dispute
    Assess deliverables due and status against those deliverables
      This period/ next period – agreed at previous meeting
      Again we will not go through ANY deliverable status at the meeting unless it is in dispute or has been missed
    Resolve departmental issues & agree issues for escalation
    Resolve departmental priority calls & agree priority calls for escalation
  Why is this different?
    Less people, therefore, greater focus
    Information given prior to meeting will be more comprehensive and focused on the department
      It will also be jointly owned as it will contain information from the Business and IT
    The primary focus of the meeting is to ensure that we are all moving in the right direction TOGETHER – not status
    Greater understanding of the factors that have influenced status and will affect decisions going forwards

## Slide 8: Proposed EnVision Framework
Cross Prioritisation – Every Four weeks
  Project Office will provide a consolidated report for discussion
    Also provide continuity by being present at Departmental and Cross Prioritisation meetings
  Objectives of meeting
    Review status
    Assess performance
    Resolve cross departmental issues and priority calls.
  Why is this different?
    Greater filtration of information
      Information is geared towards intended audience
    Only focused on resolving issues that could not be resolved at a departmental level
    Able to review hot spot areas and act accordingly.

## Slide 9: How Will This Work and What Are We Reporting?
Status
Plans
Status Vs Plan
Project Priorities
New Projects
Maintenance work
Issues – MTG FOCUS
Key Deliverables – MTG FOCUS
Resources & Costs
Cost of Projects
Budget
Cost to date
Resource Allocation
Actual FTES used – including working on support & maintenance
FTES required for next 4 weeks
Priority calls and re-allocation – MTG FOCUS
Vision & Performance
Vision statement
KPIs
information flow – Current and Future
Current Project Classification
Speculative
Strategic
Project performance
Deadlines hit
Deadlines missed
Dev/ Support ratio
Operational
Support/ Maintenance
Middle Office
Risk Management
Documentation
Settlements
Trade Accounting
Working Capital
Global Data
RAC
FinOps
Financial reporting
Accounting & Compliance
P2P
Financial Planning
Programmes – Content tbc
Programmes
Departments
Commercial
Project Office
Project Office
Collate
Consolidate
Consolidate
Collate
Collate
Collate
Cross Priorities
Consolidate
FEEDBACK
FEEDBACK

## Slide 10: What Won’t This Provide
  Ability to make on the spot priority calls – INTERCEPTION POINTS
    E.g. IT resources required to fixed production issues
    This will have to be made through existing channels
      However, we need to review how these are communicated
  It will highlight the fact that resources had to work on other areas – initially retrospective
    Resource allocation will reflect this – if people fill their time in correctly
    As we progress we should be able to plan more effectively for these eventualities – CONTINGENCY
  It will highlight problem areas where this occurs frequently so we can mitigate the impact