## Slide 1: EES / EWS Integration
Project Scope and Approach

## Slide 2: Objectives
Document high level EES and EWS processes from Origination through Invoicing
Document systems (as of December 2001) to be utilized to support EES and EWS processes
Identify opportunities for integration of processes and systems to be implemented by June 2002

## Slide 3: Scope
Primarily focused around Power commodity
Covers Origination, Structuring, Trading / Scheduling, Risk Management, Volume Management / Settlement, and Invoicing Business Areas
Includes the following deliverables
  Process Maps (showing major activities and responsibilities of each business area)
  System Overlays of Process Maps (based on anticipated systems as of Dec 2001)
  Business Interfaces (for each business area)
  Opportunities for Functional Integration (for each business area)
  Key Reporting Needs (for each business area)
  Issues List
Deliverables to be generated for each business area, EES, EWS, and combined EES/EWS
Deliverables to be generated in a 3 week timebox (Mon Oct 15 – Fri Nov 2)

## Slide 4: Approach
Week 1 – Conduct Business Area Meetings
Week 2 – Generate Documents / Follow-up
Week3 – Conduct Integrated Meetings
Oct 15 - 19
Oct 22 - 26
Oct 29 – Nov 2
Conduct Individual business area meetings across EES and EWS
Identify processes, systems, interfaces, opportunities for integration, and reporting needs
Identify issues to be resolved
Generate business area documents
Generate integrated documents (EES, EWS, combined EES/ EWS)
Follow-up on issues
Review documents with individuals involved in business area meetings
Confirm technology findings with IT
Conduct EES review meeting
Conduct EWS review meeting
Update EES and EWS documents
Conduct EES and EWS Meeting
Finalize documentation

## Slide 5: Meetings
Todd Busby (EWS and EES Origination, Structuring, and Risk)
Corry Bentley (EWS Trading and Scheduling)
Stacey White / Christin Albrecht (EWS and EES Risk respectively)
Thresa Allen / Murray O’Neil (EWS and EES Volume Management, Settlement, and Invoicing respectively)
Page ? (EES Origination)
Jeff Richter / Narsima Misra / Dale Furrow (EES Trading – West/Canada, East, URM respectively)
Vladimir Gorny (EES Site Profiling and Asset Management)
Fred Kelly (or designee) (ROC)
Business Area Meetings
Integrated Meetings
EES Integration (EES personnel from above)
EWS Integration (EWS personnel from above)
Cross EWS / EES Integration (all personnel from above)

## Slide 6: Meetings
Steve Nat (EWS IT)
Pablo Pissanetzky (EES IT)
IT Confirmation Meetings

## Slide 7: Meetings
Introduction and Objectives
Process Map Development (entities, flow, responsibilities)
Business Interfaces
Key Reporting Needs
Systems Overlay (anticipated as of Dec 01)
Opportunities for Integration
Summary and Issues/Actions Review
Business Area Meeting Agenda (approx. 2 hours duration)