## Slide 1: Fort Pierce Repowering Project 04/24/01

## Slide 2
©2001 Enron Proprietary and Confidential Information
Recommendations
Go forward with the project on a combined-cycle basis with a commercial operation date of October 2002.
Current development cost it at $3.6MM with capital exposure of $2.4MM.
Monitization at cost is likely with TECO or other 3rd party
Contract strategy with Ft. Pierce to sign the following:
  Participation Agreement
  Ground Lease
  O&M Agreement
  Tolling Agreement (Steam Agreement)
  Interconnection Agreement
Suspend engineering expenditures as of Friday, April 27, 2001 and authorize the following expenditures until the completion of contracts with FPUA.
  $600K of engineering support to cover expenditures from April 15th – April 27th (two weeks)
Enter into Physical Delivery Gas Contract with Gas Desk through Phase VI and purchase long term Phase VI capacity from FGT. (May 4th – May 11th)

## Slide 3
©2001 Enron Proprietary and Confidential Information
Estimated Project Valuation - Comparison
ASSUMPTIONS
Pre-tax analysis
278 MWs of output from June 2002 – 2031
Heat Rate
  Combined cycle heat rate of 7,080 btu/kWh HHV
  FPRP heat rate of 6,068 btu/kWh HHV
93% Availability
Gas prices based on ICF curves plus EA transport surcharge
Power prices based on ICF curves
50/50 Debt to equity ratio
Project life = 30 years (25 years + 5 year option)
Terminal Value = Assumed 0
Case 1 assumes June 2002 start using a by-pass stack
Case 2 assumes October 2002 start using a dump condenser
Case 1 VS Case 2
Simple-cycle June 2002; Combined-cycle October 2002
Combined-cycle October 2002
NPV17% = $24.3MM NPV17% = $19.2MM

## Slide 4
©2001 Enron Proprietary and Confidential Information
Major Project Risks
Commercial Risks
  Large capital expenditure without gain of asset(s)
  Material change in long-dated view of Florida market
  Default of FPUA under the Steam Agreement may collapse the value of the asset
Development Risks
  Air permit may not allow simple-cycle operations with emissions in excess of 25ppm NOx (currently, Mitsubishi’s maximum guaranty is 25ppm NOx).
  Supply of Natural Gas
  Suspend activities until FPUA has signed PA, Ground Lease, O&M and Tolling Agreements
  PA has unilateral termination by Enron through October 2001
  Step-in rights (legally questionable) thin ability for Enron to build its own steam turbine to re-capture value of Steam Agreement in electric capacity & energy minus construction time
  Change by-pass stack to dump condenser which allows for simple-cycle like operation under projected air permit
  Enter into a Physical Supply Contract with East Desk Pre-FGT Phase VI & purchase long term Phase VI capacity

## Slide 5
©2001 Enron Proprietary and Confidential Information
Major Project Risks
Development Risks (continued)
  Interconnection and transmission agreements
  FPUA Interconnection at King Plant
  FPUA Transmission
  FPL Transmission
  Certain
  In flux, physical capacity exists but FPUA only has direct control of 135MWs of the 196MWs required; Vero Beach has contractual control of remaining. Recommend Enron negotiate directly with Vero and FMPA for the gap and later with Grid Florida as these transmission lines will be ISO jurisdictional.
  FPL presently cooperating with Enron/FPUA on upgrading the present agreement. Net flow is into grid therefore no major hurdles are anticipated.

## Slide 6
©2001 Enron Proprietary and Confidential Information
Major Project Risks
Development Risks (continued)
  Mitsubishi turbine
Finance Risks
  Off-balance sheet financing in Turbo Park
  EPC Wrap
Legal Risks
  Contract Enforceability
  Requires Japanese consent to move into this project. Development team working on consent and technical modifications.
  Rush nature of project makes Turbo Park compliance tricky. Could potentially trip over hard cost before reaching criteria for Turbo Park Phase I. Pushing project into Fall 2002 will help to mitigate
  The preferred “wraps” of Turbo Park seem to be above EPC wraps offered in today’s construction market. May have to settle for a series of wraps or pay significant premium to achieve total project financing. May have to find alternative construction financing in a vehicle such as AIG High…
  No certainty that certain protections afforded Florida Municipalities (for example, sovereign immunity) are effectively waived or that other FPRP Protections (for example, step in rights and indemnities) are enforceable. Qualified opinion of outside counsel will be obtained as to enforceability.

## Slide 7
©2001 Enron Proprietary and Confidential Information
Major Project Risks
Legal Risks (continued)
  Limited Recourse
  Transmission and Interconnection
  Limited Development Discretion
  Even if contracts are fully enforceable, FPUA’s ability to collect damages against FPUA is limited by FPUA’s prior pledge of FPUA revenues in connection with bond financing. With certain exceptions, FPUA’s liability is limited to $3MM. Specific performance remedy to compel FPUA to perform contract obligations subject to certain limitations.
  There is no firm transmission available from FPUA absent future agreements with FPUA and FMPA, which agreements may not be obtained. Enron can take legal action to compel access to transmission or construct own transmission facilities.
  Aesthetic Agreement to placate city gives city unusually broad discretion over development costs and schedules based on city planner’s subjective evaluation of project aesthetics. Aesthetic Agreement provides appeals process to Florida Circuit Court.

## Slide 8
Fort Pierce Repowering Project L.L.C. (“FPRP”), a wholly owned subsidiary of Enron Americas, intends to repower the existing power generation facilities of the H. D. King Plant (“King Plant”) owned by the Fort Pierce Utilities Authority (“FPUA”) located in Fort Pierce, Florida.
The repowering will require FPUA to lease to FPRP approximately two acres of land on the King Plant property on which FPRP will build a new power generation facility (“FPRP Plant”) consisting of a Mitsubishi 501F combustion turbine (the “Turbine”) and a Cockerill Mechanical Industries (“CMI”) heat recovery steam generator (“HRSG”).
A total of approximately 278 MWs will be generated by the FPRP Plant and the King Plant, an estimated 196 MWs of net output from the FPRP Facility and 82 MWs from the #7 and #8 steam turbines in the King Plant.
The combined-cycle heat rate of the facilities will equal approximately 7,080 btu/kWh high heating value (“HHV”). Steam will be sourced to the King Plant at a heat rate of 9,500 btu/kWh HHV (an improvement to the 12,000 btu/kWh HHV steam it is currently generating from its two existing boilers). Due to this arrangement, FPRP will enjoy a reduced net heat rate equivalent of approximately 6,068 btu/kWh HHV, provided the King Plant is running.
FPUA intends to reimburse FPRP for consumed steam through a natural gas fuel allocation. In the event the King Plant is not running its steam turbines, FPRP has the right, but not the obligation, to toll the #7 and #8 King Plant turbines and generate the estimated 278 MWs for its own account at the combined cycle heat rate of approximately 7,080 btu/kWh HHV.
©2001 Enron Proprietary and Confidential Information
Deal Overview

## Slide 9
Combined-cycle power generation in Florida by Fall 2002
Attains combined cycle heat rate without requiring FPPSA approval
Innovative solution provides for combined cycle equivalent heat rate power generation via the implementation of cogeneration
Municipal as well as FP&L load service opportunities
Document status/terms
  Structured to be Turbopark compliant (subject to bank review)
    FPRP to be sold out of Turbopark prior to commercial operations
  HRSG contract executed with CMI (completion milestone payments commence June 2001)
  Remainder of definitive agreements executed by FPRP & FPUA by May 2001
    Fort Pierce City Commission > 04/23/01
    FPUA Board Meeting > 04/24/01
    FPUA obligation to buy steam if FPRP generating
    FPRP option to toll FPUA units when not dispatched by FMPA for power sales to third parties
    Specific performance remedy
      Right to substitute steam turbine at FPRP Facility if King Plant is not operating
©2001 Enron Proprietary and Confidential Information
Deal Highlights

## Slide 10
Estimated Completion
Environmental Resource Permit (ERP) issued March 2001
Public approvals
  Site plan/conditional use February 2001
  Ground Lease April 2001 (City vote 4/23/01)
FPUA remediation/tank removal > clean site delivered April 2001 (90% complete;
closing letter due 4/30/01)
Final contracts with FPUA (CPs to continuing) May 4, 2001 (FPUA vote to approve 4/24/01)
Gas Supply Agreements May 4, 2001 (If CPs are met)
Transmission
  FP&L Feasibility Study May 2001
  FPUA provides transmission capacity to FP&L May 2001
MHI Turbine
  Assignment of Contracts May – June 2001
Air Permit granted August 2001
Architectural compliance Ongoing
©2001 Enron Proprietary and Confidential Information
Development Status (Updated)

## Slide 11
Estimated Completion
Selection of EPC contractor May 2001
Project phased into Turbopark May 2001
  Commence hard costs
Ground breaking (contingent upon Air Permit) September 2001
Combined Cycle (Cogen) Operations October 2002
©2001 Enron Proprietary and Confidential Information
Construction Timing

## Slide 12
©2001 Enron Proprietary and Confidential Information
Projected Costs
$MM
Committed Costs (expenses through 4/15/01) $3.4*
  Engineering $1.7
  Development $1.0
  Legal $0.7
Current DASH Request (expenses through 5/30/01) $4.7
  Engineering $3.5
  Equipment Options $0.6
  Development/Legal $0.6
Final DASH Request (expenses through COD) $155.6
Project Total $163.7
* The $3.4MM includes the $2.481MM approved in the I-DASH and $0.921MM of development related expenditures and tasking letters.