## Slide 1: Infrastructure
Information Technology

## Slide 2: Infrastructure Scope
Network & Voice Infrastructure
  Data Communications
  Voice Communications
Server Infrastructure & Operations
  NT / W2k Core Infrastructure
  Unix Core Infrastructure
  Messaging
  Market Data
  Desktop / Client Management
  Business Application & DB Servers
Desktop / Customer Services

## Slide 3: Infrastructure Migration Approach
 | Day 1 Start-up | Transition Period | End State
Business Application Infrastructure | Physically separate servers. | Begin migration to NETCo data center. | All servers relocated in NETCo data center.
Core NT & UNIX Infrastructure | Separate active directory / domain. Logically separated infrastructure services. | Establish physically separate core infrastructure in NETCo data center. | Independent core infrastructure in NETCo data center.
Voice & Data Communications Network | Leverage Enron voice & data network. | Begin segregation of NETCo voice & data communications. | Independent voice & data network.

## Slide 4: Key Assumptions
Go-Live – January 20
“Physical” Separation of Application Server Platforms
Separation of Domain / Active Directory
“Logical” separation of other core infrastructure services
Leverage Enron’s network & voice capabilities for transition period (1-6 months)

## Slide 5: Migration Considerations Core Infrastructure
Active Directory / Domain Structure
Misc. Hardware Acquisition
  Approx $300k in equipment
Software / Enterprise Licenses
User / Data Migration Sequencing
Leveraging Core Infrastructure Services on Day 1
Data Center Services
Data Center Relocation Costs
Messaging

## Slide 6: Migration Considerations Data & Voice Network
Data Network Isolation
Phone number relocation (713-853 prefix)
Voice Mail
Internet Access
WAN relocation
ECN Voice Isolation
Network Security

## Slide 7: Data Communication
Scope Internet Access/WEB filtering Network Isolation/Security Data Center/Trading floor network Event monitoring | Migration Activities Day 1 - Current Enron Network leveraged during transition period Day 2 – Isolate NETCo Network Day 3 – Build/Integrate data center/trading floor network infrastructure.
Licenses Day 1 – Leverage current Day 2 – Cisco Hardware/Software and Monitoring tools | Special Migration Issues ISP/WAN connections Data Center/trading floor Location TCPIP/Multicast addressing Network Security
Notes: Vital Suite
NetCool
NerveCenter
Alert Page
Web Trends
Smart Filter
Cisco Works
Tac ACS

## Slide 8: Voice Communications
Scope Voice mail Maintain existing 713-853 block Isolate voice network | Migration Activities Day 1 – Leverage existing Enron Infrastructure Day 2 -Implement ECS Audix node Day 2 - Point 713-853 numbers to ECS Day 2 - Isolate ECS voice network
Licenses Day 1 – Leverage existing Day 2 – PBX Day 2 - IPC | Special Migration Issues Free up ECN Audix node to be used at ECS

## Slide 9: NT Core Infrastructure
Scope Active Directory File and Print Services Remote Access Backup services Version control NT naming services | Migration Activities Create active directory tree with interim inter-forest trust Define, prepare, execute common and user data migration Establish SAN infrastructure for mail, user and common directories
Licenses Funk Steel Belted Radius (remote access) TidalSoft’s SysAdmiral Remedy NetOps (custom) E-Request (custom) ChangeManagement (custom) Legato ClearCase, PVCS, MS SourceSafe | Special Migration Issues Active directory root domain name cannot be changed once created Accurate identification and migration of common and user data

## Slide 10: UNIX Core Infrastructure
Scope Naming services Network file services Time Services Back-ups Paging & Mail services | Migration Activities Day 1 – layer interim infrastructure, logically separated, on current infrastructure (e.g., DNS, NIS, paging, time) Separate NFS service (Netapp filers) Transition goal: deploy all services on separate servers.
Licenses Epage E10k Veritas Volume Manager Sun / Solaris Maintenance/Support iPlanet LDAP server NetWatch (custom developed) | Special Migration Issues Purchase of core infrastructure servers (DNS, NIS, etc) Approximately $225k for new hardware Domain name registration

## Slide 11: Messaging Infrastructure
Scope Outlook / Exchange 2000 e-mail Mail Sweeper Virus Detection / Prevention Instant Messenger Wireless e-mail (via Blackberry) Automated Faxing | Migration Activities Establish new messaging domain and infrastructure Isolate NETCo Mail cluster Migrate NETCo mail users
Licenses Exchange 2000 MailSweeper Sophos Norton Anti-Virus for Exchange Blackberry Enterprise Server Xtnd Connect / MMIS Optus FacSys | Special Migration Issues Connections / Gateways to external e-mail Communication for changing mail identities & incoming fax numbers

## Slide 12: Market Data Infrastructure
Scope Market data distribution infrastructure Market data feeds Subscription management Licensing managemetn | Migration Activities Market data infrastructure already exists in ECS for Day 1 start-up Provision, implement market data feed circuits Renegotiate Market Data contracts
Licenses Tibco Reuters I-Finance Reuters Cobra Market data content subscriptions | Special Migration Issues Circuit lead time for market data feeds (e.g., Bloomberg) Renegotiation, re-acquisition of market data contracts with vendors 2 Alteons for load balancing ($40k)

## Slide 13: Systems Monitoring & Management
Scope Event monitoring & alerting Systems management Availability reporting Batch Processing Application Monitoring | Migration Activities Installation of monitoring components on server images Establish command center facility Complete tool integration
Licenses NetCool NetIQ App/Ops Manager Lucent VitalSuite TidalSoft SysAdmiral NetWatch (custom) | Special Migration Issues 24x7 Operations Application monitoring

## Slide 14: Desktop / Client Management
Scope Application management Application metering Software distribution Antivirus Build management | Migration Activities Define Client build images Implement Application Integration environment Test build images and software distribution modules Client migration
Licenses NetInstall Symantec NAV & PCAnywhere LAN Licenser SQL Server | Special Migration Issues Deployment of new user accounts coordinated with new mail, file, and print infrastructure Potential upgrade opportunity to Windows/Office XP

## Slide 15: Customer Support Services
Scope 850+ employees of NETCo Two floors of ECS No Helpdesk function/floor support and hardware services only | Migration Activities Set up Remedy instance (shared with EOL)
Licenses Remedy | Special Migration Issues N/A