## Slide 1: ENRON SOUTH AMERICA 2001 Communication Program
Presented by
ESA Public Relations
November 2, 2000

## Slide 2: Communication Program
The program is based on certain assumptions about Enron’s evolving business model and challenges that Enron will have to overcome to successfully meet shareholder expectations
The program is predicated on the belief that the PR function should be relevant to the business units by providing “bottom line” support to their operating targets
The program is a working document that will be tailored and revised throughout the year in order to best serve ESA’s business needs

## Slide 3: Assumptions
Enron’s business strategy is to structure its operations as flexible networks to accelerate growth with minimal capital expenditures and divest non-strategic assets to redeploy capital into the higher growth and stronger-return businesses of commercial, commodity trading and risk management services
Enron has been a proponent in the Southern Cone and elsewhere of market-based reforms, including deregulation and privatization because competition reduces business costs and provides the public with better energy products and services, greater efficiency and value for customers.

## Slide 4: SWOT ANALYSIS
Strengths
  Experience
  Innovation
  Risk takers
  Intellectual Capital
  Assets
  Local presence
Weaknesses
  Negative Image
  Identity Crisis
    Externally & Internally
    Confusion of evolving business model
    Selling assets
  Not part of cartel
  Lacking media relations plan

## Slide 5: SWOT ANALYSIS
Opportunities
  Become industry leader in providing innovative energy solutions
  *Power and gas marketing
  *Total Energy Outsourcing
  Promote regional energy deregulation
  Strengthen relationships with key stakeholders
  Reposition Enron brand
Threats
  Changes in political environment
  Currency devaluation
  Reform fatigue
  Losing “seat at the table”
  Petrobras/YPF monopoly position
  Politicized energy policies
  Untrained regulators
  Competitors willing to operate in non-market economy
  Unfinished deregulation
  International NGO pressures on OPIC/IFIs

## Slide 6: Communication Goals
  Enhance Enron Image
  Publicize and Market Business Unit Services
  Create Regulatory Reform Messages to Influence Policy/Opinion Makers
  Enhance Media Relations Capabilities
  Strengthen the ESA PR Offices
  Enhance Good Corporate Citizenship/Social Responsibility
  Enhance Internal Communication Program in Partnership with HR
  Manage Effective Crisis Management Communications

## Slide 7: Enhance ESA Image
Goal
Develop a program to improve and/or build Enron’s brand in the region
Tasks
Conduct opinion survey as follow-up to September 1999 “The Corporate Image Project” by InterScience to establish comparative baseline data and analysis
Use survey findings to organize campaign to publicize/inform/educate/explain Enron’s business strategy and model

## Slide 8: Tactics– Enhance Enron Image
Task | Benefit | Responsibility | Target | Timeline
Opinion Survey | Comparative database for both media & government. relations planning | J. Bestard, M. Guerriero, K. Miceli | Brazil Argentina | 1 Q
Integrated marketing campaign trade shows | Improve stakeholder understanding of Enron business model/services | Local PR managers, K. Miceli & agency | Brazil Argentina | 1st & 2nd Q
Speakers bureau | Improve stakeholder understanding of Enron business model/services | K. Miceli/Brazil PR team | Brazil Argentina | 1st-4th Q

## Slide 9: Tactics– Enhance Enron Image
Task | Benefit | Responsibility | Target | Timeline
Media briefings/outreach | Improve stakeholder understanding of Enron business model/services | Local PR staff Media relations firm | Regional Brazil Argentina | 1st-4th Q
Newspaper/ Magazine stories (local/ international) | Improve stakeholder understanding of Enron business model/services | Local PR staff Media relations firm | Regional Brazil Argentina Venezuela | 1st-4th Q

## Slide 10: Publicize and Market Services
Goal
Promote and publicize Enron South America’s wholesale and direct sales services to government, partners, customers, and prospective clients.
Tasks
Position ESA Website as ESA’s “Business Card” through targeted ads and promotions
Promote BU businesses through campaign that brands, educates, differentiates and stimulates customer’s choice
Enhance BU business techniques and capabilities by organizing workshops in SP, Buenos Aires, Bogota and Caracas with EES, EOL, and Enron website specialists from Houston/Europe as presenters
Bring Enron branding specialist to Brazil and Argentina to present techniques for using Enron’s new branding attributes to market BU services.

## Slide 11: Tactics– Publicize and Market Services
Task | Benefit | Responsibility | Target | Timeline
Publicize ESA website | Increase customer awareness of services & business development | K. Miceli PR staff | Regional Brazil Argentina | 1st - 4th Q
BU ad campaign Develop collateral materials | Increased customer awareness of services & business development | PR staff, BU managers, Ad agency | Brazil Argentina | Develop 1Q Launch 2Q
Training courses for ESA team | TA from HQ business units/enhance working relations with HQ BUs | K. Miceli, Regional PR staff | Brazil/Arg Ven/Col | 2Q 3Q
Enron branding training | Better understanding and utilization of Enron brand/brand consistency | K. Miceli, Regional PR staff | Brazil/Arg | 1Q

## Slide 12: Tactics– Publicize and Market Services
Task | Benefit | Responsibility | Target | Timeline
Trade Shows | Increase awareness of services and brand through targeted events | K. Miceli PR staff | Regional Brazil Argentina | 1st - 4th Q
Events (Holiday parties) | Network & brand Enron with opinion makers and key customers | PR staff K. Miceli | All countries | 1st – 4th Q
World Energy Congress | International event that allows for increased branding & corporate positioning oppts | K. Miceli B. Salvador | Argentina With region & Brazil | 1-2 Q planning 3 Q implement
Sponsorships | Brand awareness at event & activities with opinion leaders & key customers | K. Miceli PR staff | Brazil Argentina | 1st – 4th Q

## Slide 13: Create Regulatory Reform Messages
Goal
Actively support/promote policies, laws and regulatory reforms that establish regional energy integration and market-based energy solutions for the region
Tasks
Conduct Survey of Policy & Opinion Makers to Identify Policy Positions
Establish Reform Priorities and Develop Strategic Plan
Hold off-site meeting with outside facilitator
Build stakeholder database
Support University/Think Tank Research/ Coordinate with Investors Chamber
  UFRJ’s Centro Brasileiro de Infra-Estrutura Project
  Enron-Princeton University/USP Project
  Institute of the Americas Brazil/Regional Energy Roundtables
  Coloquio IDEA 2001
  Brazil/Argentine think tank study on regional energy integration
Utilize Business/Industry Associations to Promote Positions
Customer Choice Program

## Slide 14: Tactics– Regulatory Reform Messages
Task | Benefit | Responsibility | Target | Timeline
Survey of policy & opinion makers | Identify key stakeholder policy positions | J. Bestard/K. Miceli | Brazil | 1Q
Off-site meeting with outside facilitator | Establish outreach and advocacy priorities | J. Bestard | Brazil | 1Q
Support university/think tank research by energy specialists | Develop data/analysis in support of reform positions. Important opinion makers become reform advocates. | J. Bestard, K. Miceli | Brazil Argentina | 1st – 4th Q

## Slide 15: Tactics– Regulatory Reform Messages
Task | Benefit | Responsibility | Target | Timeline
Business/ Industry Associations | Increases visibility, awareness and facilitates communicating messages to business leaders | J. Bestard, K. Miceli | Brazil Argentina Venezuela | 1st –4th Q
Customer Choice Program | Position Enron as advocate & facilitate new rules through ad & grassroots efforts campaign, messages | J. Bestard, Ad agency | Brazil Argentina | 1st – 2nd Q 1st – 4th Q

## Slide 16: Media Relations
Goal
Develop a strong media relations program to position ESA, effectively communicate key messages and strengthen Enron brand
Tasks
Create a press kit with executive bios, fact sheets, website brochure and collateral materials
Daily media monitoring and analysis of US, Latin America and in-country
Create comprehensive media database with key contacts/background information
Identify opportunities to inform media about Enron’s evolving business model, new energy services, projects, and positions on reform
Provide media training for Enron executives who serve as BU spokespersons
Sponsor a journalism training program through a well-respected think tank. Target energy and finance reporters

## Slide 17: Tactics– Media Relations
Task | Benefit | Responsibility | Target | Timeline
Develop/update media materials & press kits | Provides updated /accurate info (English, Portuguese & Spanish) | Local PR staff, PR firm | Regional All countries | 1st & 2nd Q
Media monitoring & weekly analysis | Allows team to evaluate Enron messaging & competitor’s positioning | Local PR staff, PR firm | Regional All countries | 1st & 4th Q
Proactive media relations | Build rapport w/ key media by sharing info on new business model & build media database | Local PR staff, PR firm | Regional Brazil Argentina | 1st & 4th Q

## Slide 18: Tactics– Media Relations
Task | Benefit | Responsibility | Target | Timeline
Journalist seminar | Increase rapport with key media & build understanding of business | Local PR staff, firm and K. Miceli | Brazil Argentina | 2nd – 3rd Q
Media training | Ensures consistency of messages by spokespersons | Local PR staff, K. Miceli | All countries | 1st & 2nd Q

## Slide 19: ESA Public Relations Team
Goal
Create a stronger PR professional staff through policies and procedures to e effectively support the business unit’s “bottom-line”
Tasks
Institute annual off-site training workshop for ESA PR team.
Develop and implement ESA media relations policies and procedures
Exchange weekly PR activity reports.
Expand PR functions in ESA countries to manage ESA website content

## Slide 20: Tactics– ESA PR Team
Task | Benefit | Responsibility | Target | Timeline
Off-site meeting with training & personnel enhancement | Build stronger ESA PR team & discuss business support | K. Miceli | Regional | 1 Q
Develop & implement media policies & procedures | Ensure proper handling of media requests and approvals of materials | K. Miceli | All countries | 1 Q
Weekly PR report | Allows team to be informed of activities | Local PR staff, K. Miceli | All countries | 1st – 4th Q
Manage ESA website content | Allows PR managers to support business while ensuring accuracy | Local PR staff, K. Miceli | All countries | 1st – 4th Q

## Slide 21: Corporate Responsibility Program
Goal
Demonstrate Enron’s commitment to the communities it serves through a strong corporate responsibility program
Tasks
Develop ESA community relations policy, with guidelines on corporate giving
Develop a plan to: (a) provide financial and technical assistance to the new United Way-Brazil office , (b) and organize an Enron Brazil employees fund-raising campaign for UW-Brazil, and expand to Enron Argentina, Venezuela and Colombia Publicize in Circuito Enron and ESA intranet website.
Conduct cost-benefit audit of current charitable giving to assess value to BU managers. Use findings to develop 2001 plan
Establish a process for reviewing and responding to requests in order to leverage and maximize our investments

## Slide 22: Tactics– Corporate Responsibility
Task | Benefit | Responsibility | Target | Timeline
Develop community relations policy | Allows ESA to define causes (e.g. technology, environment) while providing guidelines | K. Miceli | Regional All countries | 1 Q
Develop plan | Allows for budgeting and leveraging oppts. | K. Miceli | Regional Brazil, Arg & Ven | 1 Q
Cost benefit audit | Use finding to assess value to BU and develop 2001 plan | Local PR staff, K. Miceli | All countries | 1 Q
Evaluation & response process | Leverage and maximize investments | Local PR staff, K. Miceli | Regional All countries | 1st – 4th Q

## Slide 23: Internal Communication
Goal
Communicate Enron’s goals and new business plan to build morale, create commitment, productivity, innovation and continued success
Tasks
Partner with HR to develop a comprehensive program that utilizes and enhances existing tools, including eSpeak and Enron Corp. newsletters
Evaluate ESA Intranet and work with HR to make it more interactive for employees to access HR, corporate, and business unit information
Relaunch Circuito Enron to make it more regionally focused and available in Portuguese and Spanish
Launch an internal speakers bureau that includes brown bag lunches and employee meetings, allowing interaction between management team and different business groups and offices

## Slide 24: Tactics– Internal Communication
Task | Benefit | Responsibility | Target | Timeline
Use internal Corp communication tools | Keep team informed, build loyalty morale & awareness of ESA | K. Miceli | All countries | 1st – 4th Q
Evaluate, revise and update ESA Intranet | Creates interactive tool that provides HR, BU & other info. | Local PR staff, K. Miceli | All countries | 2 Q
Revamp Circuito Enron | Allows team to use this tool to communicate with all ESA employees | Local PR staff, K. Miceli | All countries | 1 Q
Internal speakers bureau (mtgs, brown bag lunches, etc.) | Provides management face time with employees | M. Padron, local PR staff, K. Miceli | All countries | 2Q launch

## Slide 25: Crisis Communication
Goal
Develop a crisis communication program that establishes processes and allows for effective communication during a crisis
Tasks
Evaluate and update crisis communication program (s) for business units and assets. Review messaging, appropriate contact information and relevance
Partner with Enron Crisis Center to participate in crisis training programs to ensure communication components meet requirements
Work with ESA PR team to ensure members know their area of responsibility and are familiar with procedures and key messages
Include a crisis communication seminar in the ESA PR off-site workshop

## Slide 26: Tactics– Crisis Communication
Task | Benefit | Responsibility | Target | Timeline
Evaluate/update existing program (s) | Ensures that these meet current situation & contain updated info | K. Miceli | All countries | 2-3Q
Crisis Communications Training | Ensures crisis communication plan is in place & reflects BU’s goals & needs | K. Miceli, local PR staff, Corp Crisis Center | All countries | 1st – 4th Q
ESA PR team crisis communication awareness | Enhances team’s familiarity w/existing programs | K. Miceli, Corp Crisis Ctr | All countries | 1 Q
Crisis communication workshop | Allows team to increase knowledge in the area | K. Miceli, Corp Crisis Ctr | All countries | 1st – 4th Q