## Slide 1
April 2001
Confidential & Proprietary
Enron Americas Management Presentation
Southwest Power Overview – LVC I & II

## Slide 2: Development Timeline
LVC I began commercial operation in May 1994
Southwest Power created by ENA to acquire LVC I on August 31, 1999
Southwest Power funded by non-recourse project debt ($54.9MM) and Enron/JEDI equity ($24MM).
LVC I repowered by replacing existing LM 6000 PA with a state-of-the-art LM 6000 PC in December 1999, reducing the heat rate and increasing capacity
LVC II is a 224 MW gas-fired generating facility under development
In process of selling toll on LVC II to Allegheny Energy Supply Company.
Objective to divest of SWP during 2001, after signing toll and start of construction of LVC II
Southwest Power

## Slide 3: Overview
Operates as a QF under PURPA
Capable of generating an average of 51 MW
Provides 45 MW of on-peak capacity and energy to Nevada Power Company (NPC) under a PPA through May 2024
Excess energy is available for merchant sales, dispatched by EPMI West Power Trading
Thermal host is a 12-acre tomato greenhouse (Sunco) that is 100% owned by Southwest Power
LVC I

## Slide 4: Development Overview
224 MW natural gas-fired plant consisting of two, two-on-one combined-cycle units (4 LM 6000 PCs) yielding a projected heat rate of 7,800 Btu/kWh (HHV)
Located adjacent to LVC I on approximately four acres currently owned by LVC I
EPC Contract signed on March 29, 2001 with Modern Continental.
Negotiating a toll for 100% of the capacity of Plant with Allegheny Energy Supply Company,LLC
LVC II

## Slide 5: Development Timeline
LVC II

## Slide 6: Permits
Site Plan
City of North Las Vegas Planning Commission approved the site plan on August 23, 2000.
Zoned industrial - Allows for power plant construction
“No Hazard to Air Navigation” determination issued by FAA on August 9, 2000
LVC II
Air Permit
Air permit issued November 2000 on behalf of LVC I as operator of LVC II
NOx and CO emissions are each limited to 2 ppmv
Wastewater Permit
Permit issued March 29, 2001

## Slide 7: Engineering, Procurement and Construction
EPC Contract signed with Modern Continental on March 29, 2001
Modern Continental bonded in the amount of the EPC Contract
Four GE LM 6000 PC Enhanced Sprint gas turbines have been purchased by E-NextGeneration from GE. The turbines will be assigned to the project at the purchaser’s closing and are scheduled to be delivered during the third quarter of 2001
High-voltage, step-up transformers for project have been purchased by E-NextGeneration from ABB and will be assigned to the new project owner at the project sale closing
Land near site has been leased for construction laydown, staging and parking.
LVC II

## Slide 8: Capital Cost Assumptions
LVC II

## Slide 9: Interconnections
Electrical Interconnect & Transmission
LVC II will interconnect with Nevada Power’s 138 kV substation at the site
  Nevada Power has completed engineering & cost estimation work
  Interconnection Agreement to be signed on or before April 27, 2001
Firm Transmission Point-to-Point Service to Mead Delivery Point
  Transmission system impact study complete
  Nevada Power to issue final Confirmation Letter by April 20, 2001
  Transmission Service Agreement required to be signed within 30 days of receipt of Confirmation Letter
  Transmission Service Agreement will be assigned to tolling party
LVC II

## Slide 10: Interconnections (continued)
Gas Interconnection
Southwest Gas Company to design, build and operate a new 12” lateral from Kern River Pipeline to the LCV II Facility.
  The proposal is competitive with building bypass option
  Bypass option still available if PUC approve is denied
Signing of agreement with Southwest Gas to be signed on or before April 27, 2001
LVC II

## Slide 11: Interconnections (continued)
Water
The City of North Las Vegas issued an invoice for $3 million on January 31, 2001 for water interconnection fees. Prior to issuance of the building permit and upon payment of this fee a Will Serve Letter is be issued.
Waste Water
City of North Las Vegas will receive the Project’s wastewater discharge
On June 16, 2000, the city provided written confirmation of its ability to accept wastewater with 3,000 mg/L of total dissolved solids
City Council to approve agreement on April 24, 2001.
LVC II

## Slide 12: Tolling Agreement
LVC II
A tolling agreement is being negotiated with Allegheny Energy Supply LLC
Capacity Payment | $12.15/kw month
Variable O&M Payment | $3.71/mwh escalating at CPI
Term | 15 Years
Delivery Point | Busbar
LD’s COD | $40,000/Day
Guaranteed Availability | 90% (12 month) / 95% (peak month)
Failure to meet availability | Adjustment to Capacity Payment
Steady State Heat Rate | 7,800 Btu/kWh
Failure to meet Heat Rate | Adjustment to Capacity Payment
Credit Rating | BBB+ (E Rating equivalent)

## Slide 13: Exit Strategy
West Power intends to finalize development, commence construction and then divest prior to commercial operations.
The expansion project, combined with the existing QF asset will be attractive to numerous generation companies:
  Proven reliable LM6000 technology
  100% controlling interest
  Location in fast-growing load pocket in short region
  15 year fixed-price tolling agreement
Pro-Forma economics are superior to those of Fountain Valley Power, which was recently sold to Black Hills Energy Capital.
Expressions of interest from Black Hills, Northland Power, Delta Power, Energy Investors Fund, Calpine.
Asset could be included in ENA effort to divest certain QF investments.
LVC II

## Slide 14: Returns
LVC II
Terminal Value | $ 450/kW |  | $ 350/kW |  | $ 250/kW | 
 | EnterpriseValue | Gain on Sale | EnterpriseValue | Gain on Sale | EnterpriseValue | Gain on Sale
Equity Discount Rate |  |  |  |  |  | 
16% | $ 223.0 | $ 30.2 | $ 220.7 | $ 27.9 | $ 218.5 | $ 25.6
17% | $ 219.1 | $ 26.3 | $ 217.1 | $ 24.3 | $ 215.1 | $ 22.3
18% | $ 215.6 | $ 22.8 | $ 213.8 | $ 21.0 | $ 212.1 | $ 19.3

## Slide 15: Recommendation
Approve $191.1MM to finance construction of Southwest Power expansion (LVCII) subject to:
  Execution of definitive tolling agreement with Allegheny Energy Supply Company
  Receipt of Electrical Transmission Agreement Confirmation
  Execution of Southwest Gas Interconnection Agreement
  Execution of Water/Wastewater Agreement
  Execution of Nevada Power Interconnection Agreement
LVC II